## User guide
User guide to completing this document
Dear user, Thank you for completing this template, do read this brief guide first. We need your help to gain a clear system view of STP programmes to transform identified services, including specialist services, improve productivity and use of infrastructure and understand key enablers. This will help us to:  Understand our ambitions better so we can begin to mobilise and co-ordinate our plans and manage risks and dependencies  Gain the appropriate level of granularity to respond to both the London region and national STP submission requirements  Anticipate and align to the Operating Plan requirements which is indicated to be accelerated this year. We realise it is a big ask to provide this amount of detailed information. It does mean, however, that, if complete, we only need to ask for information once, ultimately making it less onerous task.
We have applied formatting and used drop-down menus to help us compare and collate the information provided.
There are two separate elements of this template:
The workstream summary | in which we ask you to summarise workstream level information from 2016-17 to 20-21. We provide a worked example to indicate the level and type of information we are looking for. Highlight and summarise key information, drawing on existing documents such as PIDs, business cases or approved reports. If you would like to attach supporting documents to your email when you reply, do indicate that using the drop down menus provided.
The delivery plan: | in which we ask you to summarise workstream and intervention level information from 2016-17 to 20-21. We need a plan for each intervention. If you have fewer, leave sheets blank. If you have more, let us know. We have provided example rows, and ask you to include:  Interventions, outcomes and measures  Dependencies, constraints, enablers and risks  Financial investment (capital and revenue) and savings as well as movement in activity  A snapshot of achievement in year, particularly 16-17 deliverables required in the Operating Plan  Below the rows which capture the above there are text boxes in which to add commentary on: quality, operating plan deliverables, enablers and constraints, finance, activity and efficiency savings and social care impact. If a row / line relates to the one above - just add "Blank - remaining issues captured in line above" as shown in the example.
Support | If you need further support on completing this template, please email christopher.x.williams@uk.pwc.com. If you'd prefer to speak on the phone, do leave the number to reach you on.
With thanks and best wishes, Chris Williams, OHSEL

## Cancer summary
SEL priority workstream |  |  |  | Is delivery of the aim on track? (RAG = 1,2,3)
Transformation |  | Cancer |  | 2
Leadership |  | SRO: | Programme Manager: | Current delivery level:
|  | Andrew Eyres & David Cheesman | NA | SEL led Programme
Background |  | SEL is proud of the excellent cancer care provided, however, cancer is the leading cause of death and premature mortality across south east London. If we matched the best there would be 10,000 fewer cancer cases per annum across the UK. 43% of cancers are caused by lifestyple factors and so are potentially preventable. To develop the best possible care models and interventions for the cancer strategy it is important to understand the current health of the population of south east London - Approximately 16% of people in south east London are in the health and wellbeing group - Approximately 50% of people in south east London are experiencing inequalities or putting their health at risk. For example this could be people who drink too much or don’t take enough exercise or are living in poverty. - Approximately 25% of people in south east London are in the early stages of long term conditions. For example, a long term condition could be, diabetes, poor mental health or high blood pressure. - Approximately 9% of people in south east London are living with 3 or more long term conditions. - Approximately 1% of people in south east London are at the end of their life Through understanding our population better the strategy is able to focus on developing care models and innovations that best address the needs of the people in south east London. A key component of this is to develop a strong foundation of Community Based Care to support people to live healthier lives and reduce the number of people exposed to risk factors either by birth or behaviour. SEL has a track record of working together and developing an ACN.
Our strategic ambitions can be defined into three categories: 1. Focus on early detection 2. Better and more responsive care beginning with treatment through transition 3. Living with and beyond cancer In addition, we have had a strong track record of delivery across SEL which can be evidenced through the development of the A.C.N. Specifically, we've aligned services to take into account the variation in ages across the boroughs, impacting healthcare demand, as evidenced through our work at Queen Mary's. We have also recognised that GSTT serves a greater population than SEL, and have aligned our service delivery and supply structures to reflect the growing demand.
Case for change including best practice |  | Please set out a Case for change summary here and attach the document in which it can be found, if any
Since 2014, the Cancer Clinical Leadership Group has been working together to address a number of areas where there is scope for improvement and change: - Enabling the public to take ownership of their health and enable self management - Improving direct access for GP investigations, diagnostics & specialist advice - Improving the patient experience - Better coordination and integration across primary and secondary care and the third sector to achieve seamless care – Cancer Recovery Package -will ensure care is coordinated. - Consistently meet cancer waits standards (with a detailed review of any patient waiting over 100 days), and reduce variability of service delivery - Delivering cancer care services closer to home - Training and up-skilling e.g. primary care and integration across all sectors - Taking learning from one stop shop approaches and spread best practice - Reducing inequality of access to cancer treatments - Improving access to psychological support services Through the Community Based Care Clinical Leadership Group, we will address: - Providing better health promotion and primary prevention (obesity, smoking, pregnant women, alcohol) - Supporting more patients to achieve their wishes at their end of life
Financial case for change |  | Please summarise the underpinning financial case for change or savings attached to this programme ?
The STP has identified an estimated recurrent savings of £9.0m by 20/21 associated with the Cancer interventions. Further detail of this can be found in the delivery plan.
Programme position in August 2016 |  | Please briefly describe the most recent or current product or phase (eg report or business case)? |  | Is the document or product attached?
We have created a cancer model, which shows how our three areas of ambition have specific interventions within to support a patient holistically:
Interventions whose delivery contributes to the overall programme |  | Please list any interventions | Total FY21 recurrent saving attributed in July 2016 STP (£m) | Path for implementation
| 1 | Cancer waiting times | 1.2372 | Provider Transformation & Contracting
| 2 | Education and Training package for LCNs | 2.7404 | Supportive Programme Role with the Clinical Lead & HLP
| 3 | Coordination of Care: during diagnosis and treatment | 0.46395 | Provider Transformation & Contracting
| 4 | Multidisciplinary Diagnostic Centre: early diagnosis clinic | 1.384 | Supportive Programme Role-- A.C.N. role to drive implementation & commissioners to impact contracting
| 5 | High quality acute oncology services (AOS) across SEL | 1.9404 | Supportive Programme Role-- A.C.N. role to drive implementation
| 6 | Chemotheraphy closer to home | 0 | Supportive Programme Role-- A.C.N. role to drive implementation
| 7 | Living With and Beyond Cancer | 0 | Supportive Programme Role
Governance |  | Can you briefly describe your current governance structure for programme delivery and/or append a diagram, if available?
The SRO for CCLG is Andrew Eyres & David Chessman The following groups are established to support delivery across the system at the same level as the CCLG: -- NHSE Transforming Cancer Services -- SEL Partners The groups who report directly to the CCLG: -- Link to Community Based Care Programme -- 2x Cancer Locality Group -- Cancer Waits Groups -- SEL Accountable Clinical Network
Cancer Planning Group(key delivery group) |  | ToR Members | Current members
|  | CCG representatives Provider representatives CSU OHSEL PM SRO | Cheung, Mark (NHS BROMLEY CCG) Courtness, Ann (NHS LAMBETH CCG) Cunliffe, Anthony (NHS WANDSWORTH CCG) Chessman, David (GSTT) Eyres Andrew (NHS LAMBETH CCG) Griffin, Mairead Haire, Kate (GSTT) Moss, Teresa (NHS SOUTH EAST COMMISSIONING SUPPORT UNIT) Peart, Stephanie Valentine, Sarah (NHS BEXLEY CCG)
Objectives (in order of priority, most important first, one per cell) |  | Can you list your overarching programme objectives?
| 1 | Our overall objective is to improve patient outcomes, we will achieve that via:early detection, faster access, consistent care, and improved patient experience.
| 2 | Consistently meet cancer waits standards (with a detailed review of any patient waiting over 100 days), and reduce variability of service delivery
| 3 | Training and up-skilling e.g. primary care and integration across all sectors
| 4 | Taking learning from one stop shop approaches and spread best practice
| 5 | Better coordination and integration across primary and secondary care and the third sector to achieve seamless care – Cancer Recovery Package will ensure care is coordinated.
| 6 | Delivering cancer care services closer to home
| 7 | Improving direct access for GP investigations, diagnostics & specialist advice
| 8 | Improving the patient experience
| 9 | Reducing inequality of access to cancer treatments
| 10 | Supporting more patients to achieve their wishes at their end of life
| 11 | Improving access to psychological support services
Scope (what is in and out of scope) | In | - National Strategy - NHS Operational planning and guidance for cancer - Primary, social, and secondary care (specialist)
| Out | - Primary care prevention - screening - rare cancers - R&D - End of life care
Constraints to 2021 (in order of scale, most impactful first, one per cell) | 1 | Ability to prioritise outcomes
| 2 | Informatics & measurement
| 3 | workforce, staffing resources and availability of necessary funding
Risks to 2021 (in order of scale, most impactful first, one per cell) |  | Risk description | Mitigation summary | Risk post mitigation (RAG = 1,2,3)
| 1 | Lack of dedicated PM resource to oversee multiple delivery vehicleas within the infrastructure for a complex cancer program | Appoint a PM who has a strong understanding of national cancer programmes and the capacity to oversee and monitor the management of 7 interventions across SEL | 3
| 2 | No clear reporting of work to date within interventions to intervention leaders | Develop reporting mechanisms to inform on delivery success | 2
| 3 | Unclear of the funding needed to move forward the Training and Education Program, as well as the risk to milestones slipping | Continue to support the T&E team and provide links to both locality groups. | 3
| 4 | Changing of SEL delivery dates due to the updated NHS operational plan guidance | Discuss how SEL can include this provision | 2
Deliverables FY16/17 |  | Deliverable description | Target delivery Date | Status
| 1 | Chemo closer to home: additional QMS capacity '- Out of hospital delivery in 20/21 | Q4 16-17 | On track
| 2 | Cancer waiting times: improvement plan in place, delivery to national standards Q4 16-17 | Q4 16-17 | Not on track but plan to recover
| 3 | Training & education package for LCN | Q1 17-18 | Not on track but plan to recover
| 4 | Agreed AOS pathway with supporting infrastructure | Q4 17-18 | Not on track but plan to recover
| 5 | Coordination of Care: recovery package, care plan | Q4 17-18 | Plan in development
| 6 | Multidisciplinary Diagnostic Centre: early diagnosis clinic | Q1 18-19 | On track
| 7 | Living With and Beyond Cancer | Q1 19-20 | Plan in development

## Cancer Delivery Plan
STP DELIVERY AND FINANCIAL PLAN
SRO: |  | Andrew Eyres & David Cheesman | Programme Manager: NA | Is delivery of the workstream on track? (RAG = 1,2,3) |  | 2 | [5 empty] | Name of person who completed this document: |  |  | Email address:
[12 empty] | Organisation: | OHSEL |  | Telephone number:
Initiatives, outcomes and measures 2016-2021 |  |  |  | IMPACT | Cummulative impact (activity) | [6 empty] | DELIVERABLES: What will need to be delivered or produced for the initiative to be succesfully implemented? | [9 empty] | DEPENDENCIES | ENABLERS |  | ENABLERS (continued) |  |  |  | COMMISSIONING INTENTIONS | RISKS |  |  |  | 2016-17 | [6 empty] | 2017-18 | [6 empty] | 2018-19 | [6 empty] | 2019-20 | [6 empty] | 2020-21
# | Interventions (one per cell, repeat if relates to above) | What is the source of the goal we are trying to achieve? (1 per cell) | List all key Performance Indicators | What is the intended impact? | % 16-17 | % 17-18 | % 18-19 | % 19-20 | % 20-21 | Outcome fully achieved by (date) | Current achievement in SEL | Deliverable 1 description | Target delivery (date) | Deliverable 2 (if any) | Target delivery (date) | Deliverable 3 (if any) | Target delivery (date) | Deliverable 4 (if any) | Target delivery (date) | Deliverable 5 (if any) | Target delivery (date) | Dependencies (If more than 1, state the most impactful) | Key enabler required | Required no later than (date) | Secondary enabler required | Required no later than (date) | Supporting enabler required | Required no later than (date) | Describe how this initiative helps deliver Commissioning Intentions or relates to them | Risk description | RAG rating | Mitigation | Mitigation required by (date) | Investment Requirement £ | Expected Benefit £ | Gross Estimated Savings -£ | Tarriff | Unit of activity (KPI) | Activity change +/- | Activity impact comments | Investment Requirement £ | Expected Benefit £ | Gross Estimated Savings -£ | Tarriff | Unit of activity (KPI) | Activity change +/- | Activity impact comments | Investment Requirement £ | Expected Benefit £ | Gross Estimated Savings -£ | Tarriff | Unit of activity (KPI) | Activity change +/- | Activity impact comments | Investment Requirement £ | Expected Benefit £ | Gross Estimated Savings -£ | Tarriff | Unit of activity (KPI) | Activity change +/- | Activity impact comments | Investment Requirement £ | Expected Benefit £ | Gross Estimated Savings -£ | Tarriff | Unit of activity (KPI) | Activity change +/- | Activity impact comments
Cancer 1 | Cancer waiting times | Transformational | First to follow-up ratio | Activity shift | 50% | 75% | 100% | 100% | 100% | Q4 20-21 | Fair achievement | Create SE London Cancer Improvement Plan to address Cancer Waits Standards, including review of diagnostics demand and capacity | Q4 2016 - 17 | Timed care pathway agreed and implemented by south east London clinically-led tumour groups | Q2 2017 - 18 | Identify and define new care navigator roles that focus on the transfer of patients | Q2 2017 | Implement Joint data systems, including patient tracking systems | Q3 2017- 18 | Identify additional diagnostic and treatment capacity to deliver the 28 day faster diagnosis standard | Q3 2017- 18 | [7 empty] | Agreeing the baseline, plans to achieve and delivery of the four priority seven day standards |  |  |  |  | 0.11833 | 0.40438 | 0.28605 | 0.51316 | Appointments | -2.7599 |  | 0.22034 | 1.0117 | 0.79135 | 1.2839 | Appointments | -6.7562 |  | 0.2732 | 1.4561 | 1.1829 | 1.8478 | Appointments | -9.5053 |  | 0.3373 | 1.7554 | 1.4181 | 2.2277 | Appointments | -11.1908 |  | 0.29836 | 1.5356 | 1.2372 | 1.9486 | Appointments | -9.5597
Cancer 2 | Education and Training package for LCNs | Transformational | Non-elective length of stay | Improved performance | 0% | 0% | 50% | 75% | 100% | Q1 17-18 | Fair achievement | Conduct Baseline training needs assessment and priortise areas for screening (bowel, breast, and cervical) | Q3, 2016-17 | Roll out phase 1 of training and education program | Q1 2017-18 | Full implementation of diagnosis provisions for NICE guidelines and GP access | 2018-19 |  |  |  |  | Work with CBC to determine the prevention packages and pathways being rolled out | [7 empty] | Unclear of funding mechanisms to roll out final training packages | 2 | To determine priority training needs and mitigation plan during Locality meetings in October | 2016-10-31 | 0 | 0 | 0 | 0 | Bed days | 0 |  | 0 | 0 | 0 | 0 | Bed days | 0 |  | 0.018111 | 0.096527 | 0.078416 | 0 | Bed days | -0.41745 |  | 0.027837 | 0.14487 | 0.11703 | 0 | Bed days | -0.61211 |  | 0.038221 | 0.19671 | 0.15849 | 0 | Bed days | -0.81166
Cancer 2 | Education and Training package for LCNs | Transformational | Elective length of stay | Improved performance | 0% | 0% | 50% | 75% | 100% | Q1 17-18 | Fair achievement | Conduct Baseline training needs assessment and priortise areas for screening (bowel, breast, and cervical) | Q3, 2016-17 | Roll out phase 1 of training and education program | Q1 2017-18 | Full implementation of diagnosis provisions for NICE guidelines and GP access | 2018-19 | [16 empty] | 0 | 0 | 0 | 0 | Bed days | 0 |  | 0 | 0 | 0 | 0 | Bed days | 0 |  | 0.37799 | 2.0146 | 1.6366 | 0 | Bed days | -8.5929 |  | 0.53745 | 2.797 | 2.2596 | 0 | Bed days | -11.6509 |  | 0.56764 | 2.9214 | 2.3538 | 0 | Bed days | -11.8839
Cancer 2 | Education and Training package for LCNs | Transformational | First to follow-up ratio | Improved performance | 0% | 0% | 50% | 75% | 100% | Q4, 2019-20 | Fair achievement | [22 empty] | 0 | 0 | 0 | 0 | Appointments | 0 |  | 0 | 0 | 0 | 0 | Appointments | 0 |  | 0.017075 | 0.091005 | 0.07393 | 0.11549 | Appointments | -0.59408 |  | 0.031622 | 0.16457 | 0.13295 | 0.20884 | Appointments | -1.0491 |  | 0.037295 | 0.19194 | 0.15465 | 0.24358 | Appointments | -1.195
Cancer 2 | Education and Training package for LCNs | Transformational | Non-elective admissions | Improved performance | 0% | 0% | 50% | 75% | 100% | Q4, 2019-20 | Fair achievement | [22 empty] | 0 | 0 | 0 | 0 | FCE | 0 |  | 0 | 0 | 0 | 0 | FCE | 0 |  | 0.0081073 | 0.043209 | 0.035102 | 0.053328 | FCE | -0.0089447 |  | 0.012897 | 0.067118 | 0.054221 | 0.082836 | FCE | -0.013568 |  | 0.017708 | 0.091134 | 0.073427 | 0.11248 | FCE | -0.017992
Cancer 3 | Coordination of Care: during diagnosis and treatment | Transformational | First to follow-up ratio | Activity shift | 0% | 0% | 0% | 0% | 100% | Q4 17-18 |  | Design Recovery Package- holistic needs assessment | Q1 2017 - 18 | Ensure summary sheet is sent to GP-- care coordination from start to finish | Q2 2017 | [13 empty] | Agreeing the baseline, plans to achieve and delivery of the four priority seven day standards |  |  |  |  | 0 | 0 | 0 | 0 | Appointments | 0 |  | 0 | 0 | 0 | 0 | Appointments | 0 |  | 0 | 0 | 0 | 0 | Appointments | 0 |  | 0 | 0 | 0 | 0 | Appointments | 0 |  | 0.11189 | 0.57583 | 0.46395 | 0.73074 | Appointments | -3.5849
Cancer 4 | Multidisciplinary Diagnostic Centre: early diagnosis clinic | Transformational | Non-elective admissions | Activity shift | 50% | 50% | 75% | 100% | 100% | Q4 18- 19 |  | MDC design | Q3, 2016-17 | Roll out of multidisciplinary diagnostic centre model across SEL | Q3, 2017-18 | Evaluate outcomes of multidisciplinary diagnostic centre pilot | Q3, 2017-18 | [11 empty] | Agreeing the baseline, plans to achieve and delivery of the four priority seven day standards |  |  |  |  | 0.056183 | 0.192 | 0.13581 | 0.23696 | FCE | -0.041554 |  | 0.031702 | 0.14556 | 0.11386 | 0.17965 | FCE | -0.030826 |  | 0.024322 | 0.12963 | 0.10531 | 0.15998 | FCE | -0.026834 |  | 0.034391 | 0.17898 | 0.14459 | 0.2209 | FCE | -0.036183 |  | 0.035415 | 0.18227 | 0.14685 | 0.22495 | FCE | -0.035984
Cancer 4 | Multidisciplinary Diagnostic Centre: early diagnosis clinic | Transformational | First to follow-up ratio | Activity shift | 50% | 50% | 75% | 100% | 100% | Q4 18- 19 |  | MDC design | Q3, 2016-17 | Roll out of multidisciplinary diagnostic centre model across SEL | Q3, 2017-18 | Evaluate outcomes of multidisciplinary diagnostic centre pilot | Q3, 2017-18 | [16 empty] | 0.11833 | 0.40438 | 0.28605 | 0.51316 | Appointments | -2.7599 |  | 0.14689 | 0.67446 | 0.52757 | 0.85591 | Appointments | -4.5042 |  | 0.2049 | 1.0921 | 0.88716 | 1.3859 | Appointments | -7.129 |  | 0.3373 | 1.7554 | 1.4181 | 2.2277 | Appointments | -11.1908 |  | 0.29836 | 1.5356 | 1.2372 | 1.9486 | Appointments | -9.5597
Cancer 5 | High quality acute oncology services (AOS) across SEL | Transformational | Non-elective admissions | Improved performance | 0% | 25% | 75% | 100% | 100% | Q4 17- 18 |  | Baseline, design phoneline | Q3, 2016-17 | Go live of single Acute Oncology phone line for south east London | Q3 2017-2018 | [18 empty] | 0 | 0 | 0 | 0 | FCE | 0 |  | 0.055479 | 0.25473 | 0.19925 | 0.31439 | FCE | -0.053945 |  | 0.085126 | 0.45369 | 0.36857 | 0.55995 | FCE | -0.09392 |  | 0.12037 | 0.62643 | 0.50606 | 0.77314 | FCE | -0.12664 |  | 0.12395 | 0.63794 | 0.51399 | 0.78734 | FCE | -0.12594
Cancer 5 | High quality acute oncology services (AOS) across SEL | Transformational | Non-elective length of stay | Improved performance | 0% | 25% | 75% | 100% | 100% | Q4 17- 18 |  | Baseline, design phoneline | Q3, 2016-17 | Go live of single Acute Oncology phone line for south east London (GSTT currently in place) | Q3 2017-2018 | [18 empty] | 0 | 0 | 0 | 0 | Bed days | 0 |  | 0.20134 | 0.92446 | 0.72312 | 0 | Bed days | -4.0883 |  | 0.2445 | 1.3031 | 1.0586 | 0 | Bed days | -5.6356 |  | 0.33404 | 1.7384 | 1.4044 | 0 | Bed days | -7.3454 |  | 0.34399 | 1.7704 | 1.4264 | 0 | Bed days | -7.305
Cancer 6 | Living With and Beyond Cancer | National Requirement | EL Los reduction | Improved performance | 0% | 25% | 75% | 100% | 100% | Q4 19- 20 |  | Signed MOU | Q3, 2016-17 | Develop training and education package for primary care to support earlier detection and improved support to people living with cancer as a long term condition | Q1 17-18 | Implementation of breast, prostate and cancer patients access to stratified pathways of care | 2019-2020

## C&YP Summary
SEL priority workstream |  |  | Vision / aim | Is delivery of the aim on track? (RAG = 1,2,3)
Transformation |  | Children & Young People | South east London will adopt a holistic approach to the care of its children and young people; service design will take into account the physical, social, emotional and mental well being of the young person plus that of their carers and siblings. | 2
Leadership |  | SRO: | Programme Manager: | Current delivery level:
|  | Martin Wilkinson | James Mackenzie | SEL led Programme
Background |  | South east London has an average of 27.8% children living in poverty compared to a national average of 17.1%. It is estimated that less than 50% of our children and young people are living healthy lives It is estimated that 44% of our young people experience inequalities or are putting their health at risk The number of obese children doubles while children are at primary school 1 in 10 children and young people aged 5 - 16 suffer from a diagnosable mental health disorder – and this number is growing Our young people and their carers find that care is not joined up and that it can be hard to navigate through the different services Not everyone is working towards the same outcomes for patients; there are no universal outcome measures across the system, focussed on what patients want to achieve and that everyone has a shared goal of working towards Barriers exist between acute and community services because our workforce is not as adaptable, skilled or flexible as it needs be A lack of information sharing agreements and different IT systems currently prevents more co-ordinated and integrated care
Case for change including best practice |  | Please set out a Case for change summary here and attach the document in which it can be found, if any
Specifically in south east London, the following characteristics are shaping local demand for Children and Young People’s health services: - Children and young people account for 23% of the population in the region and we have a higher proportion of younger people, especially those aged 0-9 years. - Compared nationally, four out of six Clinical Commissioning Groups (CCGs) in south east London are in the bottom 25% for children living in poverty: - South east London has an average of 27.8% children living in poverty compared to a national average of 17.1%. - The average for CCGs in the top 25% is 10.5% - Compared nationally, five out of six CCGs in south east London are in the bottom 25% for childhood obesity (year 6 pupils). Levels range from 17.3% to 26%, which is consistently higher than the London average and significantly above the England average - 'Toxic stress’ (where children in families experience stress due to parental mental health issues, domestic violence and/or substance abuse) has a high incidence of prevalence in south east London. This is predictive of poor health and mental health outcomes (see “A Better Start’ bid from Lewisham) - There are known capacity constraints within parts of south east London. For instance, Children and Adolescent Mental Health services (CAMHS) and in the workforce (number of paediatric trained nurses)
Financial case for change |  | Please summarise the underpinning financial case for change or savings attached to this programme ?
The South East London STP CYP programme has modelled local CYP system level financial opportunity for financial year 2021 of: • Potential gross FY21 saving of £13 million [or £7.5 million] • Assumed recurrent FY21 investment costs of £1.5 million [or £0.8 million] • Potential recurrent FY21 net impact of £11.5 million [£6.7 million] Further detail of this can be found in the financial modelling pack.
Programme position in August 2016 |  | Please briefly describe the most recent or current product or phase (eg report or business case)? |  | Is the document or product attached?
STEP 1 – Stocktake & understand Alignment: Provider and CCG visits to understand strategic direction, review effectiveness of current OHSEL activity and understand areas where a SEL approach could support transformation/ add value - COMPLETE STEP 2 – Governance & Mechanisms/Vehicle: Review and reform existing OHSEL governance and structures to reflect STP shift. Define the purpose and value add of SEL level forums - IN PROGRESS (population planning network still under development. STEP 3 – Defining Action: Convene SEL Providers and Commissioners in September 2016 to review and refine SEL work plan. SEL health and care system CYP work programme under development with SEL health economy - IN PROGRESS STEP 4 – Delivery: The priority focus areas for 2016/17 are Implementing CYP Quality standards; Short Stay Paediatric Assessment Units; and Mental Health for Under 18s - ONGOING Sep 2016 – FY20/21 (progress to be assessed through STP governance structures.)
Interventions whose delivery contributes to the overall programme |  | Please list any interventions | Total FY21 recurrent saving attributed in July 2016 STP (£m) | Path for implementation
| 1 | Children's Integrated Community Teams | 1.3257 | Contracting Consideration
| 2 | CYP LQS achievement | 0.6609 | Provider transformation
| 3 | Short Stay Paediatric Units (inc. LQS) | 2.3786 | Provider transformation
| 4 | U&EC inreach / outreach | 2.2525 | Provider transformation
| 5 | Under 18 mental health | 0.16745 | Provider transformation
| 6 | Primary Prevention and Wellness | 0 | No action
Governance |  | Can you briefly describe your current governance structure for programme delivery and/or append a diagram, if available?
SRO - Martin Wilkinson SEL C&YP Network SEL C&YP Delivery Group SEL C&YP Project Group/s SEL C&YP Internal Programme Catch-Up
C&YP Delivery Group(key delivery group) |  | ToR Members | Current members
|  | SRO - Nominated C&YP CCG Chief Officer Clinical Lead – Nominated C&YP clinician DoF – Nominated C&YP CCG Director of Finance DoC – Nominated C&YP CCG Director of Commissioning Joint C&YP Commissioner – Nominated Joint Commissioner C&YP Head of Service Manager – Nominated managerial provider Mental Health Clinician – Nominated CAMHS mental health clinician Working Group/s Lead – Lead for any specific projects specified by delivery group Project Manager – OHSEL C&YP project manager Communication Lead – OHSEL Comms Lead User representative | Martin Wilkinson (NHS LEWISHAM CCG) Tina Sajjanhar (LEWISHAM AND GREENWICH NHS TRUST) Maria Millwood (NHS LAMBETH CCG) Warwick Tomsett (NHS LEWISHAM CCG) Maria Tanner (OXLEAS NHS FOUNDATION TRUST) Claire Lemer (GUY'S AND ST THOMAS' NHS FOUNDATION TRUST) Bruce Clark (SLAM) James Mackenzie (OHSEL) Sam Ridge (NHS SOUTH EAST COMMISSIONING SUPPORT UNIT)
Objectives (in order of priority, most important first, one per cell) |  | Can you list your overarching programme objectives?
| 1 | Improve family resilience to keep children & young people physically & mentally well
| 2 | Children & young people will be able to access more joined up care in the community
| 3 | Ensuring access to the right service quickly & effectively – no wrong door
| 4 | Development of a paediatric assessment & short stay unit, working closely with community services to support children & young people back to home/school to reduce lengthier hospital stays
| 5 | When specialist support is needed the support is there quickly & effectively
| 6 | Less variation when transitioning into adult services for young people with long term conditions.
Scope (what is in and out of scope) | In | N/A
| Out | N/A
Constraints to 2021 (in order of scale, most impactful first, one per cell) | 1 | N/A
| 2 | N/A
Risks to 2021 (in order of scale, most impactful first, one per cell) |  | Risk description | Mitigation summary | Risk post mitigation (RAG = 1,2,3)
| 1 | 4 of 5 SSPAUs in SEL are already in operation so financial oportunity may be smaller than modelled | SSPAU evaluation and recommendations should identify whether various SSPAUs models are delivering expected benefits. If evaluation shows they do not fulfil wholly expected model e.g. in/out reach, MH aspects – then plans to be developed to achieve expectations. | 1
| 2 | Pressure on Local Authority commissioning and provision of services for CYP. In particular services that support the general health and wellbeing of CYP such as public health programmes, school nursing provision, speech and language therapy services etc. | Continue to strengthen Local Authority voice and engagement in SEL CYP system meetings and delivery structures to encourage whole system thinking in regards to decisions about future funding priorities. | 1
| 3 | Failure to make appropriate connections with LCN/CBC delivery for CYP e.g. in terms of LTCs, developmental needs, and transition | Regular engagement through the five year plan with CBC structures to outline required CYP interface and expectations with emerging structures. | 2
| 4 | Availability of suitably trained staff to deliver transformed models of care and long lead times on developing the required competencies for skill mix solutions | Workforce enabler engaged to explore solutions | 2
| 5 | No SEL level CYP network currently in place to scope and deliver 'do once across SEL' interventions. Delivery plans are currently high level | CYP system level meetings starting to take place although the remit and breadth of membership requires revision. | 3
Deliverables FY16/17 |  | Deliverable description | Target delivery Date | Status
| 1 | Agreed CYP Acute Care Standards for standardised commissioning intentions | Q3, 2016-17 | On track
| 2 | SEL Peer review of London Acute Care standards | Q4, 2016-17 | On track
| 3 | Implementation of CYP Acute Care Standards | Q1, 2017-18 | On track
| 4 | SSPAU evaluation complete | Q4, 2016-17 | On track
| 5 | CYPHP Programme funding secured and underway | Q4, 2016-17 | On track
| 6 | Tier 4 Specialised CAMHS Pathway Plan | Q4, 2016-17 | On track
| 7 | SEL Asthma Audit Complete | Q3, 2016-17 | On track
| 8 | STP link into Local Transformation Plan Updates | Q3, 2016-17 | On track
| 9 | U18 MH work programme defined and specified | Q3, 2016-17 | On track
| 10 | 2016/17 Projects defined and specified | Q3, 2016-17 | On track

## C&YP Delivery Plan
STP DELIVERY AND FINANCIAL PLAN
SRO: Martin Wilkinson |  |  | Programme Manager: James Mackenzie | Is delivery of the workstream on track? (RAG = 1,2,3) |  | 2 | [5 empty] | Name of person who completed this document: |  |  | Email address:
[12 empty] | Organisation: | OHSEL |  | Telephone number:
Initiatives, outcomes and measures 2016-2021 |  |  |  | IMPACT | Cummulative impact (activity) | [6 empty] | DELIVERABLES: What will need to be delivered or produced for the initiative to be succesfully implemented? | [9 empty] | DEPENDENCIES | ENABLERS |  | ENABLERS (continued) |  |  |  | COMMISSIONING INTENTIONS | RISKS |  |  |  | 2016-17 | [6 empty] | 2017-18 | [6 empty] | 2018-19 | [6 empty] | 2019-20 | [6 empty] | 2020-21
# | Interventions (one per cell, repeat if relates to above) | What is the source of the goal we are trying to achieve? (1 per cell) | List all key Performance Indicators | What is the intended impact? | % 16-17 | % 17-18 | % 18-19 | % 19-20 | % 20-21 | Outcome fully achieved by (date) | Current achievement in SEL | Deliverable 1 description | Target delivery (date) | Deliverable 2 (if any) | Target delivery (date) | Deliverable 3 (if any) | Target delivery (date) | Deliverable 4 (if any) | Target delivery (date) | Deliverable 5 (if any) | Target delivery (date) | Dependencies (If more than 1, state the most impactful) | Key enabler required | Required no later than (date) | Secondary enabler required | Required no later than (date) | Supporting enabler required | Required no later than (date) | Describe how this initiative helps deliver Commissioning Intentions or relates to them | Risk description | RAG rating | Mitigation | Mitigation required by (date) | Investment Requirement £ | Expected Benefit £ | Gross Estimated Savings -£ | Tarriff | Unit of activity (KPI) | Activity change +/- | Activity impact comments | Investment Requirement £ | Expected Benefit £ | Gross Estimated Savings -£ | Tarriff | Unit of activity (KPI) | Activity change +/- | Activity impact comments | Investment Requirement £ | Expected Benefit £ | Gross Estimated Savings -£ | Tarriff | Unit of activity (KPI) | Activity change +/- | Activity impact comments | Investment Requirement £ | Expected Benefit £ | Gross Estimated Savings -£ | Tarriff | Unit of activity (KPI) | Activity change +/- | Activity impact comments | Investment Requirement £ | Expected Benefit £ | Gross Estimated Savings -£ | Tarriff | Unit of activity (KPI) | Activity change +/- | Activity impact comments
CYP 1 | Children's Integrated Community Teams | Transformational | Non-elective admissions (under 18s) | Activity shift | 0% | 10% | 40% | 75% | 100% | Q4, 2020-21 | Fair achievement | Piloting of multi-disciplinary teams that use the workforce in new or different ways to provide specialist intervention in community settings (CYPHP) | Q4, 2017-18 | Supporting the development and south east London implementation of Healthy London Partnership priorities and outputs e.g. asthma toolkit. | Q4, 2017-18 | Integrated Care Model developed for children with LTCs | Q4, 2018-19 |  |  |  |  | Local Care Networks | Workforce | Q3, 2017-18 |  |  |  |  | Agreeing the baseline, plans to achieve and delivery of the four priority seven day standards | Availability of suitably trained staff to deliver transformed models of care and long lead times on developing the required competencies for skill mix solutions | 2 | Workforce enabler engaged to explore solutions | Q3, 2017-18 | 0 | 0 | 0 | 0 | FCE | 0 |  | 0.036069 | 0.4187 | 0.38263 | 0.25201 | FCE | -0.2846 |  | 0.048077 | 0.45055 | 0.40247 | 0.27118 | FCE | -0.29936 |  | 0.066253 | 0.60235 | 0.5361 | 0.36255 | FCE | -0.39084 |  | 0.058312 | 0.52429 | 0.46598 | 0.31557 | FCE | -0.33222
CYP 1 | Children's Integrated Community Teams | Transformational | A&E Attendances (under 18s) | Activity shift | 0% | 10% | 40% | 75% | 100% | Q4, 2020-21 | Fair achievement | / |  | / |  | / | [12 empty] | Agreeing the baseline, plans to achieve and delivery of the four priority seven day standards | Failure to make appropriate connections with LCN/CBC delivery for CYP e.g. in terms of LTCs, developmental needs, and transition | 2 | Regular engagement through the five year plan with CBC structures to outline required CYP interface and expectations with emerging structures. | Q4, 2017-18 | 0 | 0 | 0 | 0 | Attendance | 0 |  | 0.048801 | 0.56651 | 0.51771 | 0.80075 | Attendance | -4.1693 |  | 0.0811 | 0.76002 | 0.67892 | 1.0743 | Attendance | -5.4678 |  | 0.11642 | 1.0584 | 0.94202 | 1.4961 | Attendance | -7.4362 |  | 0.10759 | 0.96733 | 0.85974 | 1.3673 | Attendance | -6.6368
CYP 2 | CYP LQS achievement | National Requirement | Non-elective admissions (under 18s) | Improved performance | 0% | 25% | 50% | 100% | / | Q4, 2019-20 | Fair achievement | Agreed CYP Acute Care Standards for standardised commissioning intentions | Q3, 2016-17 | SEL Peer review of London Acute Care standards | Q4, 2016-17 | Implementation of CYP Acute Care Standards | Q1, 2017-18 | Collate and report agreed SEL CYP Dashboard measures | Q4, 2017-18 | Development of SEL CYP Network | Q1, 2017-18 |  | Contracting/commissioning | Q3, 2016-17 |  |  |  |  | Agreeing the baseline, plans to achieve and delivery of the four priority seven day standards |  |  |  |  | 0 | 0 | 0 | 0 | FCE | 0 |  | 0.030057 | 0.34892 | 0.31886 | 0.21001 | FCE | -0.23716 |  | 0.020032 | 0.18773 | 0.1677 | 0.11299 | FCE | -0.12473 |  | 0.029446 | 0.26771 | 0.23827 | 0.16114 | FCE | -0.17371 |  | 0.019437 | 0.17476 | 0.15533 | 0.10519 | FCE | -0.11074
CYP 2 | CYP LQS achievement | National Requirement | Non-elective length of stay (under 18s) | Improved performance | 0% | 25% | 50% | 100% | / | Q4, 2019-20 | Fair achievement | / |  | / |  | / |  | / |  | / | [13 empty] | 0 | 0 | 0 | 0 | Bed days | 0 |  | 0.17722 | 2.0572 | 1.88 | 0 | Bed days | -9.5161 |  | 0.060983 | 0.5715 | 0.51051 | 0 | Bed days | -2.5843 |  | 0.085403 | 0.77646 | 0.69106 | 0 | Bed days | -3.429 |  | 0.04961 | 0.44605 | 0.39644 | 0 | Bed days | -1.9237
CYP 2 | CYP LQS achievement | National Requirement | 30 day readmissions (under 18s) | Improved performance | 0% | 25% | 50% | 100% | / | Q4, 2019-20 | Fair achievement | / |  | / |  | / |  | / |  | / | [13 empty] | 0 | 0 | 0 | 0 | FCE | 0 |  | 0.0042236 | 0.04903 | 0.044806 | 0.05913 | FCE | -0.021907 |  | 0.0085788 | 0.080395 | 0.071816 | 0.096957 | FCE | -0.035113 |  | 0.012513 | 0.11377 | 0.10125 | 0.1372 | FCE | -0.048524 |  | 0.013657 | 0.12279 | 0.10913 | 0.14808 | FCE | -0.051144
CYP 3 | Short Stay Paediatric Units (inc. LQS) | Transformational | Non-elective length of stay (under 18s) | Activity shift | 0% | 25% | 50% | 75% | 100% | Q4, 2020-21 | Fair achievement | Support development of revised SSPAU Evalautaion criteria | Q3, 2016-17 | Evaluation of 5 SEL SSPAUs and implementation of recommendations | Q1, 2017-18 | [14 empty] | 4 of 5 SSPAUs in SEL are already in operation so financial oportunity may be smaller than modelled | 1 | SSPAU evaluation and recommendations should identify whether various SSPAUs models are delivering expected benefits. If evaluation shows they do not fulfil wholly expected model e.g. in/out reach, MH aspects – then plans to be developed to achieve expectations. | Q1, 2017-18 | 0 | 0 | 0 | 0 | Bed days | 0 |  | 0 | 0 | 0 | 0 | Bed days | 0 |  | 0.18295 | 1.7145 | 1.5315 | 0 | Bed days | -7.7528 |  | 0.25621 | 2.3294 | 2.0732 | 0 | Bed days | -10.2871 |  | 0.29766 | 2.6763 | 2.3786 | 0 | Bed days | -11.5421
CYP 4 | U&EC inreach / outreach | Transformational | A&E Attendances (under 18s) | Activity shift | 0% | 0% | 25% | 50% | 100% | Q4, 2020-21 | Fair achievement | Enabling Hospital at Home approaches and rapid response teams that allow specialist follow up to avoid admissions and facilitate early discharge. | Q4, 2018-19 | Strengthen primary care ability to support and treat CYP | Q4, 2019-20 | [6 empty] | Local Care Networks | [7 empty] | Availability of suitably trained staff to deliver transformed models of care and long lead times on developing the required competencies for skill mix solutions | 2 | Workforce enabler engaged to explore solutions | Q2, 2018-19 | 0 | 0 | 0 | 0 | Attendance | 0 |  | 0 | 0 | 0 | 0 | Attendance | 0 |  | 0.013517 | 0.12667 | 0.11315 | 0.17905 | Attendance | -0.91129 |  | 0.019403 | 0.17641 | 0.157 | 0.24935 | Attendance | -1.2394 |  | 0.035863 | 0.32244 | 0.28658 | 0.45577 | Attendance | -2.2123
CYP 4 | U&EC inreach / outreach | Transformational | Non-elective length of stay (under 18s) | Activity shift | 0% | 0% | 25% | 50% | 100% | Q4, 2020-21 | Fair achievement | / |  | / |  | / | [13 empty] | Failure to make appropriate connections with LCN/CBC delivery for CYP e.g. in terms of LTCs, developmental needs, and transition | 2 | Regular engagement through the five year plan with CBC structures to outline required CYP interface and expectations with emerging structures. | Q4, 2017-18 | 0 | 0 | 0 | 0 | Bed days | 0 |  | 0 | 0 | 0 | 0 | Bed days | 0 |  | 0.091475 | 0.85724 | 0.76577 | 0 | Bed days | -3.8764 |  | 0.1281 | 1.1647 | 1.0366 | 0 | Bed days | -5.1435 |  | 0.14883 | 1.3381 | 1.1893 | 0 | Bed days | -5.7711
CYP 4 | U&EC inreach / outreach | Transformational | Non-elective admissions (under 18s) | Activity shift | 0% | 0% | 25% | 50% | 100% | Q4, 2020-21 | Fair achievement | / |  | / |  | / | [17 empty] | 0 | 0 | 0 | 0 | FCE | 0 |  | 0 | 0 | 0 | 0 | FCE | 0 |  | 0.05008 | 0.46932 | 0.41924 | 0.28248 | FCE | -0.31183 |  | 0.073614 | 0.66928 | 0.59567 | 0.40284 | FCE | -0.43427 |  | 0.097187 | 0.87381 | 0.77663 | 0.52595 | FCE | -0.55369
CYP 5 | Under 18 mental health | Transformational | Non-elective admissions (under 18s) | Improved patient experience | 0% | 0% | 25% | 50% | 100% | Q4, 2020-21 | Fair achievement | Tier 4 Specialised CAMHS Pathway Plan | Q4, 2016-17 | Mapping of under 18 mental health urgent and emergency care pathways and reasons for presentation. | Q4, 2016-17 | Development of Community Crisis Care for Under 18s model | Q4, 2019-20 | Child House (CSA/CSE) model and business case developed for SEL | Q4, 2017-18 | [14 empty] | 0 | 0 | 0 | 0 | FCE | 0 |  | 0 | 0 | 0 | 0 | FCE | 0 |  | 0.010016 | 0.093864 | 0.083848 | 0.056497 | FCE | -0.062366 |  | 0.014723 | 0.13386 | 0.11913 | 0.080568 | FCE | -0.086854 |  | 0.019437 | 0.17476 | 0.15533 | 0.10519 | FCE | -0.11074
CYP 5 | Under 18 mental health | Transformational | 30 day readmissions (under 18s) | Improved patient experience | 0% | 0% | 25% | 50% | 100% | Q4, 2020-21 | Fair achievement | / |  | / |  | / |  | / | [15 empty] | 0.13277 | 0.028743 | -0.10403 | 0.034664 | FCE | -0.013125 |  | 0.00093859 | 0.010895 | 0.0099569 | 0.01314 | FCE | -0.0048681 |  | 0.0014298 | 0.013399 | 0.011969 | 0.016159 | FCE | -0.0058522 |  | 0.0018538 | 0.016854 | 0.015001 | 0.020326 | FCE | -0.0071888 |  | 0.0015174 | 0.013643 | 0.012126 | 0.016454 | FCE | -0.0056827
CYP 6 | Primary Prevention and Wellness | Transformational |  | Improved patient experience | / | / | / | / | / |  |  | Consider how CYP services interface and handover to LCN Structures | Q4, 2017-18 | Supported Transition to Adult Services | Q4, 2020-21 | [6 empty] | Local Care Networks | [7 empty] | Failure to make appropriate connections with LCN/CBC delivery for CYP e.g. in terms of LTCs, developmental needs, and transition | 2 | Regular engagement through the five year plan with CBC structures to outline required CYP interface and expectations with emerging structures. | Q4, 2017-18
Quality: Describe how quality and safety will be maintained and improved for patients and how the above mandated outcomes are being met in 2016-17. | [28 empty] | Enablers and Constraints - how do the above enablers and constraints affect delivery? | [25 empty] | Social care impact - hypothetically, if social care funding were to decrease, what would this mean for providers? Describe the impact of a -10% or -20% reduction in funding
South east London is looking to establish a CYP network where initiatives and examples of good practice can be presented and shared. The intention is to conduct quarterly reviews of system performance using an agreed CYP dashboard. Where there is variation in performance, the data will guide the network to conduct deep dives into a specific area of focus for each meeting to explore and understand this variation, share examples of good and innovative practice, standardise good practice protocols, and consider whether there are south east London level solutions to promote continuous improvement. The network will develop strengthened communication and delivery links with the South London Neonatal Operational Delivery Network to take forward standardisation work and to provide a system level clinical governance function. The SEL network will provide a forum to improve how we disseminate the lessons learnt from Child Death Overview Panel reviews of deaths across London. | [28 empty] | CYP provision involves multiple, often small providers and spans many agencies (from hospitals to schools and clubs) that creates difficulty in convening the system in a meaningful and manageable way. Difficult to get the right balance between going 'a mile wide and inch deep' or an 'inch wide and a mile deep' in the design and delivery of interventions. Workforce constraints are difficult to address at STP level without destabilising some teams or other STP footprints. This may have a knock on effect on delivery. | [25 empty] | A funding reduction causes significant risks to the CYP programme as Local Authorities commission and provide a lot of services for CYP. In particular services that support the general health and wellbeing of CYP such as public health programmes, school nursing provision, speech and language therapy services. In addition delayed transfers of care out of inpatient settings for socially complex CYP will contiune to be a real issue without suitable social care provision.

## Maternity Summary
SEL priority workstream |  |  | Vision / aim | Is delivery of the aim on track? (RAG = 1,2,3)
Transformation |  | Maternity | To place the needs of women and their families at the centre of maternity care, supporting choice and continuity of care. From preconception through to postnatal support, maternity services will be delivered by a committed and dedicated workforce, who will ensure a safe and positive experience. | 2
Leadership |  | SRO: | Programme Manager: | Current delivery level:
|  | Martin Wilkinson | James Mackenzie | SEL led Programme
Background |  | The birth rate has risen over recent years and a self assessment of whether SEL was meeting the LQS standards showed that work was required to improve the service being offered across many areas.
Case for change including best practice |  | Please set out a Case for change summary here and attach the document in which it can be found, if any
1. The birth rate has risen considerably over the last few years and although this increase is now slowing, there are increasing numbers of women with more complicated health and social care needs who require more support. 2. Employment and retention of the highly skilled workforce required to deliver a service across all health settings. 3.Capacity issues where in some instances women are diverted away from their hospital of choice. 4. Although service users are broadly satisfied with their care in SEL, recent CQC surveys have highlighted areas for improvement in particular in postnatal wards, the provision of pain relief and breastfeeding information and advice. 5. The need to meet the London Quality Standards including increased provision of consultant presence on labour wards. These standards, originally developed by senior clinicians and patients working with London Health Programmes, highlighted the fact that current service provision was inadequate to meet the needs of women giving birth in London.
Financial case for change |  | Please summarise the underpinning financial case for change or savings attached to this programme ?
The South East London STP maternity programme has modelled local maternity system level financial opportunity for financial year 2021 of: • Potential gross FY21 saving of £6.3 million • Assumed recurrent FY21 investment costs of £0.7 million • Potential recurrent FY21 net impact of £5.6 million. Further detail of this can be found in the financial modelling pack.
Programme position in August 2016 |  | Please briefly describe the most recent or current product or phase (eg report or business case)? |  | Is the document or product attached?
STEP 1 – Stocktake & understand Alignment: Provider and CCG visits to understand strategic direction, review effectiveness of current OHSEL activity and understand areas where a SEL approach could support transformation/ add value - COMPLETE STEP 2 – Governance & Mechanisms/Vehicle: Review and reform existing OHSEL governance and structures to reflect STP shift. Define the purpose and value add of SEL level forums - COMPLETE STEP 3 – Defining Action: Convene SEL Providers and Commissioners in July 2016 to review and refine SEL work plan. SEL health and care system Maternity work programme shared with SEL health economy - COMPLETE. STEP 4 – Delivery: The priority focus areas for 2016/17 are Continuity of midwifery-led care; Increasing out of labour ward births; Implementing London Quality Standards; and Implementing saving babies lives care bundle. Supporting activities are the adoption of SEL maternity dashboard, submission of early adopter expression of interest and development of a SEL level maternity specification - ONGOING Sep 2016 – FY20/21 (progress to be assessed through STP governance structures.)
Interventions whose delivery contributes to the overall programme |  | Please list any interventions | Total FY21 recurrent saving attributed in July 2016 STP (£m) | Path for implementation
| 1 | Continuity of midwife led care | 3.3589 | Provider transformation
| 2 | Increasing out of labour ward births | 1.3499 | Provider transformation
| 3 | Maternity LQS achievement | 0.19325 | Provider transformation & Contracting Consideration
| 4 | Perinatal mental health | 0.099454 | Contracting Consideration
| 5 | Postnatal and neonatal care | 0.49727 | Provider transformation
| 6 | Saving babies lives care bundle | 0.099454 | Provider transformation
| 7 | Preparing for a healthy and confident pregnancy | 0 | No action
| 8 | Access to midwifery support by 10+0 weeks | 0 | No action
Governance |  | Can you briefly describe your current governance structure for programme delivery and/or append a diagram, if available?
SRO - Martin Wilkinson Maternity Network Maternity Delivery Group Maternity Specification Group Continuity of Care and Out of Labour Ward Births Project Group Saving Babies Lives Project Group
Maternity Delivery Group(key delivery group) |  | ToR Members | Current members
|  | SRO - Nominated Maternity CCG Chief Officer Clinical Lead – Nominated Maternity clinician DoF – Nominated Maternity CCG Director of Finance DoC – Nominated Maternity CCG Director of Commissioning HoM – Nominated Head of Midwifery Mental Health Clinician – Nominated Peri-natal mental health clinician Working Group/s Lead – Lead for any specific projects specified by delivery group Project Manager – OHSEL Maternity project manager Communication Lead – OHSEL Comms Lead | Martin Wilkinson (NHS LEWISHAM CCG) Kate Langford (GSTT) Liz James (NHS GREENWICH CCG) Theresa Osborne (NHS BEXLEY CCG) Linda Machakaire (LEWISHAM AND GREENWICH NHS TRUST) James Mackenzie (OHSEL) Lucy Ing (OHSEL)
Objectives (in order of priority, most important first, one per cell) |  | Can you list your overarching programme objectives?
| 1 | Timely access to community based antenatal and postnatal maternity services which are closely linked with other community based health, social and voluntary sector services all supporting pregnancy, childbirth and new parenthood;
| 2 | Midwifery-led continuity of maternity care as standard;
| 3 | Support from clinically expert and highly-skilled multidisciplinary teams delivering high quality, kind, safe and effective services;
| 4 | Hospital based medically-led intervention when necessary;
| 5 | Support to have a normal birth, in the right location for them, with the least intervention as possible;
| 6 | Services and a workforce that promote healthy lifestyles which have a positive effect on the health outcomes for mother and child;
| 7 | Involvement and engagement with their wider family supporting healthier lifestyles and better well-being.
Risks to 2021 (in order of scale, most impactful first, one per cell) |  | Risk description | Mitigation summary | Risk post mitigation (RAG = 1,2,3)
| 1 | Providers (especially DGHs) struggle to fund increased labour ward consultant presence to 98 hours per week in line with SEL definition | Local commissioner/s informed and leading early discussions with providers regarding plans | 1
| 2 | Continuity of care and out of labour ward birth Interventions to reduce C-section rates do not deliver expected reduction | Keep anticipated benefits under review using quarterly SEL Maternity Dashboard review against continuity of care audit results and out of labour ward births indicator | 2
| 3 | Lack/unwillingness of staff to adopt working patterns that improve continuity of care | Jane Sandall commissioned work to understand different workforce configurations for continuity - act on findings | 2
| 4 | LoS reduction opportunity not as large as modelled due to volume of out of area and tertiary referrals making peer comparsions inadequate | Keep anticipated benefits under review and identify good practice in supported discharge approaches | 2
| 5 | Failure to make appropriate connections with LCN/CBC delivery for Maternity | Regular engagement through the five year plan with CBC structures to outline required Maternity interface and expectations with emerging structures. | 2
| 6 | Lack of capacity to lead change, both transformation within provider units and system development across Network by maternity clinical leaders | Early Adopter submission to Maternity transformation fund to request additional programme resource to be embedded within providers and support transformation activity. If unsuccessful in application will have to revisit mitigation strategy | 2
Deliverables FY16/17 |  | Deliverable description | Target delivery Date | Status
| 1 | Development of generic maternity specification for SEL | Q3, 2016-17 | On track
| 2 | Standardised information on birth setting choices | Q4, 2016-17 | On track
| 3 | Agreed baseline and minimum expectations on LQS for commissioning intentions | Q3, 2016-17 | On track
| 4 | Implementation of relevant Saving Babies Lives Care Bundle Interventions | Q1, 2017-18 | On track
| 5 | Collate and report agreed SEL Maternity Dashboard measures | Q4, 2016-17 | On track
| 6 | 2016/17 Projects defined and specified | Q3, 2016-17 | On track
| 7 | 2016/17 Project Progress Updates to Network | Q4, 2016-17 | On track

## Maternity Delivery Plan
STP DELIVERY AND FINANCIAL PLAN
SRO: |  |  | Programme Manager: | Is delivery of the workstream on track? (RAG = 1,2,3) |  | 2 | [5 empty] | Name of person who completed this document: |  |  | Email address:
[12 empty] | Organisation: | OHSEL |  | Telephone number:
Initiatives, outcomes and measures 2016-2021 |  |  |  | IMPACT | Cummulative impact (activity) | [6 empty] | DELIVERABLES: What will need to be delivered or produced for the initiative to be succesfully implemented? | [9 empty] | DEPENDENCIES | ENABLERS |  | ENABLERS (continued) |  |  |  | COMMISSIONING INTENTIONS | RISKS |  |  |  | 2016-17 | [6 empty] | 2017-18 | [6 empty] | 2018-19 | [6 empty] | 2019-20 | [6 empty] | 2020-21
# | Interventions (one per cell, repeat if relates to above) | What is the source of the goal we are trying to achieve? (1 per cell) | List all key Performance Indicators | What is the intended impact? | % 16-17 | % 17-18 | % 18-19 | % 19-20 | % 20-21 | Outcome fully achieved by (date) | Current achievement in SEL | Deliverable 1 description | Target delivery (date) | Deliverable 2 (if any) | Target delivery (date) | Deliverable 3 (if any) | Target delivery (date) | Deliverable 4 (if any) | Target delivery (date) | Deliverable 5 (if any) | Target delivery (date) | Dependencies (If more than 1, state the most impactful) | Key enabler required | Required no later than (date) | Secondary enabler required | Required no later than (date) | Supporting enabler required | Required no later than (date) | Describe how this initiative helps deliver Commissioning Intentions or relates to them | Risk description | RAG rating | Mitigation | Mitigation required by (date) | Investment Requirement £ | Expected Benefit £ | Net Estimated Savings -£ | Tarriff | Unit of activity (KPI) | Activity change +/- | Activity impact comments | Investment Requirement £ | Expected Benefit £ | Net Estimated Savings -£ | Tarriff | Unit of activity (KPI) | Activity change +/- | Activity impact comments | Investment Requirement £ | Expected Benefit £ | Net Estimated Savings -£ | Tarriff | Unit of activity (KPI) | Activity change +/- | Activity impact comments | Investment Requirement £ | Expected Benefit £ | Net Estimated Savings -£ | Tarriff | Unit of activity (KPI) | Activity change +/- | Activity impact comments | Investment Requirement £ | Expected Benefit £ | Net Estimated Savings -£ | Tarriff | Unit of activity (KPI) | Activity change +/- | Activity impact comments
Maternity 1 | Continuity of midwife led care | Transformational | Reduced C-sections (total, planned, unplanned) Improvement Continuity of care audit (6 monthly) | Improved outcomes | 0% | 25% | 50% | 100% | / | Q4, 2019-20 | Fair achievement | Standardised information offer for women in SEL to allow informed choices about care and place of birth | Q4, 2016-17 | Develop standardised SEL care pathways for women with medical complexity and social complexity | Q4, 2018-19 | Explore SEL arrangements for using independent sector providers | Q4, 2017-18 | Standardisation of protocols and guidelines | Q4, 2017-18 |  |  | Establishment of Local Care Networks | Workforce | Q1, 2018-19 |  |  |  |  | Agreeing the baseline, plans to achieve and delivery of the four priority seven day standards | Continuity models involve working patterns that are unattractive to midwifery staff | 2 | Jane Sandall commissioned work to understand different workforce configurations for continuity | Q1, 2018-19 | 0 | 0 | 0 | 0 | FCE | 0 |  | 0.034553 | 0.39734 | 0.36278 | 0.45375 | FCE | -0.13946 |  | 0.06668 | 0.62191 | 0.55523 | 0.71021 | FCE | -0.21337 |  | 0.13337 | 1.2125 | 1.0792 | 1.3847 | FCE | -0.40626 |  | 0.14086 | 1.2665 | 1.1256 | 1.4463 | FCE | -0.41438
Maternity 1 | Continuity of midwife led care | Transformational | Increase in Obstetrics to Midwife-led (normal births) Increase in Number of women delivered at home, in MLU or birth centre with midwife present including both planned and unplanned births at home and other location excluding births before arrival of midwife (BBA) and ambulance Improvement Continuity of care audit (6 monthly) | Improved outcomes | 0% | 25% | 50% | 100% | / | Q4, 2019-20 | Fair achievement | / |  | / |  | / |  | / | [11 empty] | Improved continuity does not result in anticipated reductions in C-sections and LoS and increased out of labour ward births | 2 | Keep anticipated benefits under review using quarterly SEL Maternity Dashboard review against continuity of care audit results | Q1, 2017-18 | 0 | 0 | 0 | 0 | FCE | 0 |  | 0.031922 | 0.36708 | 0.33516 | 0.45012 | FCE | -0.24653 |  | 0.061603 | 0.57455 | 0.51295 | 0.70452 | FCE | -0.3772 |  | 0.12321 | 1.1202 | 0.99699 | 1.3736 | FCE | -0.71818 |  | 0.13013 | 1.17 | 1.0399 | 1.4347 | FCE | -0.73254
Maternity 1 | Continuity of midwife led care | Transformational | Reduced LoS (Obstetrics: All births) Improvement Continuity of care audit (6 monthly) | Improved outcomes | 0% | 25% | 50% | 100% | / | Q4, 2019-20 | Fair achievement | / |  | / | [15 empty] | Failure to make appropriate connections with LCN/CBC delivery for Maternity | 2 | Regular engagement through the five year plan with CBC structures to outline required Maternity interface and expectations with emerging structures. | Q4, 2017-18 | 0 | 0 | 0 | 0 | Bed days | 0 |  | 0.072151 | 0.82967 | 0.75752 | 0 | Bed days | -3.5565 |  | 0.1356 | 1.2647 | 1.1291 | 0 | Bed days | -5.3059 |  | 0.16161 | 1.4693 | 1.3077 | 0 | Bed days | -6.0272 |  | 0.14935 | 1.3428 | 1.1934 | 0 | Bed days | -5.3793
Maternity 2 | Increasing out of labour ward births | Transformational | Reduced C-sections (total, planned, unplanned) | Activity shift | 0% | 50% | 100% | / | / | Q4, 2018-19 | Fair achievement | Standardised criteria for accessing midwifery-led units (MLU) | Q4, 2017-18 | Standardised information offer for women in SEL to allow informed choices about care and place of birth | Q4, 2016-17 | Audit suitability for midwifery led settings against actually delivered in midwifery led settings | Q4, 2017-18 | [16 empty] | 0 | 0 | 0 | 0 | FCE | 0 |  | 0.040312 | 0.46356 | 0.42325 | 0.52938 | FCE | -0.1627 |  | 0.077794 | 0.72556 | 0.64776 | 0.82857 | FCE | -0.24893 |  | 0.077797 | 0.70731 | 0.62951 | 0.80773 | FCE | -0.23698 |  | 0.082167 | 0.73877 | 0.6566 | 0.84366 | FCE | -0.24172
Maternity 2 | Increasing out of labour ward births | Transformational | Increase in Obstetrics to Midwife-led (normal births) Increase in Number of women delivered at home, in MLU or birth centre with midwife present including both planned and unplanned births at home and other location excluding births before arrival of midwife (BBA) and ambulance | Activity shift | 0% | 50% | 100% | / | / | Q4, 2018-19 | Fair achievement | / |  | / |  | / | [17 empty] | 0 | 0 | 0 | 0 | FCE | 0 |  | 0.042563 | 0.48944 | 0.44688 | 0.60016 | FCE | -0.32871 |  | 0.082138 | 0.76607 | 0.68393 | 0.93936 | FCE | -0.50293 |  | 0.082141 | 0.7468 | 0.66466 | 0.91573 | FCE | -0.47879 |  | 0.086755 | 0.78002 | 0.69326 | 0.95647 | FCE | -0.48836
Maternity 3 | Maternity LQS achievement | National Requirement | Reduced C-sections (total, planned, unplanned) Improvements in CYP Acute Care Standards peer review Increase in the number of hours per week that a consultant obstetrician is present in the obstetric-led labour ward. The consultant is physically present on labour ward and has no other clinical commitments. Planned caesarean section lists are covered by a separate consultant. | Improved performance | 0% | 50% | 100% | / | / | Q4, 2018-19 | Fair achievement | Development of standardised SEL maternity specification | Q3, 2016-17 | SEL wide LQS commissioning intentions | Q3, 2016-17 | Provider/Commissioner agreement on plans to meet consultant presence on labour ward trajectory | Q2, 2017-18 | [5 empty] | Contracting/commissioning | Q3, 2016-17 | [5 empty] | Providers (especially DGHs) struggle to fund increased labour ward consultant presence to 98 hours per week in line with SEL definition | 1 | Local commissioner/s informed and leading early discussions with providers regarding plans | Q1, 2018-19 | 0 | 0 | 0 | 0 | FCE | 0 |  | 0.0057589 | 0.066223 | 0.060464 | 0.075625 | FCE | -0.023243 |  | 0.011113 | 0.10365 | 0.092538 | 0.11837 | FCE | -0.035562 |  | 0.011114 | 0.10104 | 0.08993 | 0.11539 | FCE | -0.033855 |  | 0.011738 | 0.10554 | 0.0938 | 0.12052 | FCE | -0.034532
Maternity 3 | Maternity LQS achievement | National Requirement | Reduced LoS (Obstetrics: All births) Improvements in CYP Acute Care Standards peer review Increase in the number of hours per week that a consultant obstetrician is present in the obstetric-led labour ward. The consultant is physically present on labour ward and has no other clinical commitments. Planned caesarean section lists are covered by a separate consultant. | Improved performance | 0% | 50% | 100% | / | / | Q4, 2018-19 | Fair achievement | / |  | / |  | / | [17 empty] | 0 | 0 | 0 | 0 | Bed days | 0 |  | 0.012025 | 0.13828 | 0.12625 | 0 | Bed days | -0.59275 |  | 0.022601 | 0.21079 | 0.18819 | 0 | Bed days | -0.88432 |  | 0.013467 | 0.12244 | 0.10897 | 0 | Bed days | -0.50227 |  | 0.012446 | 0.1119 | 0.099454 | 0 | Bed days | -0.44827
Maternity 4 | Perinatal mental health | Transformational | Reduced LoS (Obstetrics: All births) | Improved patient experience | / | 0% | 0% | 100% | / | Q4, 2019-20 | Fair achievement | Perinatal mental health bid - Waves 1 and 2 | Q4, 2016-17 | Adopting good practice perinatal mental health specification developed by London Mental Health Clincial Network | Q1, 2019-20 | [7 empty] | Contracting/commissioning | Q4, 2018-19 | [9 empty] | 0 | 0 | 0 | 0 | Bed days | 0 |  | 0 | 0 | 0 | 0 | Bed days | 0 |  | 0 | 0 | 0 | 0 | Bed days | 0 |  | 0.013467 | 0.12244 | 0.10897 | 0 | Bed days | -0.50227 |  | 0.012446 | 0.1119 | 0.099454 | 0 | Bed days | -0.44827
Maternity 5 | Postnatal and neonatal care | Transformational | Reduced LoS (Obstetrics: All births) Improvement Postnatal Audit (6 monthly) | Improved patient experience | / | / | / | 50% | 100% | Q4, 2020-21 | Fair achievement | Prioritising breastfeeding initiation and continuation | Q4, 2018-19 | Improved birth communication notification to GPs and coordination through LCN structures | Q1, 2018-19 | SEL input into London Maternity Clinical Network workstream and implementation of outputs | Q3, 2018-19 | [16 empty] | 0 | 0 | 0 | 0 | Bed days | 0 |  | 0 | 0 | 0 | 0 | Bed days | 0 |  | 0 | 0 | 0 | 0 | Bed days | 0 |  | 0.033668 | 0.3061 | 0.27243 | 0 | Bed days | -1.2557 |  | 0.062228 | 0.5595 | 0.49727 | 0 | Bed days | -2.2414
Maternity 6 | Saving babies lives care bundle | Transformational | Reduced LoS (Obstetrics: All births) Decrease in Stillbirth rate per 1000 births after 23+6 weeks gestation excluding TOPs | Improved performance | 0% | 25% | 50% | 100% | / | Q4, 2019-20 | Fair achievement | Reducing smoking in pregnancy (Carbon monoxide (CO) testing of all pregnant women at antenatal booking appointment and referral, as appropriate, to a stop smoking service/specialist) | Q2, 2017-18 | Risk assessment and surveillance of fetal growth | Q2, 2017-18 | Raising awareness of reduced fetal movement | Q2, 2017-18 | Effective fetal montioring during labour | Q2, 2017-18 |  |  | Ultrasound capacity | Workforce | Q1, 2017-18 | Infrastructure (estates) | Q1, 2017-18 |  |  |  | Insufficient ultrasound capacity to provide scanning requirements | 2 | Workforce enabler engaged to explore solutions | Q1, 2017-18 | 0 | 0 | 0 | 0 | Bed days | 0 |  | 0.0060126 | 0.06914 | 0.063127 | 0 | Bed days | -0.29637 |  | 0.0113 | 0.10539 | 0.094094 | 0 | Bed days | -0.44216 |  | 0.013467 | 0.12244 | 0.10897 | 0 | Bed days | -0.50227 |  | 0.012446 | 0.1119 | 0.099454 | 0 | Bed days | -0.44827
Maternity 7 | Preparing for a healthy and confident pregnancy | Transformational | n/a | Improved patient experience | / | / | / | / | / |  |  | Consider how maternity services interface and hand-in/handover to LCN structures | Q4, 2017-18 | [8 empty] | Establishment of Local Care Networks | [6 empty] | Agreeing the baseline, plans to achieve and delivery of the four priority seven day standards | Failure to make appropriate connections with LCN/CBC delivery for Maternity | 2 | Regular engagement through the five year plan with CBC structures to outline required Maternity interface and expectations with emerging structures. | Q4, 2017-18
Maternity 8 | Access to midwifery support by 10+0 weeks | Transformational | Increased number of first booking appointments completed successfully by 10+0 days | Improved patient experience | / | / | / | / | / | Q4, 2020-21 | Fair achievement | Mapping and review of current community service footprints over LCN Footprints | Q2, 2017-18 | Understanding what prevents women from seeking care early and overcoming barriers | Q4, 2017-18 | [13 empty] | Agreeing the baseline, plans to achieve and delivery of the four priority seven day standards
Quality: Describe how quality and safety will be maintained and improved for patients and how the above mandated outcomes are being met in 2016-17. | [28 empty] | Enablers and Constraints - how do the above enablers and constraints affect delivery? | [25 empty] | Social care impact - hypothetically, if social care funding were to decrease, what would this mean for providers? Describe the impact of a -10% or -20% reduction in funding
South east London already has a well established and attended maternity network where initiatives and examples of good practice are presented and shared. To build on this foundation the south east London maternity system is planning to conduct quarterly reviews of provider performance using the agreed maternity dashboard. Where there is variation in performance, the data will guide the network to conduct deep dives into a specific area of focus for each meeting to explore and understand this variation, share examples of good and innovative practice, standardise good practice protocols, and consider whether there are south east London level solutions to promote continuous improvement. The maternity network has also strengthened communication and delivery links with the South London Perinatal Mental Health network and South London Neonatal Operational Delivery Network to take forward standardisation work and to provide a system level clinical governance function. The SEL network is supporting the London Maternity Network to improve how we disseminate the lessons learnt from reviews of maternal and neonatal deaths across London. | [28 empty] | Workforce constraints are difficult to address at STP level without destabilising some teams or other STP footprints. This may have a knock on effect on delivery. | [25 empty] | A funding reduction would effect the design and delivery of the multi-agency approach in developign a care pathway for women with social complexity .

## Planned Care Summary
SEL priority workstream |  |  | Vision / aim | Is delivery of the aim on track? (RAG = 1,2,3)
Transformation |  | Planned Care | A seamless, high quality planned care service that enables patients to be seen by the right person, in the right place, at the right time. | 2
Leadership |  | SRO: | Programme Manager: | Current delivery level:
|  | Sarah Blow | Tom Henderson | SEL led Programme
Background |  | The planned care model has been developed in collaboration, drawing on insight provided by service users, community members, providers and commissioners. We have used these sessions to gather patient perspectives on quality and value. This was in the form of events that created an opportunity for communities and patients to explore proposed changes to the planned Care model and find solutions together to meet specific challenges identified in the case for change. The experiences and perspectives of patients are integral to the development of a truly service user centred model. Patients and community members have been consulted through a variety of mechanisms. Their insight has been woven into the specificity of the Planned care model design. Importantly, the model design recognises the need for a continuous quality improvement culture during implementation and delivery whereby providers and commissioners act as system stewards facilitating a feedback and improvement cycle underpinned by the voice of the patient.
Case for change including best practice |  | Please set out a Case for change summary here and attach the document in which it can be found, if any
The Case for Change: What are the opportunities for improving Planned Care? - Everyone has the same standard of care - Planned Care is a very broad subject, the Planned Care CLG is going to focus initially on 3 key high volume areas Muscular Skeletal, Ophthalmology & Diagnostics. - Elective Care Centres - Learn from examples of what has worked well for patient care -Patients are well prepared for their operation/procedure & are helped to go home quickly & safely afterwards. Discharge is planned early to prevent delays & ensure rehabilitation support is in place. - More information is available for patients about what will happen to them, empowering them to have more choice and control over their care. - GPs have greater access to a range of diagnostics - Decision making tools for GPs - Time from first appointment, to test, to getting results could be quicker and more efficient - Shared IT systems so that different services have access to notes - Opportunities for different contracting to improve outcomes, allow future flexibility; commissioners and providers co-producing pathways; incentivising change and sharing risk
Financial case for change |  | Please summarise the underpinning financial case for change or savings attached to this programme ?
The STP has identified recurrent savings of £40.7m associated with the Planned Care interventions. Further detail of this can be found in the financial modelling pack.
Programme position in August 2016 |  | Please briefly describe the most recent or current product or phase (eg report or business case)? |  | Is the document or product attached?
Interventions whose delivery contributes to the overall programme |  | Please list any interventions | Total FY21 recurrent saving attributed in July 2016 STP (£m) | Path for implementation
| 1 | Efficiencies in other planned care specialties | 27.543 | Provider Transformation & Contracting Consideration
| 2 | EOC: Clinical pathway reviews | 0.93974 | Contracting Consideration
| 3 | EOC: Efficiencies & economies of scale | 3.9673 | Contracting Consideration
| 4 | Trust Level Efficiency Savings | 3.7132 | Provider Transformation
| 5 | Diagnostics: Enabled Network Solutions | 0 | No action
Governance |  | Can you briefly describe your current governance structure for programme delivery and/or append a diagram, if available?
SRO: Sarah Blow Planned Care Planning Group MSK Pathway Group Orthopaedic Clinical Working Group
Planned Care Planning Group (key delivery group) |  | ToR Members | Current members
|  | SRO OHSEL PM CCG Representatives | Blow Sarah (NHS BEXLEY CCG) Easton Mark (NHS SOUTHWARK CCG) Henderson Tom (NHS SOUTHWARK CCG) Hines Malcolm (NHS SOUTHWARK CCG) McGrath Moira (NHS LAMBETH CCG) 'Nick Jones'
Objectives (in order of priority, most important first, one per cell) |  | Can you list your overarching programme objectives?
| 1 | 1. The development of fundamental service standards for commissioning planned care across south east London: a). standards and a common commissioning approach across south east London b). standard outcomes expected within commissioning arrangements based on best practice delivery of interventions c). incentives to deliver appropriate care within the most appropriate setting in line with evidence on outcome
| 2 | 2. The development of fundamental standards for provision of planned care across south east London. a). south east London shared standards across the pathway from referral to discharge b). evidence based, best practice delivery of planned care interventions c). shared understanding of discharge planning linked with service provision outside hospital
| 3 | 3. All services are delivered in the most efficient and effective way: a). reducing lengths of stay and waits b). minimising recovery times c). Improving clinical outcomes (for example reducing recovery times and infection rates) d). effective rehabilitation and reablement
Risks to 2021 (in order of scale, most impactful first, one per cell) |  | Risk description | Mitigation summary | Risk post mitigation (RAG = 1,2,3)
1
2
3
4
5

## Planned Care Delivery Plan
STP DELIVERY AND FINANCIAL PLAN
SRO: |  |  | Programme Manager: | Is delivery of the workstream on track? (RAG = 1,2,3) |  | 2 | [5 empty] | Name of person who completed this document: |  |  | Email address:
[12 empty] | Organisation: | OHSEL |  | Telephone number:
Initiatives, outcomes and measures 2016-2021 |  |  |  | IMPACT | Cummulative impact (activity) | [6 empty] | DELIVERABLES: What will need to be delivered or produced for the initiative to be succesfully implemented? | [9 empty] | DEPENDENCIES | ENABLERS |  | ENABLERS (continued) |  |  |  | COMMISSIONING INTENTIONS | RISKS |  |  |  | 2016-17 | [6 empty] | 2017-18 | [6 empty] | 2018-19 | [6 empty] | 2019-20 | [6 empty] | 2020-21
# | Interventions (one per cell, repeat if relates to above) | What is the source of the goal we are trying to achieve? (1 per cell) | List all key Performance Indicators | What is the intended impact? | % 16-17 | % 17-18 | % 18-19 | % 19-20 | % 20-21 | Outcome fully achieved by (date) | Current achievement in SEL | Deliverable 1 description | Target delivery (date) | Deliverable 2 (if any) | Target delivery (date) | Deliverable 3 (if any) | Target delivery (date) | Deliverable 4 (if any) | Target delivery (date) | Deliverable 5 (if any) | Target delivery (date) | Dependencies (If more than 1, state the most impactful) | Key enabler required | Required no later than (date) | Secondary enabler required | Required no later than (date) | Supporting enabler required | Required no later than (date) | Describe how this initiative helps deliver Commissioning Intentions or relates to them | Risk description | RAG rating | Mitigation | Mitigation required by (date) | Investment Requirement £ | Expected Benefit £ | Gross Estimated Savings -£ | Tarriff | Unit of activity (KPI) | Activity change +/- | Activity impact comments | Investment Requirement £ | Expected Benefit £ | Gross Estimated Savings -£ | Tarriff | Unit of activity (KPI) | Activity change +/- | Activity impact comments | Investment Requirement £ | Expected Benefit £ | Gross Estimated Savings -£ | Tarriff | Unit of activity (KPI) | Activity change +/- | Activity impact comments | Investment Requirement £ | Expected Benefit £ | Gross Estimated Savings -£ | Tarriff | Unit of activity (KPI) | Activity change +/- | Activity impact comments | Investment Requirement £ | Expected Benefit £ | Gross Estimated Savings -£ | Tarriff | Unit of activity (KPI) | Activity change +/- | Activity impact comments
Planned Care 1 | Efficiencies in other planned care specialties | Transformational | Economies of scale (Ophthalmology) | Activity shift | 0% | 0% | 33% | 67% | 100% | Q4, 2020-21 |  | Undertake stocktake of opthlamology reference costs and areas of opportunity across SEL providers | Q4, 2016-17 | [15 empty] | Agreeing the baseline, plans to achieve and delivery of the four priority seven day standards |  |  |  |  | 0 | 0 | 0 | 0 | £ | 0 |  | 0 | 0 | 0 | 0 | £ | 0 |  | 0.1187 | 1.1363 | 1.0176 | 0 | £ | 0 |  | 0.16738 | 1.5479 | 1.3806 | 0 | £ | 0 |  | 0.17631 | 1.5852 | 1.4089 | 0 | £ | 0
Planned Care 1 | Efficiencies in other planned care specialties | Transformational | Other cost efficiencies | Activity shift | 0% | 0% | 33% | 67% | 100% | Q4, 2020-21 | Fair achievement | Develop sequence and timescales of planned care specialities in line with Professor Briggs' national review of planned care. Define interventions; either SEL wide consolidation/reconfiguration (building on model used for EOC)or pathway improvement/efficiency target in existing providers as appropriate | Q4, 2016-17 | [15 empty] | Agreeing the baseline, plans to achieve and delivery of the four priority seven day standards |  |  |  |  | 0 | 0 | 0 | 0 | £ | 0 |  | 0 | 0 | 0 | 0 | £ | 0 |  | 2.1996 | 21.0561 | 18.8565 | 0 | £ | 0 |  | 3.1046 | 28.7108 | 25.6062 | 0 | £ | 0 |  | 3.2704 | 29.4045 | 26.1341 | 0 | £ | 0
Planned Care 2 | EOC: Clinical pathway reviews | Transformational | First to follow-up ratio (MSK) | Activity shift | 0% | 25% | 50% | 75% | 100% | Q4, 2020-21 | Fair achievement | Define and create orthopaedic clinical network | Q1, 2017-18 | Orthopaedic clinical network develop and agree standardised outpatient pathway and new to follow up ratio, pre and post EOC | Q1, 2017-18 | Implement agreed standard outpatient pathway across orthopaedic base sites via orthopaedic clinical network | Q2, 2017-18 | [5 empty] | Contracting/commissioning | Q1, 2017-18 |  |  |  |  | Agreeing the baseline, plans to achieve and delivery of the four priority seven day standards |  |  |  |  | 0 | 0 | 0 | 0 | Appointments | 0 |  | 0.15128 | 0.23289 | 0.081602 | 0.29873 | Appointments | -2.1088 |  | 0.046865 | 0.44863 | 0.40177 | 0.57548 | Appointments | -3.971 |  | 0.07319 | 0.67684 | 0.60365 | 0.86822 | Appointments | -5.8507 |  | 0.094354 | 0.84834 | 0.75399 | 1.0882 | Appointments | -7.1612
Planned Care 2 | EOC: Clinical pathway reviews | Transformational | Elective length of stay (MSK) | Activity shift | 0% | 25% | 50% | 75% | 100% | Q4, 2020-21 | Fair achievement | Define and create orthopaedic clinical network | Q1, 2017-18 | Implement agreed standard EOC pathway with LoS target across EOCs via orthopaedic clinical network, in line with EOC implementation timescale | Q3, 2017-18 | [7 empty] | Contracting/commissioning | Q3, 2017-18 | [9 empty] | 0 | 0 | 0 | 0 | Bed days | 0 |  | 0.15044 | 0.23159 | 0.081146 | 0 | Bed days | -1.22 |  | 0.015078 | 0.14434 | 0.12926 | 0 | Bed days | -0.74323 |  | 0.021638 | 0.2001 | 0.17846 | 0 | Bed days | -1.0062 |  | 0.023245 | 0.209 | 0.18575 | 0 | Bed days | -1.0263
Planned Care 3 | EOC: Efficiencies & economies of scale | Transformational | Elective length of stay (MSK) | Service innovation | 0% | 0% | 50% | 75% | 100% | Q4, 2020-21 | Fair achievement | NHS England assure Pre consultation business case. CiC sign off and proceed to public consultation | Q3, 2016-17 | Completion of EOC public consultation, delivery of decision making business case, CIC confirm configuration for implementation | Q1, 2017-18 | EOC full business case and implementation plan signed off. First phase of acitvity shift (timescale dependent on provider configuration chose, either during FY17 or FY18) | Q3, 2017-18 | EOC configuration implemented, build complete and go live (timescale dependent on provider configuration chosen, either during FY 18 or FY19) | Q1, 2019-20 |  |  |  | Communications | Q3, 2016-17 | Workforce | Q1, 2017-18 | Infrastructure (estates) | Q1, 2017-18 |  | Legal challenge to the EOC process either prior or following a decision being made | 2 |  |  | 0 | 0 | 0 | 0 | Bed days | 0 |  | 0 | 0 | 0 | 0 | Bed days | 0 |  | 0.022617 | 0.21651 | 0.19389 | 0 | Bed days | -1.1148 |  | 0.032456 | 0.30015 | 0.26769 | 0 | Bed days | -1.5093 |  | 0.034868 | 0.3135 | 0.27863 | 0 | Bed days | -1.5395
Planned Care 3 | EOC: Efficiencies & economies of scale | Transformational | Economies of scale (MSK) | Service innovation | 0% | 0% | 33% | 67% | 100% | Q4, 2020-21 | Fair achievement | NHS England assure Pre consultation business case. CiC sign off and proceed to public consultation | Q3, 2016-17 | Completion of EOC public consultation, delivery of decision making business case, CIC confirm configuration for implementation | Q1, 2017-18 | EOC full business case and implementation plan signed off. First phase of acitvity shift (timescale dependent on provider configuration chose, either during FY17 or FY18) | Q3, 2017-18 | EOC configuration implemented, build complete and go live (timescale dependent on provider configuration chosen, either during FY 18 or FY19) | Q1, 2019-20 |  |  |  | Communications | Q3, 2016-17 | Workforce | Q1, 2017-18 | Infrastructure (estates) | Q1, 2017-18 |  | Legal challenge to the EOC process either prior or following a decision being made | 2 |  |  | 0 | 0 | 0 | 0 | £ | 0 |  | 0 | 0 | 0 | 0 | £ | 0 |  | 0.31163 | 2.9832 | 2.6716 | 0 | £ | 0 |  | 0.43831 | 4.0534 | 3.6151 | 0 | £ | 0 |  | 0.4616 | 4.1502 | 3.6886 | 0 | £ | 0
Planned Care 4 | Trust Level Efficiency Savings | Transformational | First to follow-up ratio (MSK) | Activity shift | 0% | 50% | 75% | 100% | 100% | Q1, 2019-20 | Fair achievement | Targets impelemented in 16/17 contracts with providers | Q4, 2016-17 | [9 empty] | Contracting/commissioning | Q4, 2016-17 | [9 empty] | 0 | 0 | 0 | 0 | Appointments | 0 |  | 0.45385 | 0.69866 | 0.2448 | 0.8962 | Appointments | -6.3264 |  | 0.10545 | 1.0094 | 0.90397 | 1.2948 | Appointments | -8.9348 |  | 0.14638 | 1.3537 | 1.2073 | 1.7364 | Appointments | -11.7013 |  | 0.14153 | 1.2725 | 1.131 | 1.6323 | Appointments | -10.7418
Planned Care 4 | Trust Level Efficiency Savings | Transformational | First to follow-up ratio (Ophthalmology) | Activity shift | 0% | 50% | 75% | 100% | 100% | Q1, 2019-20 | Fair achievement | Targets impelemented in 16/17 contracts with providers | Q4, 2016-17 | [9 empty] | Contracting/commissioning | Q4, 2016-17 | [9 empty] | 0 | 0 | 0 | 0 | Appointments | 0 |  | 0.82899 | 1.2761 | 0.44715 | 1.1984 | Appointments | -10.2536 |  | 0.20865 | 1.9974 | 1.7887 | 1.8757 | Appointments | -15.688 |  | 0.30079 | 2.7817 | 2.4809 | 2.6122 | Appointments | -21.3357 |  | 0.32314 | 2.9054 | 2.5822 | 2.7284 | Appointments | -21.7624

## U&EC summary
SEL priority workstream |  |  | Vision / aim | Is delivery of the aim on track? (RAG = 1,2,3)
Transformation |  | Urgent & Emergency Care | There is a high quality consistent 24/7 emergency and urgent care service in which patients are seen quickly by the right person in the right setting. | 2
Leadership |  | SRO: | Programme Manager: | Current delivery level:
|  | Angela Bhan | Rachael Crampton | SEL leed Programme
Background |  | Demand for urgent care services continues to increase, putting pressure on our infrastructure and resources. This is a result of a fragmented system and a lack of suitable alternative settings.
Case for change including best practice |  | Please set out a Case for change summary here and attach the document in which it can be found, if any
There were 6.8 million attendances at walk-in centres and minor injury units in 2012/13, and activity at these facilities has increased by around 12 per cent annually since data was first recorded a decade ago Attendances at hospital A&E departments (officially referred to as Type 1 and Type 2 A&E) have increased by more than two million over the last decade to 16 million The number of calls received by the ambulance service over the last decade has risen from 4.9 million to over 9 million Emergency admissions to hospitals in England have increased year on year, rising 31 per cent between 2002/03 to 2012/13 This growth in demand is set to continue as people live longer with increasingly complex, and often multiple, long-term conditions These facts have led to an overwhelming consensus that our current services are unsustainable Previously we have tried to deal with increasing demand by developing new facilities. Although well-conceived and well-intentioned, these have created additional complexity and confusion, not just for patients but also for those working in the NHS Last year 2012-13, there were 5.2 million emergency admissions to hospital, yet we know that up to 1.2 million of these admissions could have been avoided 40 per cent of patients who attend an A&E department are discharged requiring no treatment. Many of these individuals could have been helped just as well closer to home, for example at their own GP’s surgery or within community based services, provided the services were accessible and convenient. South east London has 1.67m inhabitants and is expected to grow to circa 1.87million by 2021.
Financial case for change |  | Please summarise the underpinning financial case for change or savings attached to this programme ?
The STP has identified recurrent savings of £71.5m associated with the U&EC interventions. Further detail of this can be found in the financial modelling pack.
Programme position in August 2016 |  | Please briefly describe the most recent or current product or phase (eg report or business case)? |  | Is the document or product attached?
Interventions whose delivery contributes to the overall programme |  | Please list any interventions | Total FY21 recurrent saving attributed in July 2016 STP (£m) | Path for implementation
| 1 | Discharge planning and consistency | 6.8656 | Provider Transformation
| 2 | ED interface with MH: Quicker interface with specialist MH services | 4.9779 | Provider Transformation
| 3 | Enhanced access: Community rapid response teams | 17.7654 | Contracting Consideration
| 4 | Enhanced access: Primary Care Extended Hours (8-8) | 2.5055 | No action
| 5 | Enhanced ED front door | 1.0022 | Provider Transformation
| 6 | Implementation of LCNs | 1.5451 | Supportvie Programme Role
| 7 | Improved 111 and LAS: 111 advice and triage | 1.0022 | No action
| 8 | Improved 111 and LAS: LAS redirect | 1.0022 | No action
| 9 | LQS achievement | 11.249 | Provider Transformation & Contracts
| 10 | Meeting the National standards Facilities specification and designation including UCCs | 1.0022 | Contracting Consideration
| 11 | Specialist advice: Access to specialist advice | 5.9382 | Contracting Consideration
| 12 | Specialist advice: Specialist response clinic | 7.8677 | Provider Transformation
Governance |  | Can you briefly describe your current governance structure for programme delivery and/or append a diagram, if available?
The SRO for U&EC is Angela Bhan. The following groups are established to support delivery acros the system: - U&EC Whole Network Group; - U&EC Executive Group; - Front Door Working Group. The purpose and membership of these groups is being reviewed to ensure it is appropriate for delivery.
U&EC Executive Group membership (key delivery group) |  | ToR Members | Current members
|  | Co- Chair SRO DoC DoF Provider representatives Head of System Resillience OHSEL Programme Manager | Simon Eccles (GUY'S AND ST THOMAS' NHS FOUNDATION TRUST) Tricia Fitzgerald (KING'S COLLEGE HOSPITAL NHS FOUNDATION TRUST) Harvey McEnroe (LEWISHAM AND GREENWICH NHS TRUST) Angela Bhan (NHS BROMLEY CCG) Katherine Henderson (GUY'S AND ST THOMAS' NHS FOUNDATION TRUST) Graham Norton (LAS) Baack Molly (NHS SOUTH EAST COMMISSIONING SUPPORT UNIT) Adrian Dorney (Oxleas) Sean Cross (SLAM) Sridevi Kalidindi (SLAM) Rachael Crampton (NHS SOUTHWARK CCG) Mark Easton (NHS SOUTHWARK CCG) Christine Caton (NHS LAMBETH CCG) Caroline Gilmartin (NHS SOUTHWARK CCG)
Objectives (in order of priority, most important first, one per cell) |  | Can you list your overarching programme objectives?
| 1 | A proactive, multi-agency approach to managing patients and helping them to remain in the community
| 2 | A risk stratification approach that identifies patient at risk and manages them in the community
| 3 | When needed, there are services the patient can be referred to for assessment, diagnostic tests and simple treatments either in the community (Rapid Access Service or Home Ward) or specialist clinics co-located in a hospital
| 4 | The Emergency Department (ED) is truly a specialist service for those in need of emergency care that can only be delivered in hospital
| 5 | Care planning for discharge home or normal place of residence commences from the start of an episode of urgent or emergency care, with the aim of getting a patient home quickly
| 6 | All parts of the health and social care system collectively own and manage system blockages together and throughout the year, seek to improve patient flows and reduce length of stay. This is supported by strong commissioning arrangements to include arrangements for care homes, joined up Information Technology (IT), telemedicine and ‘referrer-led’ discharge.
| 7 | Emergency and urgent care is supported by Virtual Patient Record and information sharing
| 8 | The system is collectively monitored on outcomes with improvements in morbidity, mortality and patient experience, supported by a dashboard, which includes patient experience
Risks to 2021 (in order of scale, most impactful first, one per cell) |  | Risk description | Mitigation summary | Risk post mitigation (RAG = 1,2,3)
| 1 | National shortage of Band 6 staff or staffing levels required to meet the 7 days standards | Pilot workforce software to understand scenarios. Review of NWL best practice examples of how they met the standards | 1
| 2 | Shortage in staff with MH & U18s MH experience. Lack of permanent workforce of registered MH nurses (usually work on temporary contracts) | Different levels of training to utlise staff more efficiently depending on role of spotting, signposting or intervention | 1
| 3 | Do not have a complete view of which of the U&EC interventions are being delivered by each CCG and their achievement against the proposed activity shifts | Cross checking of QIPP plans to U&EC delivery plan. Where intervientions are not meeting the agreed level of indicators establish where there is the opprtunity to do so. Or adjust the trajectory of activity shift | 2
Deliverables FY16/17 |  | Deliverable description | Target delivery Date | Status
| 1 | 5 out of 6 CCGs have supported discharge plans in place | Q3, 2016-17 | Not on track but plan to recover
| 2 | 1 of our trusts has a D&A service on site to meet demand | Q3, 2016-17 | Not on track but plan to recover
| 3 | 3 of our 5 trusts have the Core 24 model in place | Q4, 2016-17 | On track
| 4 | 3 of our boroughs will have a designated HBPOS and 136 pathway in line with the new specifications | Q4, 2016-17 | Not on track but plan to recover
| 5 | Stocktake of community mental health services- 24/7 crisis care support - demand and current provision against Core standards and 4 hour wait | Q4, 2016-17 | Not on track but plan to recover
| 6 | OATS definition defined nationally. Stocktake of demand and current capacity to meet 4 hour target | Q4, 2016-17 | On track
| 7 | 5 out of 6 CCGs have Rapid access teams fully in place | Q4, 2016-17 | On track
| 8 | 2 of our CCGs will have local care networks in place | Q4, 2016-17 | On track
| 9 | 3 of our trusts are meeting the Network standards for front door streaming. Commissioners to agree the timeline for remaining providers to meet the Network front door standards | Q4, 2016-17 | On track
| 10 | All of our 5 trusts are meeting some of the 4 7DS. A pilot of workforce requirements analysis for GSTT to meet the remaining priority 7DS will commence. | Q4, 2016-17 | On track
| 11 | Refresh of 2015/16 stocktake. Working with commissioners develop plans for meeting the standards. Some standards being met already | Q4, 2016-17
| 12 | Stocktake of existing advice (email and phone) and CBC requirements | Q4, 2016-17
| 13 | Clinical hub processes in place that supports NHS 111, 999 and out-of-hours calls. | Q4, 2016-17
| 14 | 25 % reduction in the proportion of ambulance 999 calls that result in avoidable transportation to an A&E department. | Q4, 2016-17

## U&EC Delivery Plan
STP DELIVERY AND FINANCIAL PLAN
SRO: Angela Bhan |  |  | Programme Manager: Rachael Crampton | Is delivery of the workstream on track? (RAG = 1,2,3) |  | 2 | [5 empty] | Name of person who completed this document: | Rachael Crampton |  | Email address: | rachael.crampton@nhs.net
[12 empty] | Organisation: | OHSEL |  | Telephone number:
Initiatives, outcomes and measures 2016-2021 |  |  |  | IMPACT | Cummulative impact (activity) | [6 empty] | DELIVERABLES: What will need to be delivered or produced for the initiative to be succesfully implemented? | [9 empty] | DEPENDENCIES | ENABLERS |  | ENABLERS (continued) |  |  |  | COMMISSIONING INTENTIONS | RISKS |  |  |  | 2016-17 | [6 empty] | 2017-18 | [6 empty] | 2018-19 | [6 empty] | 2019-20 | [6 empty] | 2020-21
# | Interventions (one per cell, repeat if relates to above) | What is the source of the goal we are trying to achieve? (1 per cell) | List all key Performance Indicators | What is the intended impact? | % 16-17 | % 17-18 | % 18-19 | % 19-20 | % 20-21 | Outcome fully achieved by (date) | Current achievement in SEL | Deliverable 1 description | Target delivery (date) | Deliverable 2 (if any) | Target delivery (date) | Deliverable 3 (if any) | Target delivery (date) | Deliverable 4 (if any) | Target delivery (date) | Deliverable 5 (if any) | Target delivery (date) | Dependencies (If more than 1, state the most impactful) | Key enabler required | Required no later than (date) | Secondary enabler required | Required no later than (date) | Supporting enabler required | Required no later than (date) | Describe how this initiative helps deliver Commissioning Intentions or relates to them | Risk description | RAG rating | Mitigation | Mitigation required by (date) | Investment Requirement £ | Expected Benefit £ | Net Estimated Savings -£ | Tarriff | Unit of activity (KPI) | Activity change +/- | Activity impact comments | Investment Requirement £ | Expected Benefit £ | Net Estimated Savings -£ | Tarriff | Unit of activity (KPI) | Activity change +/- | Activity impact comments | Investment Requirement £ | Expected Benefit £ | Net Estimated Savings -£ | Tarriff | Unit of activity (KPI) | Activity change +/- | Activity impact comments | Investment Requirement £ | Expected Benefit £ | Net Estimated Savings -£ | Tarriff | Unit of activity (KPI) | Activity change +/- | Activity impact comments | Investment Requirement £ | Expected Benefit £ | Net Estimated Savings -£ | Tarriff | Unit of activity (KPI) | Activity change +/- | Activity impact comments
UEC 1 | Discharge planning and consistency | Transformational | Non-elective length of stay (over 18s) | Improved patient experience | 80% | 100% | 100% | 100% | 100% | Q4, 2017-18 | Fair achievement | 5 out of 6 CCGs have supported discharge plans in place | Q4, 2017-18 |  |  |  | Q4, 2018-19 |  |  |  |  | CBC and local care networks | Technology | Q4, 2020-21 |  |  |  |  | Agreeing the baseline, plans to achieve and delivery of the four priority seven day standards |  |  |  |  | 0.3072 | 4.0001 | 3.6929 | 0 | Bed Days | -17.4929 |  | 0.60127 | 7.12 | 6.5187 | 0 | Bed Days | -30.5167 |  | 0.97758 | 9.2546 | 8.2771 | 0 | Bed Days | -38.8435 |  | 1.0846 | 9.861 | 8.7764 | 0 | Bed Days | -40.4975 |  | 0.85916 | 7.7247 | 6.8656 | 0 | Bed Days | -30.9806
UEC 2 | ED interface with MH: Quicker interface with specialist MH services | Transformational | 30 day readmissions (over 18s) | Improved patient experience | 20% | 50% | 75% | 100% | 100% | Q4, 2019-20 | N/A (new service) | 1 of our trusts has a D&A service on site to meet demand | Q3, 2016-17 | Options appraisal - investment and benefits. | Q1, 2017-18 | Agreed models implemented across SEL | Q4, 2019-20 | [5 empty] | Workforce | Q4, 2020-21 |  |  |  |  | Agreeing the baseline, plans to achieve and delivery of the four priority seven day standards | Lack of Drug&Alcohol staff in ED (or located off site which causes patients to abscond) | 2 | Different levels of training to utilise staff more efficiently depending on role of spotting, signposting or intervention |  | 0.002456 | 0.03198 | 0.029524 | 0.038716 | FCE | -0.016277 |  | 0.0080089 | 0.094839 | 0.08683 | 0.11481 | FCE | -0.04723 |  | 0.019035 | 0.1802 | 0.16117 | 0.21815 | FCE | -0.087723 |  | 0.025525 | 0.23206 | 0.20654 | 0.28094 | FCE | -0.11032 |  | 0.020893 | 0.18785 | 0.16696 | 0.22742 | FCE | -0.087211
UEC 2 | ED interface with MH: Quicker interface with specialist MH services |  |  |  | 50% | 50% | 100% | 100% | 100% | Q4, 2019-20 | Fair achievement | 3 of our 5 trusts have the Core 24 model in place | Q4, 2016-17 | Plan for delivery of Core 24 or alternative models agreed | Q4, 2016-17 | Core 24 or other alternative models in place across SEL | Q4, 2018-19 | [5 empty] | Workforce | Q4, 2020-21 | [5 empty] | Shortage in staff with MH & U18s MH experience. Lack of permanent workforce of registered MH nurses (usually work on temporary contracts) | 1 | Different levels of training to utilise staff more efficiently depending on role of spotting, signposting or intervention
UEC 2 | ED interface with MH: Quicker interface with specialist MH services |  |  |  | 60% | 60% | 60% | 80% | 100% | Q4, 2020-21 | Fair achievement | 3 of our boroughs will have a designated HBPOS and 136 pathway in line with the new specifications | Q4, 2016-17 | Wider SEL HBPoS provision using pan-London option analysis complete | Q4, 2017-18 | Roll out of new SEL HBPoS provision | Q4, 2018-19 | Improved care coordination and pathways & London s136 pathway compliant | Q4, 2019-20 |  |  |  | Infrastructure (estates) | Q4, 2020-21
UEC 2 | ED interface with MH: Quicker interface with specialist MH services |  |  |  | 35% | 50% | 100% | 100% | 100% | Q4, 2018-19 | Fair achievement | Review of community mental health services- 24/7 crisis care support - demand and current provision against Core standards. | Q4, 2016-17 | Options appraisal including cost and benefits. | Q1, 2017-18 | Agreed models implemented across SEL | Q4, 2018-19 | [12 empty] | Shortage in staff with MH & U18s MH experience. Lack of permanent workforce of registered MH nurses (usually work on temporary contracts) | 1 | Different levels of training to utilise staff more efficiently depending on role of spotting, signposting or intervention
UEC 2 | ED interface with MH: Quicker interface with specialist MH services |  |  |  | 25% | 50% | 100% | 100% | 100% | Q4, 2018-19 | N/A (new service) | OATS definition defined nationally. Stocktake of demand and current capacity | Q4, 2016-17 | Standardised care pathway developed for all OATs across SEL | Q4, 2017-18 | Pathway implemented | Q4, 2018-19
UEC 2 | ED interface with MH: Quicker interface with specialist MH services | Transformational | Non-elective length of stay (over 18s) | Improved performance | 0% | 10% | 25% | 50% | 100% | Q4, 2020-21 | Fair achievement | as above | [16 empty] | Agreeing the baseline, plans to achieve and delivery of the four priority seven day standards |  |  |  |  | 0 | 0 | 0 | 0 | Bed Days | 0 |  | 0.030063 | 0.356 | 0.32594 | 0 | Bed Days | -1.5258 |  | 0.1222 | 1.1568 | 1.0346 | 0 | Bed Days | -4.8554 |  | 0.27115 | 2.4652 | 2.1941 | 0 | Bed Days | -10.1244 |  | 0.42958 | 3.8624 | 3.4328 | 0 | Bed Days | -15.4903
UEC 2 | ED interface with MH: Quicker interface with specialist MH services | Transformational | Non-elective admissions (over 18s) | Improved patient experience | 0% | 10% | 25% | 50% | 100% | Q4, 2020-21 | Fair achievement | as above | [21 empty] | 0 | 0 | 0 | 0 | FCE | 0 |  | 0.0067114 | 0.079474 | 0.072763 | 0.09196 | FCE | -0.051392 |  | 0.030683 | 0.29047 | 0.25979 | 0.33611 | FCE | -0.18361 |  | 0.086398 | 0.78551 | 0.69911 | 0.90892 | FCE | -0.48489 |  | 0.17247 | 1.5506 | 1.3782 | 1.7943 | FCE | -0.93478
UEC 3 | Enhanced access: Community rapid response teams | Transformational | A&E Attendances (over 18s) | Activity shift | 80% | 100% | 100% | 100% | 100% | Q4, 2017-18 | Fair achievement | 5 out of 6 CCGs have Rapid access teams fully in place | Q4, 2016-17 | Where less establish the opportunity to meet the activity shift trajectory. | Q4, 2017-18 | [7 empty] | Contracting/commissioning | Q4, 2020-21 | [5 empty] | Teams already exist with no opportunity to make activity shifts to meet 5 year trajectory | 2 | Stocktake to understand what activity shifts are already being achieved and by what teams |  | 0.11332 | 1.4755 | 1.3622 | 2.1615 | Attendance | -11.5905 |  | 0.17783 | 2.1058 | 1.9279 | 3.0848 | Attendance | -16.1853 |  | 0.29329 | 2.7765 | 2.4832 | 4.0674 | Attendance | -20.861 |  | 0.36202 | 3.2914 | 2.9294 | 4.8217 | Attendance | -24.1499 |  | 0.31353 | 2.819 | 2.5055 | 4.1296 | Attendance | -20.199
UEC 3 | Enhanced access: Community rapid response teams | Transformational | Non-elective length of stay (over 18s) | Activity shift | 80% | 100% | 100% | 100% | 100% | Q4, 2017-18 | Fair achievement | as above | [21 empty] | 0.3072 | 4.0001 | 3.6929 | 0 | Bed Days | -17.4929 |  | 0.60127 | 7.12 | 6.5187 | 0 | Bed Days | -30.5167 |  | 0.97758 | 9.2546 | 8.2771 | 0 | Bed Days | -38.8435 |  | 1.0846 | 9.861 | 8.7764 | 0 | Bed Days | -40.4975 |  | 0.85916 | 7.7247 | 6.8656 | 0 | Bed Days | -30.9806
UEC 3 | Enhanced access: Community rapid response teams | Transformational | Non-elective admissions (over 18s) | Activity shift | 80% | 100% | 100% | 100% | 100% | Q4, 2017-18 | Fair achievement | as above | [21 empty] | 0.20124 | 2.6203 | 2.4191 | 3.032 | FCE | -1.7317 |  | 0.40878 | 4.8407 | 4.4319 | 5.6012 | FCE | -3.1303 |  | 0.74755 | 7.077 | 6.3294 | 8.1888 | FCE | -4.4735 |  | 1.0525 | 9.5689 | 8.5164 | 11.0723 | FCE | -5.9069 |  | 1.0505 | 9.4448 | 8.3944 | 10.9287 | FCE | -5.6937
UEC 4 | Enhanced access: Primary Care Extended Hours (8-8) | Transformational | A&E Attendances (over 18s) | Activity shift | 33% | 100% | 100% | 100% | 100% | Q4, 2017-18 | Fair achievement | 2 of our CCGs will have local care networks in place | Q4, 2016-17 | [20 empty] | 0.046743 | 0.60865 | 0.56191 | 0.89162 | Attendance | -4.7811 |  | 0.17783 | 2.1058 | 1.9279 | 3.0848 | Attendance | -16.1853 |  | 0.29329 | 2.7765 | 2.4832 | 4.0674 | Attendance | -20.861 |  | 0.36202 | 3.2914 | 2.9294 | 4.8217 | Attendance | -24.1499 |  | 0.31353 | 2.819 | 2.5055 | 4.1296 | Attendance | -20.199
UEC 5 | Enhanced ED front door | Transformational | A&E Attendances (over 18s) | Activity shift | 60% | 75% | 100% | 100% | 100% | Q4, 2018-19 | Fair achievement | 3 of our trusts are meeting the Network standards for front door streaming. Commissioners to agree the timeline for remaining providers to meet the Network front door standards | Q4, 2016-17 | standards met | Q4, 2018-19 | [7 empty] | Contracting/commissioning | Q4, 2020-21 | [5 empty] | Challenging for ED staff to deliver messages on where a patient should have presented in a busy A&E department | 3 | Culture shift training. Reviewing best practice models of redirection for suitability in SEL |  | 0.033995 | 0.44265 | 0.40866 | 0.64845 | Attendance | -3.4772 |  | 0.053348 | 0.63173 | 0.57838 | 0.92544 | Attendance | -4.8556 |  | 0.11732 | 1.1106 | 0.99329 | 1.627 | Attendance | -8.3444 |  | 0.14481 | 1.3166 | 1.1718 | 1.9287 | Attendance | -9.66 |  | 0.12541 | 1.1276 | 1.0022 | 1.6519 | Attendance | -8.0796
UEC 6 | Implementation of LCNs | Transformational | 30 day readmissions (over 18s) | Activity shift | 25% | 100% | 100% | 100% | 100% | Q4, 2017-18 | Fair achievement | Refer to the CBC delivery plan | [21 empty] | 0.00307 | 0.039975 | 0.036905 | 0.048395 | FCE | -0.020346 |  | 0.016018 | 0.18968 | 0.17366 | 0.22963 | FCE | -0.094461 |  | 0.02538 | 0.24027 | 0.21489 | 0.29087 | FCE | -0.11696 |  | 0.025525 | 0.23206 | 0.20654 | 0.28094 | FCE | -0.11032 |  | 0.020893 | 0.18785 | 0.16696 | 0.22742 | FCE | -0.087211
UEC 6 | Implementation of LCNs | Transformational | Non-elective admissions (over 18s) | Activity shift | 25% | 100% | 100% | 100% | 100% | Q4, 2017-18 | Fair achievement | Refer to the CBC delivery plan | [21 empty] | 0.010325 | 0.13444 | 0.12411 | 0.15556 | FCE | -0.088847 |  | 0.067114 | 0.79474 | 0.72763 | 0.9196 | FCE | -0.51392 |  | 0.12273 | 1.1619 | 1.0392 | 1.3444 | FCE | -0.73445 |  | 0.1728 | 1.571 | 1.3982 | 1.8178 | FCE | -0.96979 |  | 0.17247 | 1.5506 | 1.3782 | 1.7943 | FCE | -0.93478
UEC 7 | Improved 111 and LAS: 111 advice and triage | Transformational | A&E Attendances (over 18s) | Activity shift | 25% | 50% | 75% | 100% | 100% | Q4, 2019-20 | Fair achievement | Clinical hub in place that supports NHS 111, 999 and out-of-hours calls. | [10 empty] | Technology | [10 empty] | 0.014165 | 0.18444 | 0.17027 | 0.27019 | Attendance | -1.4488 |  | 0.035566 | 0.42116 | 0.38559 | 0.61696 | Attendance | -3.2371 |  | 0.087986 | 0.83296 | 0.74497 | 1.2202 | Attendance | -6.2583 |  | 0.14481 | 1.3166 | 1.1718 | 1.9287 | Attendance | -9.66 |  | 0.12541 | 1.1276 | 1.0022 | 1.6519 | Attendance | -8.0796
UEC 8 | Improved 111 and LAS: LAS redirect | Transformational | A&E Attendances (over 18s) | Activity shift | 25% | 50% | 75% | 100% | 100% | Q4, 2019-20 | Fair achievement | Reduction in the proportion of ambulance 999 calls that result in avoidable transportation to an A&E department. | [10 empty] | Technology | [10 empty] | 0.014165 | 0.18444 | 0.17027 | 0.27019 | Attendance | -1.4488 |  | 0.035566 | 0.42116 | 0.38559 | 0.61696 | Attendance | -3.2371 |  | 0.087986 | 0.83296 | 0.74497 | 1.2202 | Attendance | -6.2583 |  | 0.14481 | 1.3166 | 1.1718 | 1.9287 | Attendance | -9.66 |  | 0.12541 | 1.1276 | 1.0022 | 1.6519 | Attendance | -8.0796
UEC 9 | LQS achievement | National Requirement | Non-elective admissions (over 18s) | Improved performance | 40% | 60% | 100% | 100% | 100% | Q4, 2018-19 | Fair achievement | All of our 5 trusts are meeting some of the 4 7DS. A pilot of workforce requirements analysis for GSTT to meet the remaining priority 7DS will commence. | Q4, 2016-17 | Meet the four priority standards for seven-day hospital services for all urgent network specialist services. | Q3, 2017-18 | SEL achieving the 4 priority 7DS in all providers | Q1, 2018-19 | [5 empty] | Workforce | Q1, 2018-19 | [5 empty] | National shortage of Band 6 staff or staffing levels required to meet the standards | 1 | pilot workforce software to understand scenarios. Review of NWL best practice examples of how they met the standards |  | 0.016519 | 0.2151 | 0.19858 | 0.24889 | FCE | -0.14216 |  | 0.040268 | 0.47684 | 0.43658 | 0.55176 | FCE | -0.30835 |  | 0.12273 | 1.1619 | 1.0392 | 1.3444 | FCE | -0.73445 |  | 0.1728 | 1.571 | 1.3982 | 1.8178 | FCE | -0.96979 |  | 0.17247 | 1.5506 | 1.3782 | 1.7943 | FCE | -0.93478
UEC 9 | LQS achievement | National Requirement |  |  | 25% | 40% | 50% | 75% | 100% | Q4, 2020-21 | Fair achievement | Provider plans in place to meet LQS | Q4, 2016-17 | SEL meeting the LQS | Q4, 2020-21 | [7 empty] | Workforce | Q4, 2020-21
UEC 9 | LQS achievement | National Requirement | Non-elective length of stay (over 18s) | Improved performance | 25% | 40% | 50% | 75% | 100% | Q4, 2020-21 | Fair achievement | as above |  | as above |  | as above | [17 empty] | 0.096001 | 1.25 | 1.154 | 0 | Bed Days | -5.4665 |  | 0.24051 | 2.848 | 2.6075 | 0 | Bed Days | -12.2067 |  | 0.48879 | 4.6273 | 4.1385 | 0 | Bed Days | -19.4218 |  | 0.81346 | 7.3957 | 6.5823 | 0 | Bed Days | -30.3731 |  | 0.85916 | 7.7247 | 6.8656 | 0 | Bed Days | -30.9806
UEC 9 | LQS achievement | National Requirement | 30 day readmissions (over 18s) | Improved performance | 25% | 40% | 50% | 75% | 100% | Q4, 2020-21 | Fair achievement | as above |  | as above |  | as above | [17 empty] | 0.05526 | 0.71955 | 0.66429 | 0.87111 | FCE | -0.36622 |  | 0.11533 | 1.3657 | 1.2503 | 1.6533 | FCE | -0.68012 |  | 0.22842 | 2.1624 | 1.934 | 2.6179 | FCE | -1.0527 |  | 0.34458 | 3.1329 | 2.7883 | 3.7927 | FCE | -1.4894 |  | 0.37607 | 3.3813 | 3.0052 | 4.0935 | FCE | -1.5698
UEC 10 | Meeting the National standards Facilities specification and designation including UCCs | National Requirement | A&E Attendances (over 18s) | Activity shift | 10% | 25% | 35% | 50% | 100% | Q4, 2020-21 | Fair achievement | Refresh of 2015/16 stocktake. Working with commissioners develop plans for meeting the standards. Some standards being met already | Q3, 2016-17 | Plan for delivery incorporated into contracts and delivered as part of the Provider CIP and QIPP plans | Q1, 2018-19 | Facilities specification met | Q4, 2020-21 | [5 empty] | Contracting/commissioning | Q4, 2020-21 | Technology | Q4, 2020-21 | [7 empty] | 0.0056659 | 0.073776 | 0.06811 | 0.10808 | Attendance | -0.57953 |  | 0.017783 | 0.21058 | 0.19279 | 0.30848 | Attendance | -1.6185 |  | 0.04106 | 0.38871 | 0.34765 | 0.56944 | Attendance | -2.9205 |  | 0.072404 | 0.65828 | 0.58588 | 0.96433 | Attendance | -4.83 |  | 0.12541 | 1.1276 | 1.0022 | 1.6519 | Attendance | -8.0796
UEC 11 | Specialist advice: Access to specialist advice | Transformational | Non-elective length of stay (over 18s) | Activity shift | 0% | 10% | 25% | 50% | 100% | Q4, 2020-21 | N/A (new service) | Stocktake of existing advice (email and phone) and CBC requirements | Q4, 2016-17 | Costed service specification for commissioners and providers | Q2, 2017-18 | Service changes in place | Q4, 2020-21 | [5 empty] | Technology | Q4, 2020-21 | Workforce | Q4, 2020-21 | [7 empty] | 0 | 0 | 0 | 0 | Bed Days | 0 |  | 0.030063 | 0.356 | 0.32594 | 0 | Bed Days | -1.5258 |  | 0.1222 | 1.1568 | 1.0346 | 0 | Bed Days | -4.8554 |  | 0.27115 | 2.4652 | 2.1941 | 0 | Bed Days | -10.1244 |  | 0.42958 | 3.8624 | 3.4328 | 0 | Bed Days | -15.4903
UEC 11 | Specialist advice: Access to specialist advice | Transformational | A&E Attendances (over 18s) | Improved patient experience | 0% | 10% | 25% | 50% | 100% | Q4, 2020-21 | N/A (new service) | as above |  | as above | [19 empty] | 0 | 0 | 0 | 0 | Attendance | 0 |  | 0.017783 | 0.21058 | 0.19279 | 0.30848 | Attendance | -1.6185 |  | 0.073322 | 0.69413 | 0.62081 | 1.0168 | Attendance | -5.2153 |  | 0.18101 | 1.6457 | 1.4647 | 2.4108 | Attendance | -12.075 |  | 0.31353 | 2.819 | 2.5055 | 4.1296 | Attendance | -20.199
UEC 12 | Specialist advice: Specialist response clinic | Transformational | A&E Attendances (over 18s) | Improved patient experience | 0% | 10% | 25% | 50% | 100% | Q4, 2020-21 | N/A (new service) | stocktake of existing services and ability to meet required activity shifts | Q1, 2017-18 | Where less establish the opportunity to meet the activity shift trajectory | Q2, 2017-18 | Implement revised models to meet trajectory or adjust the activity shift that can be realised | Q4, 2020-21 | [5 empty] | Workforce | Q4, 2020-21 | [9 empty] | 0 | 0 | 0 | 0 | Attendance | 0 |  | 0.0071131 | 0.084231 | 0.077118 | 0.12339 | Attendance | -0.64741 |  | 0.029329 | 0.27765 | 0.24832 | 0.40674 | Attendance | -2.0861 |  | 0.072404 | 0.65828 | 0.58588 | 0.96433 | Attendance | -4.83 |  | 0.12541 | 1.1276 | 1.0022 | 1.6519 | Attendance | -8.0796
UEC 12 | Specialist advice: Specialist response clinic | Transformational | Non-elective length of stay (over 18s) | Improved patient experience | 0% | 10% | 25% | 50% | 100% | Q4, 2020-21 | N/A (new service) | as above | [21 empty] | 0 | 0 | 0 | 0 | Bed Days | 0 |  | 0.060127 | 0.712 | 0.65187 | 0 | Bed Days | -3.0517 |  | 0.24439 | 2.3137 | 2.0693 | 0 | Bed Days | -9.7109 |  | 0.54231 | 4.9305 | 4.3882 | 0 | Bed Days | -20.2487 |  | 0.85916 | 7.7247 | 6.8656 | 0 | Bed Days | -30.9806
NHSE Operating Plan deliverables - Please summarise all relevant goals to 2020 and deliverables in 2016-17 defined in the Operating Framework
Deliver the four hour A&E standard, and standards for ambulance response times including through implementing the five elements of the A&E Improvement Plan. • By November 2017, meet the four priority standards for seven-day hospital services for all urgent network specialist services. • Implement the Urgent and Emergency Care Review, ensuring a 24/7 integrated care service for physical and mental health is implemented by March 2020 in each STP footprint, including a clinical hub that supports NHS 111, 999 and out-of-hours calls. • Deliver a reduction in the proportion of ambulance 999 calls that result in avoidable transportation to an A&E department. • Initiate cross-system approach to prepare for forthcoming waiting time standard for urgent care for those in a mental health crisis.

## U&EC Template Tracker (hidden)
Worksheet | Template Section | CLG | Completion Owner | Progress | Approved by SRO
Workstream Summary | Vision/Aim | U&EC | Chris | drafted ready for PM review
Workstream Summary | RAG for delivery of Workstream | U&EC | PM
Workstream Summary | Leadership | U&EC | Chris | drafted ready for PM review
Workstream Summary | Background | U&EC | Chris | drafted ready for PM review
Workstream Summary | Case for change including best practice | U&EC | Chris | drafted ready for PM review
Workstream Summary | Financial case for change | U&EC | Chris | drafted ready for PM review
Workstream Summary | Programme Position in August 2016 | U&EC | PM
Workstream Summary | Interventions | U&EC | Chris | drafted ready for PM review
Workstream Summary | Governance | U&EC | Chris | drafted ready for PM review
Workstream Summary | Overarching Objectives | U&EC | Chris | drafted ready for PM review
Workstream Summary | Scope | U&EC | PM
Workstream Summary | Constraints to 2021 | U&EC | PM
Workstream Summary | Risks to 2021 | U&EC | PM
Workstream Summary | Deliverables for FY16/17 | U&EC | PM
Delivery Plan | RAG for delivery of workstream | U&EC | PM
Delivery Plan | Interventions | U&EC | Chris | drafted ready for PM review
Delivery Plan | Source of the goal seeking to achieve | U&EC | Chris | drafted ready for PM review
Delivery Plan | List of key Performance metrics | U&EC | Chris | drafted ready for PM review
Delivery Plan | Intended impact | U&EC | Chris | drafted ready for PM review
Delivery Plan | Progress to intervention delivery | U&EC | PM
Delivery Plan | Intervention completion date | U&EC | PM
Delivery Plan | Current achievement in SEL | U&EC | PM
Delivery Plan | Deliverable descriptions | U&EC | PM
Delivery Plan | Target delivery dates | U&EC | PM
Delivery Plan | Dependencies | U&EC | PM
Delivery Plan | Enablers | U&EC | PM
Delivery Plan | Risks | U&EC | PM
Delivery Plan | Investment required (£) by year | U&EC | Jos / Chris | Populated as at 28 Sep
Delivery Plan | Expected Benefits (£) by year | U&EC | Jos / Chris | Populated as at 28 Sep
Delivery Plan | Gross Estimated Savings (-£) by year | U&EC | Jos / Chris | Populated as at 28 Sep
Delivery Plan | Unit of activity by year | U&EC | Jos / Chris | Populated as at 28 Sep
Delivery Plan | Activity change +/- by year | U&EC | Jos / Chris | Populated as at 28 Sep
Delivery Plan | Activity impact comments by year | U&EC | Jos / Chris | Populated as at 28 Sep
Delivery Plan | Quality: how is quality and safety maintained and improved for patients in 2016-17 | U&EC | PM
Delivery Plan | Enablers and Constraints: delivey impact summary | U&EC | PM
Delivery Plan | Finance, activity and efficiency savings: summary | U&EC | Jos / Chris | Populated as at 28 Sep
Delivery Plan | Social Care impact | U&EC | PM

## CBC Summary (hidden)
SEL priority workstream |  |  | Vision / aim | Is delivery of the aim on track? (RAG = 1,2,3)
Transformation |  |  |  | 2
Leadership |  | SRO: | Programme Manager: | Current delivery level:
SEL leed Programme
Background
Case for change including best practice |  | Please set out a Case for change summary here and attach the document in which it can be found, if any
Financial case for change |  | Please summarise the underpinning financial case for change or savings attached to this programme ?
Programme position in August 2016 |  | Please briefly describe the most recent or current product or phase (eg report or business case)? |  | Is the document or product attached?
Interventions whose delivery contributes to the overall programme |  | Please list any interventions | Total FY21 recurrent saving attributed in July 2016 STP (£m) | Path for implementation
1
2
3
4
5
6
7
8
9
10
11
12
Governance |  | Can you briefly describe your current governance structure for programme delivery and/or append a diagram, if available?
Objectives (in order of priority, most important first, one per cell) |  | Can you list your overarching programme objectives?
1
2
3
4
5
6
7
8
Scope (what is in and out of scope) | In
Out
Constraints to 2021 (in order of scale, most impactful first, one per cell) | 1
2
Risks to 2021 (in order of scale, most impactful first, one per cell) |  | Risk description | Mitigation summary | Risk post mitigation (RAG = 1,2,3)
1
2
3
4
5
Deliverables FY16/17 |  | Deliverable description | Target delivery Date | Status
1
2
3
4
5
6
7
8
9
Is there anything else you think we should be looking into / considering (including opportunities or initiatives)?
Name of person who completed this document: |  |  | Email address:
Organisation: |  |  | Telephone number:

## CBC Delivery Plan (hidden)
STP DELIVERY AND FINANCIAL PLAN
SRO: |  |  | Programme Manager: | Is delivery of the workstream on track? (RAG = 1,2,3) |  | 2 | [5 empty] | Name of person who completed this document: |  |  | Email address:
[12 empty] | Organisation: | OHSEL |  | Telephone number:
Initiatives, outcomes and measures 2016-2021 |  |  |  | IMPACT | Cummulative impact (activity) | [6 empty] | DELIVERABLES: What will need to be delivered or produced for the initiative to be succesfully implemented? | [17 empty] | DEPENDENCIES | ENABLERS |  | ENABLERS (continued) |  |  |  | COMMISSIONING INTENTIONS | RISKS |  |  |  | 2016-17 | [5 empty] | 2017-18 | [5 empty] | 2018-19 | [5 empty] | 2019-20 | [5 empty] | 2020-21
# | Sub workstreams (one per cell, repeat if relates to above) | What is the source of the goal we are trying to achieve? (1 per cell) | List all key Performance Indicators | What is the intended impact? | % 16-17 | % 17-18 | % 18-19 | % 19-20 | % 20-21 | Outcome fully achieved by (date) | Current achievement in SEL | Deliverable 1 description | Target delivery (date) | Deliverable 2 (if any) | Target delivery (date) | Deliverable 3 (if any) | Target delivery (date) | Deliverable 4 (if any) | Target delivery (date) | Deliverable 5 (if any) | Target delivery (date) | Deliverable 6 (if any) | Target delivery (date) | Deliverable 7 (if any) | Target delivery (date) | Deliverable 8 (if any) | Target delivery (date) | Deliverable 9 (if any) | Target delivery (date) | Dependencies (If more than 1, state the most impactful) | Key enabler required | Required no later than (date) | Secondary enabler required | Required no later than (date) | Supporting enabler required | Required no later than (date) | Describe how this initiative helps deliver Commissioning Intentions or relates to them | Risk description | RAG rating | Mitigation | Mitigation required by (date) | Investment Requirement £ | Expected Benefit £ | Gross Estimated Savings -£ | Unit of activity (KPI) | Activity change +/- | Activity impact comments | Investment Requirement £ | Expected Benefit £ | Gross Estimated Savings -£ | Unit of activity (KPI) | Activity change +/- | Activity impact comments | Investment Requirement £ | Expected Benefit £ | Gross Estimated Savings -£ | Unit of activity (KPI) | Activity change +/- | Activity impact comments | Investment Requirement £ | Expected Benefit £ | Gross Estimated Savings -£ | Unit of activity (KPI) | Activity change +/- | Activity impact comments | Investment Requirement £ | Expected Benefit £ | Gross Estimated Savings -£ | Unit of activity (KPI) | Activity change +/- | Activity impact comments
CBC1 | Federation/Alliances Established | Transformational |  | Future demand and capacity management | 50% | 100% | [5 empty] | All local GP practices have agreed to an Alliance | Complete | The Alliance has a recognised legal identity | Complete | Commissioner offer made to Alliance and contract in place following due diligence | Q1, 2017-18 | 3 to 5 year business plan developed | Q1, 2017-18 | [17 empty] | Agreeing the baseline, plans to achieve and delivery of the four priority seven day standards |  |  |  |  | 40000 | 10000 | -50000 | Telephone appointments | 500 | Reduced tariff of 500+ opatient appts | 40000 | 10000 | -50000 | Telephone appointments | 500 | Reduced tariff of 500+ opatient appts | 40000 | 10000 | -50000 | Telephone appointments | 500 | Reduced tariff of 500+ opatient appts | 40000 | 10000 | -50000 | Telephone appointments | 500 | Reduced tariff of 500+ opatient appts | 40000 | 10000 | -50000 | Telephone appointments | 500 | Reduced tariff of 500+ opatient appts
CBC2 | LCN integrated system leadership & management | Transformational |  | Service innovation | 66% | 100% | [5 empty] | Local Care Networks defined | Complete | LCN leadership team & management structure in place with clear governance and decision-making arrangements | Complete | Enabling strategies, e.g. workforce, IM&T, Estates embedded across networks with localised delivery plans | Q1, 2017-18 | [19 empty] | Agreeing the baseline, plans to achieve and delivery of the four priority seven day standards |  |  |  |  | 40000 | 10000 | -50000 | Telephone appointments | 501 | Reduced tariff of 500+ opatient appts | 40000 | 10000 | -50000 | Telephone appointments | 501 | Reduced tariff of 500+ opatient appts | 40000 | 10000 | -50000 | Telephone appointments | 501 | Reduced tariff of 500+ opatient appts | 40000 | 10000 | -50000 | Telephone appointments | 501 | Reduced tariff of 500+ opatient appts | 40000 | 10000 | -50000 | Telephone appointments | 501 | Reduced tariff of 500+ opatient appts
CBC3 | Accessible Care standards and associated big hitters implemented | Transformational |  | Activity shift | 33% | 100% | [5 empty] | Improved access to GP practice including 8 to 8 7/7 | Q2, 2017-18 | UCC/walk-in centres | Complete | Able to share medical records across federations | Q1, 2017-18 | Single telephone triage and booking across federations | Q4, 2017-18 | Reablement (encompassing rapid response and supported discharge) | Q4, 2016-17 | Same day access to specialist advice and clinics (including diagnostics) | Q1, 2017-18 | [13 empty] | Agreeing the baseline, plans to achieve and delivery of the four priority seven day standards
CBC4 | Proactive Care standards and associated big hitters implemented | Transformational |  | Activity shift | 20% | 66% | 100% |  |  |  |  | Local communities and stakeholders actively and routinely involved in priority setting and service redesign across networks | Q1, 2018-19 | Asset mapping and social prescribing | Q1, 2017-18 | Care coordinators/navigators/patient liaison across networks | Q1, 2017-18 | Health & Wellbeing champions across networks | Q1, 2018-19 | Primary prevention and enhanced public health programmes | Q1, 2018-19 | Active risk stratification | Complete | Training in motivational skills and health coaching | Q1, 2017-18 | Enhanced call & recall and screening for hard to reach groups | Q1, 2017-18 | Enhanced support to vulnerable people in care homes, extra care housing and receiving domiciliary care | Complete
CBC5 | Coordinated Care standards and associated big hitters implemented | Transformational |  | Activity shift | 33% | 66% | 100% |  |  |  |  | Active care registers within GP practices | Complete | Identifying people at risk of developing LTCs | Q3, 2017-18 | Patient/carer education programmes | Q1, 2018-19 | See MDT working below, reablement above, care coordinators above, assigned care professionals below | N/A
CBC6 | Continuity of Care standards and associated big hitters implemented | Transformational |  | Activity shift | 0% | 100% | [5 empty] | All patients have a named GP | Q1, 2017-18 | Flexible appointment lengths according to patient need commissioned | Q1, 2017-18 | Assigned care professional in final year of life | Q1, 2017-18 | Multi-disciplinary teams established within networks | Q1, 2017-18
Quality: Describe how quality and safety will be maintained and improved for patients and how the above mandated outcomes are being met in 2016-17. | [11 empty] | NHSE Operating Plan deliverables - Please summarise all relevant goals to 2020 and deliverables in 2016-17 defined in the Operating Framework | [24 empty] | Enablers and Constraints - how do the above enablers and constraints affect delivery? | [10 empty] | Finance, activity and efficiency savings - provide a summary of impact on finance, activity and efficiency savings of this workstream | [11 empty] | Social care impact - hypothetically, if social care funding were to decrease, what would this mean for providers? Describe the impact of a -10% or -20% reduction in funding
[Description here in how quality is being addressed in no more than 250 words. Any points which require further expansion to be added as a deliverable below] PM to complete | [36 empty] | [Description here in no more than 250 words] | [10 empty] | [Description here in no more than 250 words] | [11 empty] | [Description here in no more than 250 words]

## CBC Template Tracker (hidden)
Worksheet | Template Section | CLG | Completion Owner | Progress | Approved by SRO
Workstream Summary | Vision/Aim | CBC | Chris | e.g drafted ready for PM review
Workstream Summary | RAG for delivery of Workstream | CBC | PM
Workstream Summary | Leadership | CBC | Chris
Workstream Summary | Background | CBC | Chris
Workstream Summary | Case for change including best practice | CBC | Chris
Workstream Summary | Financial case for change | CBC | Chris
Workstream Summary | Programme Position in August 2016 | CBC | PM
Workstream Summary | Interventions | CBC | Chris
Workstream Summary | Governance | CBC | Chris
Workstream Summary | Overarching Objectives | CBC | Chris
Workstream Summary | Scope | CBC | PM
Workstream Summary | Constraints to 2021 | CBC | PM
Workstream Summary | Risks to 2021 | CBC | PM
Workstream Summary | Deliverables for FY16/17 | CBC | PM
Delivery Plan | RAG for delivery of workstream | CBC | PM
Delivery Plan | Interventions | CBC | Chris
Delivery Plan | Source of the goal seeking to achieve | CBC | Chris
Delivery Plan | List of key Performance metrics | CBC | Chris
Delivery Plan | Intended impact | CBC | Chris
Delivery Plan | Progress to intervention delivery | CBC | PM
Delivery Plan | Intervention completion date | CBC | PM
Delivery Plan | Current achievement in SEL | CBC | PM
Delivery Plan | Deliverable descriptions | CBC | PM
Delivery Plan | Target delivery dates | CBC | PM
Delivery Plan | Dependencies | CBC | PM
Delivery Plan | Enablers | CBC | PM
Delivery Plan | Risks | CBC | PM
Delivery Plan | Investment required (£) by year | CBC | Jos / Chris
Delivery Plan | Expected Benefits (£) by year | CBC | Jos / Chris
Delivery Plan | Gross Estimated Savings (-£) by year | CBC | Jos / Chris
Delivery Plan | Unit of activity by year | CBC | Jos / Chris
Delivery Plan | Activity change +/- by year | CBC | Jos / Chris
Delivery Plan | Activity impact comments by year | CBC | Jos / Chris
Delivery Plan | Quality: how is quality and safety maintained and improved for patients in 2016-17 | CBC | PM
Delivery Plan | Enablers and Constraints: delivey impact summary | CBC | PM
Delivery Plan | Finance, activity and efficiency savings: summary | CBC | Jos / Chris
Delivery Plan | Social Care impact | CBC | PM

## Menu (hidden)
Year | Year | Status | Priority | 16-17 | 17-18 | Current | 1 | Yes, attached | Programmes | Programme | Delivery level | 18-19 |  | 5 year | Word limits |  |  | Enablers | Impact | Savings badged
1 | 2016-17 | On track | High | 31/07/16 or earlier and overdue | 2017-04-30 | Opportunity Analysis | 2 | No attachment | Delivery model implementation – C&H | Environment, leisure and physical environment | Locally delivered programme with NEL line of sight | 2018-04-30 | National, mandatory | Q3, 2016-17 | words | characters | Domain 1 - Preventing people from dying prematurely: how successful the NHS is in reducing the number of avoidable deaths. | Technology | Activity shift | Health commissioner QIPP
2 | 2017-18 | Not on track but plan to recover | Medium | 2016-08-31 | 2017-05-31 | Implementation plan | 3 |  | Delivery model implementation – WEL | Early years, schools and healthy families | Locally delivered programme with NEL co-ordination | 2018-05-31 | National guideline or best practice | Q4, 2016-17 | 500 | 2700 | Domain 2 - Enhancing quality of life for people with long-term conditions: how successfully the NHS is supporting people with long-term conditions to live as normal a life as possible. | Infrastructure (estates) | Current demand and capacity management | Provider CIP - contributing to 2%
3 | 2018-19 | Not on track and no plan to recover | Low | 2016-09-30 | 2017-06-30 | Business Case |  |  | Delivery model implementation - BHR | Employment | NEL led programme | 2018-06-30 | London region, mandatory | Q1, 2017-18 | 250 | 1350 | Domain 3 - Helping people to recover from episodes of ill health or following injury: how people recover from ill health or injury and wherever possible how it can be prevented. | Workforce | Future demand and capacity management | Provider CIP - above 2%
4 | 2019-20 |  | TBC | 2016-10-31 | 2017-07-31 | Progress report | Good achievement |  | Prevention and wellbeing | Healthy living and smoking cessation |  | 2018-07-31 | London guideline or best practice | Q2, 2017-18 | 100 | 540 | Domain 4 - Ensuring that people have a positive experience of care: looks at the importance of providing a positive experience of care for patients, service users and carers. | Procurement | Improved outcomes | Existing transformation programme (eg TST, ACO)
5 | 20120-21 |  |  | 2016-11-30 | 2017-08-31 | No attachment | Fair achievement |  | Enhanced Primary care | Housing and planning |  | 2018-08-31 | NEL ambition | Q3, 2017-18 |  |  | Domain 5 - Treating and caring for people in a safe environment and protecting them from avoidable harm: explores patient safety and its importance in terms of quality of care to deliver better health outcomes. | Contracting/commissioning | Improved patient experience | Local authority
|  |  |  | 2016-12-31 | 2017-09-30 |  | Poor achievement | Yes, completed | Planned Care: maternity | Self-care management |  | 2018-09-30 | BHR ambition | Q4, 2017-18 |  |  |  | Communications | Improved performance
|  |  |  | 2017-01-31 | 2017-11-30 |  | National outlier (poor) | Yes, partially completed | Planned Care: Cancer | Community based end of life care |  | 2018-10-31 | C&H ambition | Q1, 2018-19 |  |  |  | Engagement | Improved quality
|  |  |  | 2017-02-28 | 2017-12-31 |  | N/A (new service) | No, to be completed | Planned Care: Surgery | Enhanced primary care |  | 2018-11-30 | WEL ambition | Q2, 2018-19 |  |  |  |  | Service innovation
|  |  |  | 2017-03-31 | 2018-01-31 |  |  | Please refer to separate SRO |  | Reducing unnecessary diagnostics |  | 2018-12-31 | Borough ambition | Q3, 2018-19
[5 empty] | 2018-02-28 |  |  |  | Unscheduled care | Pathway redesign and best in class clinical productivity, especially outpatient care |  | 2019-01-31 |  | Q4, 2018-19
[5 empty] | 2018-03-31 |  |  |  | Mental Health | Medicines management |  | 2019-02-28 |  | Q1, 2019-20
[9 empty] | Medicines management | High quality integrated mental health care and support |  | 2019-03-31 |  | Q2, 2019-20
[9 empty] | Procurement | Ambulatory care |  |  |  | Q3, 2019-20
[9 empty] | Bank & agency and back office (HR) | Integrated health and social care |  |  |  | Q4, 2019-20
[9 empty] | Back office (finance) | Integration children's and young people's care |  |  |  | Q1, 2020-21
[9 empty] | Back office (IT) | Transforming Sexual Health services |  |  |  | Q2, 2020-21
[9 empty] | Pathology | Localised programmes for learning disabilities |  |  |  | Q3, 2020-21
[9 empty] | Estates utilisation and productivity | Screening for cancer and other conditions |  |  |  | Q4, 2020-21
[9 empty] | Estates disposals | Integrated urgent and emergency care (including LAS)
[9 empty] | New capacity | Improving the treatment of cancer in community and secondary settings
[9 empty] | Cancer | Planned care strategy, including surgery
[9 empty] | Cardiac | Maternity
[9 empty] | Mental Health | Safely transitioning patients from King George Hospital's emergency dept
Renal
Neonatal
Communications
Digital
Finance
Workforce
Learning disabiliites

## Backing sheet (hidden)
Programme | Programme | Vision | Is delivery of the aim on track? (RAG = 1,2,3) | SRO: | Delivery lead: | Current delivery level: | Background | Case for change | Case for change doc attached? | Financial case for change | Financial case for change doc attached? | Programme position Aug 16 | Programme position Aug 16 doc attached? | Workstream 1 | Workstream 1 doc attached? | Workstream 2 | Workstream 2 doc attached? | Workstream 3 | Workstream 3 doc attached? | Workstream 4 | Workstream 4 doc attached? | Workstream 5 | Workstream 5 doc attached? | Workstream 6 | Workstream 6 doc attached? | Workstream 7 | Workstream 7 doc attached? | Governance | Governance diagramme attached | Objective 1 | Objective 2 | Objective 3 | Objective 4 | Objective 5 | In scope | Out of scope | Constraint 1 | Constraint 2 | Constraint 3 | Constraint 4 | Constraint 5 | Assumption 1 | Assumption 2 | Assumption 3 | Assumption 4 | Assumption 5 | Risk 1 | Risk 1 Mitigation | Risk 1 score post mitigation | Risk 2 | Risk 2 Mitigation | Risk 2 score post mitigation | Risk 3 | Risk 3 Mitigation | Risk 3 score post mitigation | Risk 4 | Risk 4 Mitigation | Risk 4 score post mitigation | Risk 5 | Risk 5 Mitigation | Risk 5 score post mitigation | Deliverable 1 | Deliverable 1 target date | Deliverable 1 status | Deliverable 2 | Deliverable 2 target date | Deliverable 2 status | Deliverable 3 | Deliverable 3 target date | Deliverable 3 status | Deliverable 4 | Deliverable 4 target date | Deliverable 4 status | Deliverable 5 | Deliverable 5 target date | Deliverable 5 status | Anything else? | Who completed | Organisation | Email | Telephone number
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!