## CBC Milestones
SEL Community Based Care Implementation Milestones | [16 empty] | 2016-10-21
| 2015/16 |  |  |  | 2016/17 |  |  |  | 2017/18 |  |  |  | 2018/19 |  |  |  | 2019/20
Milestones | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4
Federation/Alliances Established | bar: 2016/17 Q1 to 2017/18 Q1
All local GP practices have agreed to an Alliance | bar: 2015/16 Q1 to 2016/17 Q1
The Alliance has a recognised legal identity | bar: 2015/16 Q1 to 2016/17 Q1
Commissioner offer made to Alliance and contract in place following due diligence | bar: 2015/16 Q1 to 2017/18 Q1
3 to 5 year business plan developed | bar: 2015/16 Q3 to 2017/18 Q1
LCN integrated system leadership & management | bar: 2017/18 Q1
Local Care Networks defined | bar: 2015/16 Q1 to 2016/17 Q1
LCN leadership team & management structure in place with clear governance and decision-making arrangements | bar: 2015/16 Q1 to 2016/17 Q1
Enabling strategies, e.g. workforce, IM&T, Estates embedded across networks with localised delivery plans | bar: 2017/18 Q1
Accessible Care standards and associated big hitters implemented | bar: 2017/18 Q1 to 2017/18 Q2
Improved access to GP practice including 8 to 8 7/7 | bar: 2015/16 Q1 to 2017/18 Q2
UCC/walk-in centres | bar: 2015/16 Q1 to 2016/17 Q1
Able to share medical records across federations | bar: 2015/16 Q1 to 2017/18 Q1
Single telephone triage and booking across federations | bar: 2015/16 Q1 to 2017/18 Q4
Reablement (encompassing rapid response and supported discharge) | bar: 2015/16 Q1 to 2016/17 Q4
Same day access to specialist advice and clinics (including diagnostics) | bar: 2015/16 Q1 to 2017/18 Q1
Proactive Care standards and associated big hitters implemented | bar: 2017/18 Q1 to 2018/19 Q1
Local communities and stakeholders actively and routinely involved in priority setting and service redesign across networks | bar: 2015/16 Q1 to 2018/19 Q1
Asset mapping and social prescribing | bar: 2015/16 Q1 to 2017/18 Q1
Care coordinators/navigators/patient liaison across networks | bar: 2015/16 Q1 to 2017/18 Q1
Health & Wellbeing champions across networks | bar: 2015/16 Q1 to 2018/19 Q1
Primary prevention and enhanced public health programmes | bar: 2015/16 Q1 to 2018/19 Q1
Active risk stratification | bar: 2015/16 Q1 to 2016/17 Q1
Training in motivational skills and health coaching | bar: 2016/17 Q1 to 2017/18 Q1
Enhanced call & recall and screening for hard to reach groups | bar: 2016/17 Q1 to 2017/18 Q1
Enhanced support to vulnerable people in care homes, extra care housing and receiving domiciliary care | bar: 2016/17 Q1
Coordinated Care standards and associated big hitters implemented | bar: 2018/19 Q1
Active care registers within GP practices | bar: 2015/16 Q1 to 2016/17 Q1
Identifying people at risk of developing LTCs | bar: 2016/17 Q1 to 2017/18 Q3
Patient/carer education programmes | bar: 2016/17 Q1 to 2018/19 Q1
See MDT working below, reablement above, care coordinators above, assigned care professionals below
Continuity of Care standards and associated big hitters implemented | bar: 2016/17 Q1 to 2017/18 Q1
All patients have a named GP | bar: 2015/16 Q1 to 2017/18 Q1
Flexible appointment lengths according to patient need commissioned | bar: 2015/16 Q1 to 2017/18 Q1
Assigned care professional in final year of life | bar: 2015/16 Q1 to 2017/18 Q1
Multi-disciplinary teams established within networks | bar: 2015/16 Q1 to 2017/18 Q1
Key:
Milestone | bar: 2015/16 Q1
Delivery window | bar: 2015/16 Q1 to 2015/16 Q3

## Dashboard
SEL CBC & Primary Care Delivery Plan |  | SEL Progress Dashboard
|  | Select Date | Q1 April 2018
|  | Select Specification (for right graph) | Health and wellbeing liaison and information
SEL integrated single system leadership and management progress Q1 April 2018
SEL GP Alliance/Federation progress Q1 April 2018
SEL Specification - Health and wellbeing liaison and information progress Q1 April 2018
Detailed progress at Q1 April 2018 |  | Select Area | Bromley
Integrated single system leadership and management |  | Progress at Q1 April 2018 |  | Bromley integrated single system leadership and management progress to Q1 April 2018
Local Care Networks defined | LCNs defined | 100%
Leadership & Common Voice (formal/informal leadership development programmes, local learning sets) | Leadership and common voice | 100%
Access to Expertise (governance, structure development, legal support, business dev. & new models of care) | Access to expertise | 100%
Direct Management Support (coaching/mentoring, management/admin staff) | Direct management support | 100%
Time & Headroom (facilitated events and engagement across the network) | Time and headroom | 100%
Peer Working & Support (enabling strategies, e.g. workforce, IM&T, Estates and across networks) | Peer working and support | 100%
LCN leadership team & management structure in place with the 'core' represented/engaged and with clear governance and decision-making arrangements | LCN leadership team | 100%
GP Alliances/Federations |  | Progress at Q1 April 2018
All local GP practices have agreed to an Alliance | All GP practices agreed to alliance | 100%
The practices are geographically aligned | Geographical alignment | 100% |  | Bromley GP Alliance/Federation progress to Q1 April 2018
The Alliance has a recognised legal identity | Legal identity | 100%
The Alliance is registered with the CQC | CQC registered | 100%
Specification for an enhanced primary care service created and agreed | Specification for enhanced primary care | 100%
Commissioner offer made to Alliance and contract in place following due diligence | Commissioner offer made and contract in place | 100%
Alliance leadership, governance & decision-making arrangements in place | Leadership, governance & decision-making arrangements in place | 100%
Alliance management structure in place | Management structure in place | 100%
3 to 5 year business plan developed | 3 to 5 year business plan developed | 100%
Specifications |  | Progress at Q1 April 2018 |  | Bromley service specifications progress to Q1 April 2018
Patient Choice |  | 100%
Contacting the practice |  | 100%
Routine opening hours |  | 100%
Extended opening hours |  | 100%
Same day access |  | 100%
Urgent and Emergency Care |  | 100%
Continuity of Care |  | 100%
Co-Design |  | 100%
Developing assets and resources for improving health and wellbeing |  | 100%
Personal conversations focussed on an individual's health goals |  | 100%
Health and wellbeing liaison and information |  | 100%
Patients not currently accessing primary care services |  | 100%
Case finding and review |  | 100%
Named professional |  | 100%
Care Planning |  | 100%
Patients supported to manage their health and wellbeing |  | 100%
Multi-disciplinary working |  | 100%

## SEL
SEL CBC & Primary Care Delivery Plan |  |  |  |  | Key: |  | Step in progress |  |  |  | Activity begins to be met for some patients
[7 empty] | Step complete |  |  |  | SPG specification delivery date
Predicted pan London delivery date
[6 empty] | 2015 |  |  |  | 2016 |  |  |  | 2017 |  |  |  | 2018 |  |  |  | 2019 |  |  |  | 2020
[5 empty] | Pre-2015 | Q1 April 2015 | Q2 Jul 2015 | Q3 Oct 2015 | Q4 Jan 2016 | Q1 April 2016 | Q2 Jul 2016 | Q3 Oct 2016 | Q4 Jan 2017 | Q1 April 2017 | Q2 Jul 2017 | Q3 Oct 2017 | Q4 Jan 2018 | Q1 April 2018 | Q2 Jul 2018 | Q3 Oct 2018 | Q4 Jan 2019 | Q1 April 2019 | Q2 Jul 2019 | Q3 Oct 2019 | Q4 Jan 2020 | Q1 April 2020 | Q2 Jul 2020 | Q3 Oct 2020 | Q4 Jan 2021
Spec |  |  | Owner | Start | Pre-2015 | Year 1 |  |  |  | Year 2 |  |  |  | Year 3 |  |  |  | Year 4 |  |  |  | Year 5
Integrated single system leadership and management
|  | SEL |  |  | 9.65% | 31.74% | 45.54% | 55.68% | 69.75% | 74.79% | 75.98% | 79.7% | 98.21% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
|  | Bexley |  |  | 0% | 0% | 42.86% | 50% | 71.43% | 78.57% | 78.57% | 78.57% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
|  | Bromley |  |  | 6% | 28.57% | 35.71% | 50% | 64.29% | 71.43% | 71.43% | 78.57% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
|  | Greenwich |  |  | 7.143% | 7.143% | 50% | 57.14% | 67.86% | 78.57% | 78.57% | 78.57% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
|  | Lambeth |  |  | 7.143% | 57.14% | 57.14% | 60.71% | 92.86% | 92.86% | 92.86% | 92.86% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
|  | Lewisham |  |  | 0% | 17.86% | 17.86% | 35.71% | 35.71% | 39.29% | 46.43% | 53.57% | 92.86% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
|  | Southwark |  |  | 35.71% | 64.29% | 67.86% | 78.57% | 82.14% | 85.71% | 85.71% | 92.86% | 96.43% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
Notes: degree to which LCNs may become organisations in their own right will become clearer over time
Federations/Alliances
|  | SEL |  |  | 25.82% | 46.48% | 60.5% | 69.52% | 84.29% | 91.37% | 96.27% | 97.2% | 97.9% | 97.9% | 99.3% | 99.3% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
|  | Bexley |  |  | 29.56% | 38.89% | 44.44% | 50% | 61.11% | 72.22% | 77.78% | 77.78% | 83.33% | 83.33% | 94.44% | 94.44% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
|  | Bromley |  |  | 11.11% | 52.78% | 69.44% | 86.11% | 94.44% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
|  | Greenwich |  |  | 0% | 55.56% | 55.56% | 55.56% | 94.44% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
|  | Lambeth |  |  | 38.89% | 41.67% | 55.56% | 72.22% | 83.33% | 86.11% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
|  | Lewisham |  |  | 0% | 0% | 38.89% | 50% | 72.22% | 86.11% | 94.44% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
|  | Southwark |  |  | 72.22% | 88.89% | 94.44% | 94.44% | 94.44% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
Notes:
Accessible Care
A1 | Spec | Patient Choice
|  | SEL |  |  | 20.77% | 53.01% | 53.68% | 63.28% | 76.1% | 85.78% | 87.43% | 93.11% | 95.37% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
|  | Bexley |  |  | 14.29% | 21.43% | 21.43% | 64.29% | 75% | 82.14% | 85.71% | 92.86% | 96.43% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
|  | Bromley |  |  | 28.57% | 32.14% | 35.71% | 42.86% | 71.43% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
|  | Greenwich |  |  | 0% | 75% | 75% | 89.29% | 92.86% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
|  | Lambeth |  |  | 14.29% | 89.29% | 89.29% | 92.86% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
|  | Lewisham |  |  | 28.57% | 46.43% | 46.43% | 46.43% | 64.29% | 64.29% | 64.29% | 82.14% | 82.14% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
|  | Southwark |  |  | 35.71% | 42.86% | 42.86% | 42.86% | 50% | 64.29% | 71.43% | 82.14% | 92.86% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
Notes:
A2 |  | Contacting the practice
|  | SEL |  |  | 11.75% | 52.9% | 58.84% | 67.64% | 71.45% | 81.94% | 82.32% | 89.14% | 92.06% | 97.27% | 98.42% | 98.42% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
|  | Bexley |  |  | 0% | 17.5% | 17.5% | 52.5% | 60% | 77.5% | 77.5% | 82.5% | 82.5% | 85% | 87.5% | 87.5% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
|  | Bromley |  |  | 2.5% | 62.5% | 85% | 90% | 90% | 92.5% | 92.5% | 95% | 97.5% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
|  | Greenwich |  |  | 0% | 38.5% | 43.5% | 53% | 53% | 77.5% | 80% | 87.5% | 90% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
|  | Lambeth |  |  | 10% | 65% | 70% | 80% | 90% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
|  | Lewisham |  |  | 0% | 40% | 40% | 40% | 40% | 45% | 45% | 70% | 80% | 95% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
|  | Southwark |  |  | 55% | 80% | 80% | 80% | 85% | 92.5% | 92.5% | 95% | 97.5% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
Notes:
A3 |  | Routine opening hours
|  | SEL |  |  | 0% | 52.18% | 83.22% | 91.67% | 91.67% | 95.84% | 96.85% | 96.85% | 97.48% | 98.11% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
|  | Bexley |  |  | 0% | 0% | 0% | 67% | 67% | 67% | 75% | 75% | 80% | 85% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
|  | Bromley |  |  | 0% | 0% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
|  | Greenwich |  |  | 0% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
|  | Lambeth |  |  | 0% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
|  | Lewisham |  |  | 0% | 0% | 75% | 75% | 75% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
|  | Southwark |  |  | 0% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
Notes:
A4 |  | Extended opening hours
|  | SEL |  |  | 28.36% | 54.11% | 57.04% | 65.42% | 74.62% | 80.38% | 80.38% | 89.14% | 91.24% | 98.01% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
|  | Bexley |  |  | 33.33% | 33.33% | 33.33% | 33.33% | 50% | 50% | 50% | 66.67% | 83.33% | 91.67% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
|  | Bromley |  |  | 33.33% | 83.33% | 91.67% | 75% | 75% | 83.33% | 83.33% | 91.67% | 91.67% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
|  | Greenwich |  |  | 0% | 31.25% | 31.25% | 62.5% | 68.75% | 87.5% | 87.5% | 93.75% | 93.75% | 93.75% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
|  | Lambeth |  |  | 33.33% | 50% | 50% | 83.33% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
|  | Lewisham |  |  | 0% | 16.67% | 25% | 25% | 41.67% | 50% | 50% | 75% | 75% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
|  | Southwark |  |  | 66.67% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
Notes:
A5 |  | Same day access
|  | SEL |  |  | 10.68% | 41.37% | 44.57% | 47.43% | 50.76% | 82.2% | 82.2% | 87.93% | 90.24% | 97.48% | 97.48% | 97.48% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
|  | Bexley |  |  | 0% | 20% | 30% | 30% | 35% | 65% | 65% | 70% | 75% | 80% | 80% | 80% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
|  | Bromley |  |  | 5% | 25% | 30% | 40% | 40% | 90% | 90% | 95% | 95% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
|  | Greenwich |  |  | 20% | 67% | 67% | 67% | 67% | 90% | 90% | 90% | 90% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
|  | Lambeth |  |  | 0% | 65% | 70% | 75% | 80% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
|  | Lewisham |  |  | 0% | 5% | 5% | 5% | 5% | 50% | 50% | 75% | 75% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
|  | Southwark |  |  | 40% | 60% | 60% | 60% | 70% | 90% | 90% | 90% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
Notes:
A6 |  | Urgent and Emergency Care
|  | SEL |  |  | 12.19% | 49.05% | 57.54% | 65.01% | 65.01% | 80.1% | 80.1% | 84.27% | 97.92% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
|  | Bexley |  |  | 0% | 33.33% | 0% | 50% | 50% | 83.33% | 75% | 75% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
|  | Bromley |  |  | 8.333% | 12.5% | 43.75% | 50% | 50% | 75% | 75% | 75% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
|  | Greenwich |  |  | 33.33% | 50% | 75% | 75% | 75% | 75% | 75% | 75% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
|  | Lambeth |  |  | 0% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
|  | Lewisham |  |  | 0% | 0% | 12.5% | 12.5% | 12.5% | 50% | 50% | 75% | 87.5% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
|  | Southwark |  |  | 33.33% | 87.5% | 93.75% | 93.75% | 93.75% | 93.75% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
Notes:
A7 |  | Continuity of Care
|  | SEL |  |  | 16.97% | 46.56% | 49.74% | 57.66% | 66.59% | 82.14% | 83.94% | 86.39% | 91.17% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
|  | Bexley |  |  | 4.286% | 50% | 50% | 78.57% | 82.14% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
|  | Bromley |  |  | 37.86% | 46.43% | 53.57% | 57.14% | 71.43% | 92.86% | 92.86% | 96.43% | 96.43% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
|  | Greenwich |  |  | 16.43% | 67.86% | 71.43% | 75% | 78.57% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
|  | Lambeth |  |  | 16.43% | 46.43% | 50% | 53.57% | 67.86% | 71.43% | 71.43% | 71.43% | 71.43% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
|  | Lewisham |  |  | 0% | 14.29% | 17.86% | 28.57% | 32.14% | 57.14% | 60.71% | 71.43% | 89.29% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
|  | Southwark |  |  | 21.43% | 57.14% | 57.14% | 60.71% | 71.43% | 78.57% | 85.71% | 85.71% | 96.43% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
Notes:
Proactive Care
Delivery of specifications
P1 |  | Co-Design
|  | SEL |  |  | 12.7% | 77.56% | 81.73% | 85.98% | 89.98% | 97.83% | 97.83% | 97.83% | 98.6% | 98.6% | 99.37% | 99.37% | 99.37% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
|  | Bexley |  |  | 0% | 87.5% | 87.5% | 87.5% | 91.67% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
|  | Bromley |  |  | 4.167% | 75% | 75% | 79.17% | 79.17% | 91.67% | 91.67% | 91.67% | 95.83% | 95.83% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
|  | Greenwich |  |  | 0% | 70.83% | 70.83% | 70.83% | 70.83% | 95.83% | 95.83% | 95.83% | 95.83% | 95.83% | 95.83% | 95.83% | 95.83% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
|  | Lambeth |  |  | 0% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
|  | Lewisham |  |  | 0% | 37.5% | 62.5% | 83.33% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
|  | Southwark |  |  | 70.83% | 91.67% | 91.67% | 91.67% | 95.83% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
Notes:
P2 |  | Developing assets and resources for improving health and wellbeing
|  | SEL |  |  | 21.19% | 42.75% | 47.59% | 57.52% | 61.34% | 74.59% | 76.42% | 83.45% | 88.78% | 96.06% | 96.06% | 96.06% | 98.58% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
|  | Bexley |  |  | 0% | 11.25% | 23.75% | 55% | 56.25% | 68.75% | 75% | 84.38% | 84.38% | 93.75% | 93.75% | 93.75% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
|  | Bromley |  |  | 25% | 31.25% | 37.5% | 43.75% | 43.75% | 59.38% | 59.38% | 87.5% | 87.5% | 90.62% | 90.62% | 90.62% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
|  | Greenwich |  |  | 0% | 34.38% | 34.38% | 34.38% | 34.38% | 68.75% | 68.75% | 68.75% | 68.75% | 90.62% | 90.62% | 90.62% | 90.62% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
|  | Lambeth |  |  | 25% | 75% | 75% | 78.12% | 78.12% | 90.62% | 90.62% | 93.75% | 96.88% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
|  | Lewisham |  |  | 50% | 56.25% | 56.25% | 62.5% | 75% | 75% | 81.25% | 81.25% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
|  | Southwark |  |  | 18.75% | 34.38% | 46.88% | 65.62% | 75% | 81.25% | 81.25% | 81.25% | 90.62% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
Notes:
P3 |  | Personal conversations focussed on an individual's health goals
|  | SEL |  |  | 28.28% | 48.96% | 54.35% | 58.33% | 74.04% | 80.75% | 83.19% | 87.18% | 94.54% | 98.74% | 98.74% | 98.74% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
|  | Bexley |  |  | 16.67% | 41.67% | 50% | 58.33% | 75% | 75% | 83.33% | 91.67% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
|  | Bromley |  |  | 25% | 25% | 33.33% | 41.67% | 66.67% | 75% | 75% | 83.33% | 91.67% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
|  | Greenwich |  |  | 33.33% | 58.33% | 58.33% | 58.33% | 58.33% | 83.33% | 83.33% | 83.33% | 83.33% | 91.67% | 91.67% | 91.67% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
|  | Lambeth |  |  | 33.33% | 66.67% | 66.67% | 66.67% | 83.33% | 83.33% | 83.33% | 83.33% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
|  | Lewisham |  |  | 33.33% | 41.67% | 50% | 58.33% | 66.67% | 75% | 83.33% | 91.67% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
|  | Southwark |  |  | 25% | 58.33% | 66.67% | 66.67% | 91.67% | 91.67% | 91.67% | 91.67% | 91.67% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
Notes:
P4 |  | Health and wellbeing liaison and information
|  | SEL |  |  | 13.32% | 32.15% | 36.55% | 47.36% | 57.44% | 64.96% | 67.02% | 69.65% | 72.86% | 82.9% | 82.9% | 83.84% | 98% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
|  | Bexley |  |  | 0% | 10% | 10% | 35% | 37.5% | 43.75% | 50% | 62.5% | 68.75% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
|  | Bromley |  |  | 18.75% | 25% | 25% | 37.5% | 37.5% | 50% | 50% | 50% | 56.25% | 56.25% | 56.25% | 56.25% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
|  | Greenwich |  |  | 0% | 25% | 25% | 31.25% | 50% | 62.5% | 62.5% | 62.5% | 62.5% | 75% | 75% | 81.25% | 93.75% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
|  | Lambeth |  |  | 12.5% | 43.75% | 50% | 56.25% | 75% | 87.5% | 93.75% | 93.75% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
|  | Lewisham |  |  | 31.25% | 37.5% | 50% | 62.5% | 75% | 75% | 75% | 75% | 75% | 75% | 75% | 75% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
|  | Southwark |  |  | 12.5% | 43.75% | 50% | 56.25% | 62.5% | 62.5% | 62.5% | 68.75% | 68.75% | 93.75% | 93.75% | 93.75% | 93.75% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
Notes:
P5 |  | Patients not currently accessing primary care services
|  | SEL |  |  | 3.264% | 20.01% | 21.05% | 37.36% | 50.72% | 65.81% | 70.54% | 73.54% | 74.7% | 92.79% | 92.79% | 93.95% | 93.95% | 94.89% | 94.89% | 94.89% | 94.89% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
|  | Bexley |  |  | 0% | 18.75% | 18.75% | 18.75% | 31.25% | 50% | 62.5% | 68.75% | 68.75% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
|  | Bromley |  |  | 6.25% | 17.5% | 17.5% | 36.25% | 36.25% | 56.25% | 56.25% | 62.5% | 68.75% | 93.75% | 93.75% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
|  | Greenwich |  |  | 0% | 43.75% | 43.75% | 43.75% | 56.25% | 81.25% | 81.25% | 81.25% | 81.25% | 87.5% | 87.5% | 87.5% | 87.5% | 93.75% | 93.75% | 93.75% | 93.75% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
|  | Lambeth |  |  | 0% | 12.5% | 12.5% | 50% | 93.75% | 93.75% | 93.75% | 93.75% | 93.75% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
|  | Lewisham |  |  | 0% | 0% | 6.25% | 18.75% | 25% | 37.5% | 37.5% | 37.5% | 37.5% | 75% | 75% | 75% | 75% | 75% | 75% | 75% | 75% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
|  | Southwark |  |  | 12.5% | 31.25% | 31.25% | 50% | 50% | 68.75% | 87.5% | 93.75% | 93.75% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
Notes:
Coordinated Care
C1 |  | Case finding and review
|  | SEL |  |  | 28.72% | 46.53% | 47.83% | 53.33% | 66.13% | 83.15% | 83.85% | 86.36% | 90.85% | 97.52% | 97.52% | 98.85% | 99.37% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
|  | Bexley |  |  | 33.33% | 45.83% | 50% | 62.5% | 70.83% | 83.33% | 83.33% | 91.67% | 91.67% | 95.83% | 95.83% | 95.83% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
|  | Bromley |  |  | 29.17% | 35.83% | 40% | 48.33% | 48.33% | 75% | 75% | 87.5% | 87.5% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
|  | Greenwich |  |  | 37.5% | 45.83% | 45.83% | 45.83% | 70.83% | 95% | 95% | 79.17% | 95% | 91.67% | 91.67% | 95.83% | 95.83% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
|  | Lambeth |  |  | 25% | 58.33% | 58.33% | 66.67% | 75% | 91.67% | 91.67% | 95.83% | 95.83% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
|  | Lewisham |  |  | 16.67% | 33.33% | 33.33% | 37.5% | 54.17% | 70.83% | 75% | 79.17% | 83.33% | 95.83% | 95.83% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
|  | Southwark |  |  | 33.33% | 58.33% | 58.33% | 58.33% | 79.17% | 83.33% | 83.33% | 83.33% | 91.67% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
Notes:
C2 |  | Named professional
|  | SEL |  |  | 19.14% | 42.22% | 47.76% | 51.84% | 63.86% | 78.63% | 80.39% | 87.49% | 88.96% | 98.32% | 98.32% | 99.25% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
|  | Bexley |  |  | 10% | 15% | 25% | 30% | 40% | 65% | 65% | 80% | 85% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
|  | Bromley |  |  | 40% | 44% | 49% | 54% | 64% | 75% | 80% | 90% | 90% | 95% | 95% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
|  | Greenwich |  |  | 25% | 55% | 55% | 55% | 65% | 85% | 85% | 85% | 85% | 95% | 95% | 95% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
|  | Lambeth |  |  | 0% | 60% | 60% | 60% | 80% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
|  | Lewisham |  |  | 30% | 40% | 45% | 50% | 65% | 75% | 80% | 85% | 90% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
|  | Southwark |  |  | 10% | 30% | 45% | 55% | 60% | 65% | 65% | 80% | 80% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
Notes:
C3 |  | Care Planning
|  | SEL |  |  | 23.93% | 44.37% | 47.8% | 52.59% | 64.99% | 80.89% | 82.12% | 85.66% | 88.64% | 97.92% | 97.92% | 99.05% | 99.42% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
|  | Bexley |  |  | 21.67% | 30.42% | 37.5% | 46.25% | 55.42% | 74.17% | 74.17% | 85.83% | 88.33% | 97.92% | 97.92% | 97.92% | 97.92% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
|  | Bromley |  |  | 34.58% | 39.92% | 44.5% | 51.17% | 56.17% | 75% | 77.5% | 88.75% | 88.75% | 97.5% | 97.5% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
|  | Greenwich |  |  | 31.25% | 50.42% | 50.42% | 50.42% | 67.92% | 90% | 90% | 82.08% | 90% | 93.33% | 93.33% | 95.42% | 97.92% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
|  | Lambeth |  |  | 12.5% | 59.17% | 59.17% | 63.33% | 77.5% | 95.83% | 95.83% | 97.92% | 97.92% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
|  | Lewisham |  |  | 23.33% | 36.67% | 39.17% | 43.75% | 59.58% | 72.92% | 77.5% | 82.08% | 86.67% | 97.92% | 97.92% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
|  | Southwark |  |  | 21.67% | 44.17% | 51.67% | 56.67% | 69.58% | 74.17% | 74.17% | 74.17% | 78.33% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
Notes:
C4 |  | Patients supported to manage their health and wellbeing
|  | SEL |  |  | 15.14% | 40.11% | 42.72% | 51.79% | 61.56% | 71.56% | 76.33% | 78.34% | 80.99% | 93.24% | 93.69% | 93.69% | 98.95% | 99.55% | 99.55% | 99.55% | 99.55% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
|  | Bexley |  |  | 0% | 9.286% | 20% | 41.43% | 46.43% | 57.14% | 57.14% | 67.86% | 67.86% | 89.29% | 92.86% | 92.86% | 96.43% | 96.43% | 96.43% | 96.43% | 96.43% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
|  | Bromley |  |  | 17.86% | 21.43% | 25% | 39.29% | 46.43% | 64.29% | 64.29% | 67.86% | 67.86% | 85.71% | 85.71% | 85.71% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
|  | Greenwich |  |  | 0% | 46.43% | 46.43% | 46.43% | 46.43% | 64.29% | 64.29% | 64.29% | 64.29% | 85.71% | 85.71% | 85.71% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
|  | Lambeth |  |  | 14.29% | 64.29% | 64.29% | 67.86% | 85.71% | 92.86% | 92.86% | 92.86% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
|  | Lewisham |  |  | 50% | 53.57% | 57.14% | 60.71% | 71.43% | 71.43% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
|  | Southwark |  |  | 3.571% | 35.71% | 35.71% | 50% | 64.29% | 71.43% | 71.43% | 71.43% | 78.57% | 96.43% | 96.43% | 96.43% | 96.43% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
Notes:
C5 |  | Multi-disciplinary working
|  | SEL |  |  | 50.56% | 54.73% | 54.73% | 60.75% | 72.47% | 84.42% | 89.06% | 93.69% | 93.69% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
|  | Bexley |  |  | 25% | 25% | 25% | 25% | 25% | 50% | 50% | 50% | 50% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
|  | Bromley |  |  | 15% | 15% | 15% | 25% | 25% | 50% | 75% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
|  | Greenwich |  |  | 50% | 50% | 50% | 50% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
|  | Lambeth |  |  | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
|  | Lewisham |  |  | 0% | 25% | 25% | 50% | 75% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
|  | Southwark |  |  | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
Notes:
SE London supporting activities
CBC Programme
Delivery Group
Delivery Dashboard
Local delivery plan development
Other CLGs Programmes
Alignment of interventions
IM&T
Estates
Workforce

## Bexley
SEL CBC & Primary Care Delivery Plan |  |  | Key: |  | Key: |  | Step in progress |  |  | Activity begins to be met for some patients
[7 empty] | Step complete |  |  | SPG specification delivery date
Predicted pan London delivery date
[6 empty] | 2015 |  |  |  | 2016 |  |  |  | 2017 |  |  |  | 2018 |  |  |  | 2019 |  |  |  | 2020
|  | Bexley |  |  | Pre-2015 | Q1 April 2015 | Q2 Jul 2015 | Q3 Oct 2015 | Q4 Jan 2016 | Q1 April 2016 | Q2 Jul 2016 | Q3 Oct 2016 | Q4 Jan 2017 | Q1 April 2017 | Q2 Jul 2017 | Q3 Oct 2017 | Q4 Jan 2018 | Q1 April 201 | Q2 Jul 2018 | Q3 Oct 2018 | Q4 Jan 2019 | Q1 April 2019 | Q2 Jul 2019 | Q3 Oct 2019 | Q4 Jan 2020 | Q1 April 2020 | Q2 Jul 2020 | Q3 Oct 2020 | Q4 Jan 2021 | Status | Activity to date | Dependent activity? | Change from current baseline | Funding required | Funding source | Funding secured | How will we know if it has been delivered (what are our measures?) | Support required from HLP
Spec |  | Examples of supporting activity | Owner | Start | Pre-2015 | Year 1 |  |  |  | Year 2 |  |  |  | Year 3 |  |  |  | Year 4 |  |  |  | Year 5 |  |  |  | Year 6 |  |  |  | On track Slippage Complete - Achieving Complete - under-achieving Other |  | Are there activities which must be completed before this activity can be commenced?
| Federations/Alliances | Integrated single system leadership and management |  |  | 0% | 0% | 42.86% | 50% | 71.43% | 78.57% | 78.57% | 78.57% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
|  | Local Care Networks defined |  |  | 0% | 0% | 50% | 50% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  | The 3 LCNs in Bexley are defined. |  | Same |  |  |  | 3 LCNs defined - Clocktower, Frognal & North Bexley. | None
|  | Leadership & Common Voice (formal/informal leadership development programmes, local learning sets) |  |  | 0% | 0% | 0% | 50% | 50% | 50% | 50% | 50% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  | The CCG arranged a practice development event in Summer 2015. Quarterly engagement events are in place on which primary care development features. Monthly LCN (locality) meetings are also in place with all practices. Fellow programme developed for future leaders. Integrated Care Organisation in development with Local Authority, Oxleas NHSFT, with Federation involvement to wrap around LCNs. Chair hosts monthly networking meetings and has open communication channels with all GPs. | Continued engagement of GP community and other stakeholders on LCN programme board. | Same | 10000 | CCG | Yes | LCNs on agenda and discussed at locality meetings and engagement events. Additionally aligned with Integrated Care Organisation work. | None
|  | Access to Expertise (governance, structure development, legal support, business dev. & new models of care) |  |  | 0% | 0% | 50% | 50% | 50% | 50% | 50% | 50% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  | LCN Board in place to take forward development. LCN Programme Director in place. Consultancy support being sought. | Ability to recruit consultancy to move agenda forward. | Same | 130000 | CCG | Yes | Appointment of Programme Director and consultancy support. | None
|  | Direct Management Support (coaching/mentoring, management/admin staff) |  |  | 0% | 0% | 50% | 50% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  | CCG Chair provides coaching and mentoring support. LCN programme director in place. Consultancy support being sought. |  | Same |  |  |  | Programme board and network set up and ongoing engagement. | None
|  | Time & Headroom (facilitated events and engagement across the network) |  |  | 0% | 0% | 50% | 50% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  | LCN Board in place to take forward development meets monthly & workshops held. Development meeting held with all Bexley practices in June. Further development event with all practices planned for September. |  | Same |  |  |  | Programme board and network set up and ongoing engagement. | None
|  | Peer Working & Support (enabling strategies, e.g. workforce, IM&T, Estates and across networks) |  |  | 0% | 0% | 50% | 50% | 50% | 50% | 50% | 50% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  | Data sharing in place across all practices and UCCs, now being extended to L&G (Connect care) and D&G trusts and Oxleas. Stakeholder groups for both estates and IT are in place with stakeholder involvement. Practice pharmacist pilot scheme now in place. | Continued HESL funding for PC staff training. SEL ETTF bid for Connect care to further progress data sharing. LCNs on local estates strategy group and ICT working group and Bexley linked care meeting. Active CEPN, hosted by CIC, working on various workforce strategies. | Same | tbc | HESL/ETTF | Pending | Data sharing across health economy; estates strategy implemented; sufficient workforce to deliver TPC. | None
|  | LCN leadership team & management structure in place with the 'core' represented/engaged and with clear governance and decision-making arrangements |  |  | 0% | 0% | 50% | 50% | 50% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  | LCNs established and being developed with federation involvement. Well established LCN (locality) structure in place with elected GP and locality leads and LCN chairs. | Continued engagement of GP community and other stakeholders and demonstration of whole system decision making. Ongoing development of LCN membership. | Same | 3000 | CCG | Yes | LCNs making decisions about services and fully operational. | None
Notes: LCN programme board established and meetings scheduled. Programme Director now in post
|  | Federations/Alliances |  |  | 29.56% | 38.89% | 44.44% | 50% | 61.11% | 72.22% | 77.78% | 77.78% | 83.33% | 83.33% | 94.44% | 94.44% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
|  | All local GP practices have agreed to an Alliance |  |  | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  | There is one federation (CIC) in Bexley. ICO being established. |  | Same |  |  |  | CIC & ICO in place. | None
|  | The practices are geographically aligned |  |  | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  | All practices are geographically aligned in 3 localities / LCNs. |  | Same |  |  |  | 3 LCNs defined - Clocktower, Frognal & North Bexley. | None
|  | The Alliance has a recognised legal identity |  |  | 33% | 50% | 50% | 50% | 50% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  | The legal entity is Bexley Neighbourhood Health CIC. |  | Same |  |  |  | CIC in place. | None
|  | The Alliance is registered with the CQC |  |  | 33% | 50% | 50% | 50% | 50% | 50% | 50% | 50% | 50% | 50% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  | The CIC has been advised by the CQC not to register. | Liaison needed London wide with CQC to get agreement that all federations need to be registered. | Slower |  |  |  | CIC registered with CQC. | Liaison with CQC.
|  | Specification for an enhanced primary care service created and agreed |  |  | 0% | 50% | 50% | 50% | 50% | 50% | 50% | 50% | 50% | 50% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  | CIC holds CEPN. Discussions underway with regards to Saturday morning provision. | The PMS review needs to be complete before discussions on Saturday morning provision can be finalised. | Slower |  |  |  | CIC delivering services. | None
|  | Commissioner offer made to Alliance and contract in place following due diligence |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 50% | 50% | 50% | 50% | 50% | 50% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  | Discussions have taken place with regards to Diabetes and Saturday mornings. Discussions ongoing. ICO to deliver community services. | The PMS review needs to be complete before discussions on Saturday morning provision can be finalised. ICO established. | Slower |  |  |  | CIC & ICO delivering services. | None
|  | Alliance leadership, governance & decision-making arrangements in place |  |  | 0% | 0% | 50% | 50% | 50% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  | CIC established with directors in post. |  | Same |  |  |  | Governance in place to take decisions regarding delivery of services. | Access to federation development activities.
|  | Alliance management structure in place |  |  | 0% | 0% | 0% | 50% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  | CIC established with directors in post. |  | Same |  |  |  | Governance in place to take decisions regarding delivery of services. | Access to federation development activities.
|  | 3 to 5 year business plan developed |  |  | 0% | 0% | 0% | 0% | 50% | 50% | 50% | 50% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  | Business plan under development. Meeting recently held to explore this. | Funding support required to facilitate writing of business plan. | Same | 10000 | Practices / HLP | No | Business Plan in place. | Support to Federation to write business plan.
Notes: three LCNs and one Bexley-wide CiC with legal entity in place
Accessible Care
A1 | Spec | Patient Choice | [28 empty] | Patients will be given a choice of access options and should be able to decide on the consultation most appropriate to their needs Different patients, in different situations, have different access needs. Some patients value continuity of care over rapid access. Some people place more value on seeing a particular clinician. Others want a more convenient appointment time, or to book an appointment four or more weeks in advance. General practice should make all these options available to the patient at the point of contact and allow the patient to select the service they want. Practices should also include reasonable adjustments to remove access barriers for patients, such as considerations for the homeless or non-English speakers, as well as adhering to the Equality Act (2010) for physical access needs (ramps, hearing loops etc.).
|  | SEL |  |  | 14.29% | 21.43% | 21.43% | 64.29% | 75% | 82.14% | 85.71% | 92.86% | 96.43% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
|  | Patient able to see particular clinician |  |  | 0% | 50% | 50% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  | Practice baseline audit evidenced that 100% of practices reported that all patients have an option to see a clinician of their choice. |  | Same |  |  |  | Patients see a particular clinician if requested. | None
|  | Patients able to book up to 4 weeks in advance |  |  | 0% | 0% | 0% | 75% | 75% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  | Practice baseline audit evidenced that 81% (22/27 practices) said that patients can book 4 weeks in advance. Working with other practices. | Practices willingness to facilitate and change appointment booking systems. Needs to be included in PMS and GMS contracts. | Same |  |  |  | Patients able to book an appointment 4 weeks in advance. | None
|  | Support available for non English speakers |  |  | 0% | 0% | 0% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  | Interpreting services in place across Bexley. |  | Same |  |  |  | Patients able to access interpreting services when required. | None
|  | Infrastructure available for accessibility (hearing loops etc.) |  |  | 0% | 0% | 0% | 75% | 75% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  | Practice baseline audit evidenced that 74% (20/27 practices) said they had a hearing loop, some practices have subsequently bid for PCIF funding. | NHS England management of PC contracts to ensure DDA compliant. | Same | TBA | Infrastructure grant | No | All practices meet required regulations for infrastructure. | None
|  | Patients able to book at times convenient to them |  |  | 0% | 0% | 0% | 0% | 50% | 50% | 75% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  | 90% of patients in the patient survey report satisfaction with convenience of appointments. |  | Same |  |  |  | Patients able to book a time convenient to them. | None
|  | Improved access to general practice - big hitter scheme |  |  | 0% | 0% | 0% | 0% | 25% | 25% | 25% | 50% | 75% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  | The CCG is piloting Web GP that facilitates self help and email consultations (c1/3 of the population). There is a working group of practices to pilot video consolations. Saturday mornings will be offered in Bexley under new PMS contract. Extended hours under 16/17 DES. | ETTF bid to implement infrastructure to role out video consultations. The PMS review needs to be complete before discussions on Saturday morning provision can be finalised. | Same | 350000 | CCG/ETTF | Pending | Patients able to access consultations through variety of means. | None
|  | Local Urgent Care Centres/Walk-in centres offering alternatives to GP practice |  |  | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  | There are 2 UCCs in Bexley, one open 24 hours and one 8am to 10pm. |  | Same |  |  |  | UCCs available in Bexley. | None
Notes:
A2 |  | Contacting the practice | [28 empty] | Patients will be required to only make one call, click or contact in order to make an appointment. Primary care teams will maximise the use of technology and actively promote online services to patients including appointment booking, prescription ordering, viewing medical records and email consultations. Currently appointments are often allocated based on who gets through to the practice rather than by clinical need. Many practices hold back appointments so that a patient getting through may be told that there are no appointments left but that they should call back later or the following day when more are released. This increases the number of calls coming into the practice as patients have to call several times before securing an appointment and patients who do call back join the back of the queue. In future patients would have multiple options for making an appointment, and would only need to make contact once in order to have a discussion with a clinician.
|  | SEL |  |  | 0% | 17.5% | 17.5% | 52.5% | 60% | 77.5% | 77.5% | 82.5% | 82.5% | 85% | 87.5% | 87.5% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
Individual practice level
|  | Telephone booking and triage system available |  |  | 0% | 0% | 0% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  | A number of practices offer telephone triage and all practices have been encouraged to offer this at PCDWG and engagement events. A focus group is in place to investigate front of house options, e.g. central telephone booking & triage to improve patient contact. |  | Same |  |  |  | Triage available in practices where found to be beneficial to patients. | None
|  | Online booking system available |  |  | 0% | 0% | 0% | 75% | 75% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  | Patients can book appointments through practice websites. Work is ongoing to improve and develop websites - investigation of central Bexley website hosted by Federation. All practices with low usage have been contacted by the PCDWG and has been discussed at practice visits. All practices have posters advertising online services. |  | Same |  |  |  | Patients able to book appointments online. | None
|  | Online prescription service available |  |  | 0% | 0% | 0% | 75% | 75% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  | Patients can order prescriptions through practice websites. |  | Same |  |  |  | Patients able to order prescriptions online | None
|  | Medical records available online (functionality available) |  |  | 0% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  | It is a contractual requirement for practices to make medical records available to patients who request them. Functionality is available to allow access online. | Practices updating websites to allow patients the ability to access medical records online. | Same |  |  |  | Infrastructure in place. | None
|  | Process/ IT in place to support email consultations |  |  | 0% | 50% | 50% | 50% | 75% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  | Web GP is being piloted for 1/3 of patients in Bexley which includes self help and email consultations. There is a working group of practices to pilot video consolations. | ETTF bid to implement infrastructure to role out video consultations. - See A1. | Same | See above | See above | See above | IT in place to support email consultations. | None
|  | Access routes (in particular online) advertised to patients |  |  | 0% | 25% | 25% | 50% | 75% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  | An article has been placed in the Bexley Magazine (March) to promote online services to patients. Work ongoing with Patient council. Posters in practices. |  | Same |  |  |  | Increased patient awareness of available access routes. | None
|  | Federation level | Federation level | Federation level
|  | Able to share medical records |  |  | 0% | 0% | 0% | 50% | 75% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  | Linked care (data sharing) in place across Bexley - 26/27 practices. Connect care agreement in place with LMC. | ETTF funding to support connect care infrastructure. | Same | 100000 | ETTF | Pending | Ability to share medical records between practices and practices and other providers. | None
|  | Single telephone booking and triage system |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  | There are no plans for a federated booking system for Monday to Friday 8am to 6.30pm. This is something that may be required for 8-8 top up assuming a federated approach is taken. | Practices willingness to partake in a single telephone booking and triage system. | Slower | 60000 | ETTF | Pending | Ability for patients to book for top-up 8-8 centrally. | None
|  | Online booking system |  |  | 0% | 0% | 0% | 0% | 0% | 25% | 25% | 50% | 50% | 50% | 75% | 75% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  | There are no plans for a federated online booking system for Monday to Friday 8am to 6.30pm. There will be a central booking system for Saturday mornings when in place. | The PMS review needs to be complete before discussions on Saturday morning provision can be finalised. | Slower | Ditto | Ditto | Ditto | Availability of centralised online booking system. | None
|  | Enhanced access options through working as a federation |  |  | 0% | 0% | 0% | 25% | 25% | 50% | 50% | 75% | 75% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  |  | ETTF bid to implement infrastructure to role out video consultations. | Same | See above | See above | See above | Availability of enhanced access options for Bexley patients. | None
Notes:
A3 |  | Routine opening hours | [28 empty] | Patients will be able to access pre-bookable routine appointments with a primary health care professional (see ‘workforce implications’ for the proposed primary care team) at all practices 8am – 6.30pm Monday to Friday and 8am to 12 noon on Saturdays. An alternative equivalent patient offer may be provided where there is a clear, evidenced local need. There is significant variation in opening hours across London. This specification will create an equitable offer to patients across the capital. During the specified hours, all practices will be open to allow patients to access all services, including attending an appointment, speaking to a receptionist, and collecting or ordering a prescription.
|  | SEL |  |  | 0% | 0% | 0% | 67% | 67% | 67% | 75% | 75% | 80% | 85% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
|  | All practices open in routine opening times |  |  | 0% | 0% | 0% | 67% | 67% | 67% | 75% | 75% | 80% | 80% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  | The CCG is working with all practices to ensure core hour provision. Some practices have reviewed and changed their opening hours as a result. | This is a contractual requirement and needs to be enforced by NHS England | Slower |  |  |  | All practices open for contractual hours. | None
|  | Contracts updated to specify appointments to be offered at these times |  |  | 0% | 0% | 0% | 67% | 67% | 67% | 75% | 75% | 80% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  |  | NHS England need to ensure this through PMS review. | Slower |  |  |  | All practices open for contractual hours. | None
|  | Workforce requirements met to offer appointments during these times |  |  | 0% | 0% | 0% | 67% | 67% | 67% | 75% | 75% | 80% | 80% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  | The workforce requirements required is for GPs to determine. However, there is a shortage of GPs in Bexley and it is difficult to recruit. The CCG is looking at a number of initiatives to encourage more GPs. A Fellows scheme has just been agreed and is in the process of being implemented. Substantial work on apprenticeships and mentoring schemes. CCG also asked for a number of GPs to be included in recent NHSE initiative for those finding it difficult to recruit. | Ability to recruit necessary clinical staff. | Slower |  |  |  | Availability of appointments during core hours. | None
|  | Appointments available at all routine times |  |  | 0% | 0% | 0% | 67% | 67% | 67% | 75% | 75% | 80% | 80% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  |  | NHS England need to enforce contractual requirements. | Slower |  |  |  | Availability of appointments during core hours. | None
Notes:
A4 |  | Extended opening hours | [28 empty] | Patients will be able to access a GP or other primary care health professional seven days per week, 12 hours per day (8am to 8pm or an alternative equivalent offer based on local need) in their local area, for pre-bookable and unscheduled care appointments. This service will be delivered by networks of practices working together at scale. In most cases a larger practice in the local community will take the lead to provide this service on behalf of other practices. A suggested offer of 8am to 8pm is described here, however there could be a suitable alternative equivalent offer based on local population needs, for which the totality of the offer (seven days, 12 hours) is not reduced.
|  | SEL |  |  | 33.33% | 33.33% | 33.33% | 33.33% | 50% | 50% | 50% | 66.67% | 83.33% | 91.67% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
|  | Local Urgent Care Centres/Walk-in centres offering extended hours |  |  | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  | The two urgent care centres in Bexley already offer unscheduled care during these times (12 hours a day). Pre-bookable appointments are being investigated. |  | Same |  |  |  | UCCs in place. | None
|  | Improved access to general practice - big hitter scheme |  |  | 0% | 0% | 0% | 0% | 25% | 25% | 25% | 50% | 75% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
|  | 8 to 8 7/7 |  |  | 0% | 0% | 0% | 0% | 25% | 25% | 25% | 50% | 75% | 75% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  |  | ETTF bid has been submitted for infrastructure funding - awaited result. The CCG also needs additional investment c£1m per annum to pay for the ongoing running costs. | Slower | £1.3m | ETTF/Transformation funding | No | Implementation of top up hubs | None
|  | Notes: Top up hub model proposed | [29 empty] | The CCG is only considering a top up hub model.
A5 |  | Same day access | [28 empty] | Patients who want to be seen the same day will be able to have a consultation with a GP or appropriately skilled nurse on the same day within routine surgery hours at the practice at which they are registered (see Specification A3: Routine opening hours). Patients with new health conditions often want to see or speak to a GP as soon as possible. It’s important for patients who may be distressed or suffer if diagnosis and treatment is delayed. Consultations could be face-to-face or on the phone (or video phone) but will be provided by a GP or an appropriately skilled nurse on the same day. Practices would be encouraged to use a demand led telephone triage system. These approaches provide a phone conversation with an appropriate clinician throughout the day, often within 30 minutes of the patient contacting the practice. The patient can then discuss their needs with the clinician and between them they can decide the most appropriate course of action (e.g. face-to-face consultation of appropriate length according to need; referral to community pharmacist, nurse, healthcare assistant or other service; booking for diagnostic tests; and self care).
|  | SEL |  |  | 0% | 20% | 30% | 30% | 35% | 65% | 65% | 70% | 75% | 80% | 80% | 80% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
As A4 above, and:
|  | Reablement big hitter encompassing rapid response and supported discharge |  |  | 0% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  | There is an integrated rapid response team in place that responds to crises to avoid hospital admissions. SUSD in place. |  | Same |  |  |  | Patients supported to prevent hospital admission and facilitate discharge. | None
|  | Telephone triage - practice |  |  | 0% | 0% | 50% | 50% | 75% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  | A number of practices offer telephone triage and all practices have been encouraged to offer this at PCDWG and engagement events. |  | Same |  |  |  | Triage available in practices where found to be beneficial to patients. | None
|  | Telephone triage - Federation/Alliance |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  | There are no plans for a federated booking system for Monday to Friday 8am to 6.30pm. This is something that may be required for 8-8 top up assuming a federated approach is taken. | Practices willingness to partake in a single telephone booking and triage system. | Slower | See A2 | See A2 | See A2 | Ability for patients to book for top-up 8-8 centrally. | None
|  | Access to specialist advice and specialist response clinic (U&EC intervention) |  |  | 0% | 0% | 0% | 0% | 0% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  | Practices refer to specialist advice and diagnostics as required following consultation. |  | Same |  |  |  | Specialist advice available to patients as agreed in consultations. | None
|  | Same day diagnostics (planned Care intervention) |  |  | 0% | 0% | 0% | 0% | 0% | 25% | 25% | 50% | 75% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  | This is not a requirement within the Transforming PC. Practices refer to specialist advice and diagnostics as required following consultation. |  | Same |  |  |  | Diagnostics available to patients as agreed in consultations. | None
Notes:
A6 |  | Urgent and Emergency Care | [28 empty] | Patients with urgent or emergency needs will need to be clinically assessed rapidly. Practices should have systems in place and skilled staff to ensure these patients are effectively identified and responded to appropriately. In the event that a patient accesses general practice with emergency care needs, there should be sufficient processes and procedures in place to enable all members of the practice to respond to that patient’s needs appropriately.
|  | SEL |  |  | 0% | 33.33% | 0% | 50% | 50% | 83.33% | 75% | 75% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
|  | All practice personnel trained to identify emergencies |  |  | 0% | 0% | 0% | 50% | 50% | 75% | 75% | 75% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  | The baseline audit evidenced: 100% of practices reported that that there are sufficient procedures and processes in place for staff to respond appropriately to patients' needs. |  | Faster |  |  |  | All practice personnel trained to identify emergencies. | None
|  | Processes in place to ensure emergencies are appropriately dealt with |  |  | 0% | 0% | 0% | 50% | 50% | 75% | 75% | 75% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  | There is an integrated rapid response team in place that responds to crises to avoid hospital admissions. Practices refer to specialist advice and diagnostics as required following consultation. |  | Faster |  |  |  | Processes in place and being used in all practices. | None
|  | Also see reablement above encompassing rapid response |  |  |  | 100% | [24 empty] | There is an integrated rapid response team in place that responds to crises to avoid hospital admissions. SUSD in place. |  | Same |  |  |  | Patients supported to prevent hospital admission and facilitate discharge. | None
|  | Also see access to specialist advice and specialist response clinic (U&EC intervention) | [7 empty] | 100% | [20 empty] | Practices refer to specialist advice and diagnostics as required following consultation. |  | Same |  |  |  | Specialist advice available to patients as agreed in consultations. | None
Notes: local CEPNs to ensure that staff are trained and processes in place
A7 |  | Continuity of Care | [28 empty] | All patients will be registered with a named GP who is responsible for providing an ongoing relationship for care coordination and care continuity. Practices will provide flexible appointment lengths as appropriate. All patients should have a named GP for care continuity and coordination. Other GPs or healthcare professionals within the practice team may provide care as appropriate but the named GP will effectively still oversee delivery of the care plan. General practice will routinely improve continuity of care through a range of mechanisms such as buddying; job sharing; forming ‘teams within teams’; developing organised handover systems; enhanced use of communication and recordkeeping technology; and increased involvement of patients and carers in care planning. These measures are of particular importance where personal continuity is not possible.
|  | SEL |  |  | 4.286% | 50% | 50% | 78.57% | 82.14% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
|  | All patients given a named GP as main contact (over 75s and risk stratified patients currently asper the DES from 2015/16) |  |  | 15% | 50% | 50% | 75% | 75% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  | All patients have a named GP. |  | Same |  |  |  | All patients have a named GP contact. | None
|  | Practice able to give flexible appointment lengths - links to offer/contract with Alliances/Federations |  |  | 0% | 0% | 0% | 75% | 75% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  | Practices already give flexible appointment times dependant on the patient's requirements. |  | Same |  |  |  | Patients given flexible appointment lengths. | None
|  | Assigned clinician/nurse in final year of life |  |  | 15% | 50% | 50% | 75% | 75% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  | Bexley has the largest increase in CMC usage in London. |  | Same |  |  |  | Patients have an assigned clinician in final year of life. | None
|  | Coordinate my care plans for patients identified as in final year of life |  |  | 0% | 50% | 50% | 75% | 75% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  | Bexley has the largest increase in CMC usage in London. |  | Same |  |  |  | CMC plans in place for patients identified as being in their final year of life. | None
|  | Able to share medical records |  |  | 0% | 0% | 0% | 50% | 75% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  | Sharing of medical records is in place across Bexley for 26/27 GP practices (read/write). |  | Same |  |  |  | Data sharing in place between practices | None
|  | See reablement above |  |  | 0% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  | There is an integrated rapid response team in place that responds to crises to avoid hospital admissions. SUSD in place. |  | Same |  |  |  | Patients supported to prevent hospital admission and facilitate discharge. | None
|  | Multi-disciplinary Teams |  |  | 0% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  | All practices have localised mdt meetings. ETTF bid to improve infrastructure for remote mdt. |  | Same | See above | See above | See above | MDT teams in place to improve continuity of care. | None
Notes:
Proactive Care
P1 |  | Co-Design | [28 empty] | Primary care teams will work with communities, patients, their families, charities and voluntary sector organisations to co-design approaches to improve the health and wellbeing of the local population. Involving individuals and communities in designing services will ensure that approaches are relevant locally; that they do not duplicate (and are integrated with) existing services in the community; and that they are more likely to be successful. The process of co-design in itself will support improved understanding of health and wellbeing for those involved, support the identification of community advocates and volunteers and further build community resilience. An example would be engaging local young people, schools and youth workers in designing new ways of communicating with young people living with a long term condition.
|  | SEL |  |  | 0% | 87.5% | 87.5% | 87.5% | 91.67% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
|  | Local strategy and annual plan for user and stakeholder engagement activities including hard to reach groups and communities |  |  | 0% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  | Patient engagement and comms plan in place. Patient engagement and comms teams part of PCDWG. |  | Same |  |  |  | Strategy & comms plan in place and good involvement from hard to reach groups & communities. | None
|  | Borough-wide representative PPV group established and recorded engagement activities taking place |  |  | 0% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  | Patient council, youth forum and pensioners forum in place. Mystery shopper scheme in place. CCG patient engagement team working with all practices to ensure that PPGs are in place. Active engagement with Healthwatch, who also sit on the PCDWG. |  | Same |  |  |  | Continued engagement from borough wide groups. | None
|  | Active Patient Participation at individual practices/LCNs |  |  | 0% | 75% | 75% | 75% | 75% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  | CCG patient engagement team working with all practices to ensure that PPGs are in place. |  | Same |  |  |  | Active patient participation at PPGs. | None
|  | Individual practices inviting and recording comments about services and actively responding |  |  | 0% | 75% | 75% | 75% | 75% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  | CCG patient engagement team working with all practices to ensure that PPGs are in place to fulfil contractual requirements and CQC expectations. Practices encouraging FFT responses and PPG involvement in services. Iplato FFT module in place which has improved response rate. |  | Same |  |  |  | Practices inviting patient involvement and comment and acting on comments. | None
|  | Local communities and stakeholders actively and routinely involved in priority setting and service redesign and their contributions recorded |  |  | 0% | 75% | 75% | 75% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  | Commissioning Intentions reviewed and discussed at engagement events and through patient groups including active stakeholder involvement. All service re-design initiatives feature patient involvement. |  | Same |  |  |  | Active patient involvement in commissioning intentions and service redesign. | None
|  | Variety of channels for communicating with and receiving/recording feedback from service users established |  |  | 0% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  | Building capacity transformation programme within LBB & BVSC has a 3-year plan of activities to engage the local communities and build resilience. Patient council, youth forum and pensioners forum in place. Mystery shopper scheme in place. |  | Same |  |  |  | Various communication and feedback channels available. | None
Notes:
P2 |  | Developing assets and resources for improving health and wellbeing | [28 empty] | Primary care teams will work with others to develop and map the local social capital and resources that could empower people to remain healthy; and to feel connected to others and to support in their local community. Practices will work with local voluntary and community, health, third sector and other organisations; and with local authorities to: • provide additional capacity for improving health and wellbeing (e.g. Citizen's Advice, community pharmacy services and the probation services) • protect community resources for future generations (e.g. with the Environment Agency) • test new ways to build and improve relationships with local communities • build a map of local community assets that can be harnessed for health and wellbeing • identify and develop local community health and wellbeing champions, advocates and volunteers. Establishing and maintaining an up-to-date map of community assets will assist a range of organisations involved in an individual’s care. The map will support other ‘first contact’ providers such as NHS 111 and community pharmacies to offer patients a range of options.
|  | SEL |  |  | 0% | 11.25% | 23.75% | 55% | 56.25% | 68.75% | 75% | 84.38% | 84.38% | 93.75% | 93.75% | 93.75% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
|  | Joint Market Position statement/commissioning intentions developed (LA/CCG - with key voluntary sector partners) |  |  | 0% | 0% | 0% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  | All key partners on LCN board. CIs include primary care with all stakeholders engaged in development. Commissioning Intentions reviewed and discussed at engagement events and through patient groups including active stakeholder involvement. |  | Same |  |  |  | Commissioning intentions developed and agreed with partners / stakeholders. | None
|  | Local asset map developed with key partners and stakeholders and in place |  |  | 0% | 0% | 0% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  | BVSC directory of services with links in practices' favourites and on Vibe. Practices encouraged to include link on website. LBB have developed online care portal that links to marketplace for identifying all services in the borough that support health & social care needs for adults. The building capacity transformation board chaired by LBB/BVSC focussed on building community resilience and ensuring the best use of voluntary services to support the public sector. |  | Same |  |  |  | Asset map in place. | None
|  | Social Prescribing scheme in place |  |  | 0% | 40% | 40% | 40% | 50% | 50% | 50% | 75% | 75% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  | Social prescribing in place in Clocktower and health champions pilot in place across Bexley. Health champions uses volunteers. Library service offers a range of services to support the wellbeing agenda. & working with practices to promote services. Citizens Advice Bureau working with practices to help address social / financial issues. Providers Advice Forum in Bexley to ensure joined up services and appropriate access for vulnerable people. Care hub in place. Web GP pilot in place across 1/3 of Bexley patients to encourage self help and facilitate e-consultations. | Outcome of pilot needs to be assessed. Likelihood that a mixture of Social Prescribing and health champions will be rolled out across Bexley. | Same | 100000 | CCG | No | Social prescribing / health champions scheme in place. | None
|  | Developing role of wider primary care team and using more effectively e.g. community pharmacy |  |  | 0% | 0% | 50% | 75% | 75% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  | The Federation was successful in its bid for a pilot for pharmacists working in general practice across the borough. | CIC/practices rolling put practice pharmacists. | Same |  |  |  | Flexible workforce in practices. | None
|  | Local community health and wellbeing champions identified and developed |  |  | 0% | 0% | 50% | 75% | 75% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  | Health champions pilot in place across Bexley. Health champions uses volunteers who are fully trained. | Outcome of pilot needs to be assessed. Likelihood that a mixture of Social Prescribing and health champions will be rolled out across Bexley. | Same | See above | See above | See above | Social prescribing / health champions scheme in place. | None
|  | Care coordinators/patient liaison established across LCNs |  |  | 0% | 0% | 0% | 0% | 0% | 50% | 50% | 75% | 75% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  | Some practices have home grown patient liaison / care coordinators - discussed at PCDWG. Some care coordination built into CCG discharge schemes. |  | Same |  |  |  | Care Coordinators / patient liaison in place. | None
|  | Primary prevention and public health programmes (obesity, alcohol and smoking) |  |  | 0% | 50% | 50% | 50% | 50% | 50% | 50% | 75% | 75% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  | LBB responsible for public health programmes. Smoking cessation service currently being redesigned to serve the most vulnerable segment of the population. CCG offers obesity prevention service through BVSC for 7 year olds. Walking away from diabetes service in place in Bexley. Programme also in place to encourage activity to over 40s. Sexual health service in place advertised to patients by LBB. | LBB to implement dependant on funding cuts. | Same | tba | LBB/CCG | No | Prevention and PH programmes in place. | None
|  | Federation to define the services to be offered and to build on existing provision - links to offer/contract with Alliances/Federations |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 50% | 50% | 50% | 50% | 50% | 50% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  |  | Federation needs to work with LBB to define. | Slower |  |  |  | CIC delivering enhanced services. | None
Notes: pilot social prescribing scheme in one LCN and considering roll-out; health champions across all LCNs in 6 practices to start Jan 16; weight management programme in place and being extended to children.
P3 |  | Personal conversations focussed on an individual's health goals | [28 empty] | Q admissions risk strat tool in place and all practices signed up for DES in 15/16. Practices have staff in place who have motivational and health coaching skills. Further training being organised provided by LBB. As part of introduction of PCIF in 15/16, a representative from every practice had to attend training in motivational behaviour change related to obesity. 18 health champion volunteers have completed motivational skills and health coaching training funded by the CCG.
|  | SEL |  |  | 16.67% | 41.67% | 50% | 58.33% | 75% | 75% | 83.33% | 91.67% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
|  | Risk stratification tool in place and DES to have goal setting conversations with 2% of population |  |  | 50% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  | Q admissions risk strat tool in place and all practices signed up for DES in 15/16. |  | Same |  |  |  | Risk strat tool and DES in place. | None
|  | Training for GP practice staff in motivational skills and health coaching |  |  | 0% | 25% | 50% | 75% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  | Practices have staff in place who have motivational and health coaching skills. Further training being organised provided by LBB. As part of introduction of PCIF in 15/16, a representative from every practice had to attend training in motivational behaviour change related to obesity. |  | Same |  |  |  | GP practice staff trained in motivational skills and health coaching. | None
|  | Training for others within the LCN (including vol sector and health champions) in motivational skills and health coaching |  |  | 0% | 0% | 0% | 0% | 25% | 25% | 50% | 75% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  | 18 health champion volunteers have completed motivational skills and health coaching training funded by the CCG. |  | Same |  |  |  | Others in LCN trained in motivational skills and health coaching. | None
Notes:
P4 |  | Health and wellbeing liaison and information | [28 empty] | Primary care teams will enable and assist people to access information, advice and connections that will allow them to achieve better health and wellbeing. This health and wellbeing liaison function will extend into schools, workplaces and other community settings. These services would offer a range of interventions from brief focused information to more extensive advice and support. Interventions could include group support, 1:1 coaching, signposting and improving health literacy. The service would also build partnerships to build on the contribution to health and wellbeing already made by leisure centres, gyms and voluntary groups.
|  | SEL |  |  | 0% | 10% | 10% | 35% | 37.5% | 43.75% | 50% | 62.5% | 68.75% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
|  | Asset mapping advertised and accessible (hard copy and on-line) |  |  | 0% | 0% | 0% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  | Care Hub leaflets in development for advertising within GP practices. Practices dedicating space to libraries information. Asset mapping available online via libraries and contact centre and available to health champions & through social prescribing. Voluntary health champions and social prescriber trained in use of asset resource. Care hub and community assets available to all. Health information being publicised in libraries A number of the jointly commissioned prevention & early intervention services have active programmes in the community. Programme on preventing loneliness in place. Community programme across Bexley in December to raise awareness to dementia (Dementia friends). Work continuing to develop a dementia action alliance so that businesses are engaged in process. |  | Same |  |  |  | Asset mapping available and accessible. | None
|  | Active programmes in the community (i.e. schools, workplaces and other community settings) |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  | Youth forum in place to engage younger generation. Libraries service in place across the borough offering community groups to engage the local population. Active patient's forum. Work underway to work with schools. | Accessibility to schools, workplaces etc. | Same | 25000 | CCG | Yes | Active community programmes in place. | None
|  | Care coordinators/navigators/liaison trained in how to access resource |  |  | 0% | 0% | 0% | 0% | 0% | 25% | 50% | 75% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  | Practices and health champions trained in use of services. |  | Same |  |  |  | Training in how to access resource undertaken. | None
|  | Health champions, carers and service users able to use resources |  |  | 0% | 40% | 40% | 40% | 50% | 50% | 50% | 75% | 75% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  | Practices and health champions trained in use of services. |  | Same |  |  |  | Users able to use resources. | None
Notes:
P5 |  | Patients not currently accessing primary care services | [28 empty] | Primary care teams will design ways to reach people who do not routinely access services and who may be at higher risk of ill health. This specification focuses on two key areas: 1. People on the registered list (but not attending the practice). • Practices will design ways to reach vulnerable patients who may live in circumstances which make it harder for them to access general practice. This includes patients whose language and culture form barriers to receiving care, for instance gypsies, travellers, sex workers, homeless people, vulnerable migrants, people in care homes, and people with learning disabilities or severe mental illness. Practices will identify the patients on their registered list who have not been attending and are therefore at higher risk of ill health. These may be people who have declined invitations for services, are reaching crisis, suffering social isolation or stigma. These patients will require a more personalised service offer, care coordination and care planning. Using peer advocates who have direct personal experience and can empathise with patients has been shown to be an effective way of engaging with these groups of patients. • Primary care teams will also design approaches to follow up those patients who might be attending the practices from time to time but are not taking up invitations for services such as screening and vaccinations. Understanding the root causes for non-attendance will be crucial to ensuring maximum take-up of these services in the future; for example, understanding religious or cultural reasons for non-attendance. 2. The unregistered population. • Working collaboratively across a population and across multiple agencies, primary care teams will also design (with the support of their CCG) ways to reach and care for the unregistered population, for example homeless patients and people released from custody or places of detention.
|  | SEL |  |  | 0% | 18.75% | 18.75% | 18.75% | 31.25% | 50% | 62.5% | 68.75% | 68.75% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
|  | Enhanced Call & recall for screening and vaccinations programme targeting hard to reach groups - consider link to Alliance/Federation offer/contract |  |  | 0% | 0% | 0% | 0% | 50% | 50% | 50% | 50% | 50% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  | Will happen through new PMS KPI targets. Iplato in place which allows practices to send invites for screening & vaccinations & send reminders to targeted groups. | NHS England need to ensure this through PMS review. | Same |  |  |  | Enhanced call, recall for screening & vacs prog in place to target hard to reach groups. | None
|  | Support to vulnerable people in the community (care homes, extra care housing and domiciliary care) |  |  | 0% | 50% | 50% | 50% | 50% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  | LES in place with practices to support care homes. Health champions scheme linking into sheltered housing scheme to explore opportunities. Provider forum set up to support vulnerable people. PCDWG has had focus on homelessness and carers. Flu vaccination programme in 15/16 for housebound patients. |  | Same |  |  |  | Support available to vulnerable people in the community. | None
|  | Working with local third sector, local authority and community groups to identify people not accessing services and co-design and implement ways of reaching such people |  |  | 0% | 25% | 25% | 25% | 25% | 50% | 50% | 75% | 75% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  | Healthwatch liaising with hard to reach groups undertaking engagement work. |  | Same |  |  |  | Identifying and reaching those not accessing services. | None
|  | Training for carers and others to recognise symptoms and engage with primary care services |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 50% | 50% | 50% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  | Resources for carers through the Care Hub now available. Carers can access support through social prescribing & health champions. |  | Same |  |  |  | Carers and others trained to recognise symptoms. | None
Notes:
Coordinated Care
C1 |  | Case finding and review | [28 empty] | Practices will identify patients who would benefit from coordinated care and continuity with a named clinician, and will proactively review those that are identified on a regular basis. Patients with complex conditions who need care from more than one professional or team will be added to a coordinated care register and will be provided with an enhanced level of service. These patients may have long term conditions but may also be patients with a range of other health conditions and social support needs such as children and families with complex problems; people with mental health conditions; people in nursing homes; people at the end of life; or vulnerable people who find it hard to access services (for example homeless patients; those with learning difficulties or members of the traveller community). Patients will be identified using a combination of clinical alerts, risk profiling and clinical judgment. Every practice, or network of practices where appropriate, will run a regular risk profiling/risk stratification process in order to identify patients who should be on their care coordination register. The intensity of care, frequency and duration of contact with patients should be scaled up or stepped down as a result of reviews and patient progress. This should enable practices to identify those who may be, or are at risk of, experiencing an exacerbation of their condition but who have not reached a crisis point to seek treatment.
|  | SEL |  |  | 33.33% | 45.83% | 50% | 62.5% | 70.83% | 83.33% | 83.33% | 91.67% | 91.67% | 95.83% | 95.83% | 95.83% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
|  | Risk Stratification tool in place, evaluated and further developed |  |  | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  | A risk strat tool is in place across Bexley. there is 100% sign up to the avoiding unplanned admissions DES in 15/16 which is now extended for 1617. |  | Same |  |  |  | Risk strat tool in place. | None
|  | Active care registers in place |  |  | 50% | 50% | 75% | 75% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  | Practices have a range of registers in place to capture various groups. Active care registers are in place for 2% patients- frequent fliers at ED, Nursing Home residents, registered under the GP enhanced contract. |  | Same |  |  |  | Active care registers in place. | None
|  | Extending care registers beyond 2% of the adult population - consider as part of offer/contract with Federation/Alliance |  |  | 0% | 0% | 0% | 25% | 25% | 50% | 50% | 75% | 75% | 75% | 75% | 75% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  | This is not a requirement of TPC. | This is not a requirement of TPC. | Slower | 250000 | tbc | No | Care registers extended beyond 2%. | None
|  | Working with local third sector, local authority and community groups to identify people at risk |  |  | 0% | 50% | 50% | 75% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  | Working with LBB and providers forum on homeless people. District nurses liaise with practices. MDT teams in place in practices. Bexley also has the largest increase in CMC in London. BVSC, LBB and hospice on PCDWG working with practices. Palliative Personal care now in place with GBCH. | Continued engagement of stakeholders. | Same |  |  |  | Identification of people at risk. | None
|  | Identify people at risk of developing LTCs (see P5) |  |  | 0% | 25% | 25% | 50% | 50% | 50% | 50% | 75% | 75% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  | Working with LBB and providers forum on homeless people. District nurses liaise with practices. MDT teams in place in practices. Bexley also has the largest increase in CMC in London. BVSC, LBB and hospice on PCDWG working with practices. Palliative Personal care now in place with GBCH. Primary Care Improvement Fund (PCIF) looks to better case finding of dementia to improve identification and registration rates to 76%. Identify people at risk- childhood obesity measurement programme via PCIF, to identify and intervene to support improved lifestyle. Health checks offered by practices funded by LBB. Social prescribing and health champions in place for social support needs. Practices advertising library services which also offers a range of social support. |  | Same |  |  |  | Identification of people at risk of developing LTCs. | None
|  | Hospital in-reach linked to reablement and end of life services |  |  | 50% | 50% | 50% | 50% | 50% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  | Hospital in reach services/Rapid Response services are in place. Bexley also has the largest increase in CMC in London. |  | Same | 250000 | CCG | Yes | Hospital-in-reach in place. | None
Notes: CCG confirmed position
C2 |  | Named professional | [28 empty] | Patients identified as needing coordinated care will have a named professional who oversees their care and ensures continuity. All patients identified as needing coordinated care should have a named professional from whom they routinely receive their care. The lead GP will provide continuity of care, either personally or in collaboration with a 'micro team' of clinicians and professionals in and around the practice, for example members of the wellbeing team or community pharmacists. Patients may also be allocated an additional member of the practice team or an additional health or social care professional as a care coordinator to act as their first point of contact if they have questions, concerns or problems. The person who coordinates their care should work with the patient to achieve their goals. For some patients this will require extended consultations, for others it will mean regular contact with an extended primary care team. Patients with more complex needs would ideally be able to contact their care coordinator 24/7 for certain periods of very acute clinical risk or towards the end of their life. The intensity of contact and amount of time spent with the named GP and extended team will fluctuate in accordance with need, as assessed by risk profiling and regular communication with patients and their family and carers. The GP should act as an advocate and guide and should coordinate care with the extended practice team and a wider multidisciplinary team as appropriate. If patients go into hospital or transition to other services, general practice should continue to be proactively informed about the patient as they move between services, continuing to coordinate their care if appropriate.
|  | SEL |  |  | 10% | 15% | 25% | 30% | 40% | 65% | 65% | 80% | 85% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
|  | Named professional assigned to individuals on care register |  |  | 50% | 50% | 75% | 75% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  | Practice baseline audit stated 24/27 have a named GP assigned to patients; other 3 practices are working on this area. All patients on CMC have a named professional. |  | Same |  |  |  | Named professional assigned to individuals on care register. | None
|  | Care coordinators/patient liaison established across (see P2) |  |  | 0% | 0% | 0% | 0% | 0% | 50% | 50% | 75% | 75% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  | All practices have localised mdt meeting. Some practices have patient liaison officers / care coordinators. Practices have been encouraged to grow their own care co-ordinators. Some care coordination built into CCG discharge schemes. |  | Same |  |  |  | Care Coordinators / patient liaison in place. | None
|  | Named professional assigned to others at risk (see C1) |  |  | 0% | 0% | 0% | 0% | 0% | 50% | 50% | 75% | 75% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  | Working with LBB and providers forum on homeless people. District nurses liaise with practices. MDT teams in place in practices. Bexley also has the largest increase in CMC in London. BVSC, LBB and hospice on PCDWG working with practices. Palliative Personal care now in place with GBCH. | Working with other stakeholders to identify those at risk. |  |  |  |  | Named professional assigned to others at risk. | None
|  | Training for GP practice staff in motivational skills and health coaching (see P3) |  |  | 0% | 25% | 50% | 75% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  | Motivational skills training has been organised and run for practice staff and health champions. Training has been given in Identifying and Providing support to overweight and obese children and young people. Practices have staff in place who have motivational and health coaching skills. Further training being organised provided by LBB. As part of introduction of PCIF in 15/16, a representative from every practice had to attend training in motivational behaviour change related to obesity. |  | Same |  |  |  | GP practice staff trained in motivational skills and health coaching. | None
|  | Training for others within the LCN (including vol sector and health champions) in motivational skills and health coaching (see P3) |  |  | 0% | 0% | 0% | 0% | 0% | 25% | 25% | 50% | 75% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  | Motivational skills training has been organised and run for practice staff and health champions. Training has been given in Identifying and Providing support to overweight and obese children and young people. 18 health champion volunteers have completed motivational skills and health coaching training funded by the CCG. |  | Same |  |  |  | Others in LCN trained in motivational skills and health coaching. | None
Notes:
C3 |  | Care Planning | [28 empty] | Each individual identified for coordinated care will be invited to participate in a holistic care planning process in order to develop a single care plan that can be shared with teams and professionals involved in their care. Development of the care plan should follow the approach described in Delivering Better Services for People with Long Term Conditions – Building the House of Care. This represents a departure from the current focus on individual diseases towards a generic approach in which patients’ goals drive care delivery and greater attention is paid to the contribution that people make towards managing their own health. Care planning should be based on a philosophy of co-created goals for maintaining and improving health. It should be an iterative process that continues for as long as an individual has complex needs. Patients identified for coordinated care, and their carers, should be encouraged to play an active part in determining their own care and support needs as part of a collaborative care planning process. This should involve discussing care and support options, agreeing goals the patient can achieve themselves, and co-producing a single holistic care plan that includes the needs of family and carers.
|  | SEL |  |  | 21.67% | 30.42% | 37.5% | 46.25% | 55.42% | 74.17% | 74.17% | 85.83% | 88.33% | 97.92% | 97.92% | 97.92% | 97.92% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  | 0%
|  | See C1 above |  |  | 33.33% | 45.83% | 50% | 62.5% | 70.83% | 83.33% | 83.33% | 91.67% | 91.67% | 95.83% | 95.83% | 95.83% | 95.83% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  | • In line with Avoiding Unplanned Admissions, practices carry out monthly review and MDT case care planning. This is being supported by the CCG, supporting the practices to bring in other care services that would be helpful. • Patients are invited to partake in care planning and this is shared with the wider MDT. • Further plans are in place to enable the sharing of data across Bexley Practices (Bexley Linked Care) • CMC registration rates have increased by over 100% since April 1st –supported by PCIF incentive scheme (71 additions pcm vs. 29 before scheme). This will have a major impact on the patients achieving their Preferred place of death, given that since its inception, 79% of CMC patients in have died in their preferred place. (Where patients have a CMC care plan, 17% die in hospital, nationally, 54% die in hospital) | Continued engagement of stakeholders. | Same |  |  |  | See C1 above | None
|  | See C2 above |  |  | 10% | 15% | 25% | 30% | 40% | 65% | 65% | 80% | 85% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  | • In line with Avoiding Unplanned Admissions, practices carry out monthly review and MDT case care planning. This is being supported by the CCG, supporting the practices to bring in other care services that would be helpful. • Patients are invited to partake in care planning and this is shared with the wider MDT. • Further plans are in place to enable the sharing of data across Bexley Practices (Bexley Linked Care) • CMC registration rates have increased by over 100% since April 1st –supported by PCIF incentive scheme (71 additions pcm vs. 29 before scheme). This will have a major impact on the patients achieving their Preferred place of death, given that since its inception, 79% of CMC patients in have died in their preferred place. (Where patients have a CMC care plan, 17% die in hospital, nationally, 54% die in hospital) | Working with other stakeholders to identify those at risk. | Same |  |  |  | See C2 above | None
Notes:
C4 |  | Patients supported to manage their health and wellbeing | [28 empty] | Patients identified as needing coordinated care will have a named professional who oversees their care and ensures continuity. All patients identified as needing coordinated care should have a named professional from whom they routinely receive their care. The lead GP will provide continuity of care, either personally or in collaboration with a 'micro team' of clinicians and professionals in and around the practice, for example members of the wellbeing team or community pharmacists. Patients may also be allocated an additional member of the practice team or an additional health or social care professional as a care coordinator to act as their first point of contact if they have questions, concerns or problems. The person who coordinates their care should work with the patient to achieve their goals. For some patients this will require extended consultations, for others it will mean regular contact with an extended primary care team. Patients with more complex needs would ideally be able to contact their care coordinator 24/7 for certain periods of very acute clinical risk or towards the end of their life. The intensity of contact and amount of time spent with the named GP and extended team will fluctuate in accordance with need, as assessed by risk profiling and regular communication with patients and their family and carers. The GP should act as an advocate and guide and should coordinate care with the extended practice team and a wider multidisciplinary team as appropriate. If patients go into hospital or transition to other services, general practice should continue to be proactively informed about the patient as they move between services, continuing to coordinate their care if appropriate.
|  | SEL |  |  | 0% | 9.286% | 20% | 41.43% | 46.43% | 57.14% | 57.14% | 67.86% | 67.86% | 89.29% | 92.86% | 92.86% | 96.43% | 96.43% | 96.43% | 96.43% | 96.43% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
|  | Asset Mapping (see P2) |  |  | 0% | 0% | 0% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  | BVSC directory of services with links in practices' favourites and on Vibe. Practices encouraged to include link on website. LBB have developed online care portal that links to marketplace for identifying all services in the borough that support health & social care needs for adults. The building capacity transformation board chaired by LBB/BVSC focussed on building community resilience and ensuring the best use of voluntary services to support the public sector. |  | Same |  |  |  | Asset map in place. | None
|  | Social Prescribing (see P2) |  |  | 0% | 40% | 40% | 40% | 50% | 50% | 50% | 75% | 75% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  | Social prescribing in place in Clocktower and health champions pilot in place across Bexley. Health champions uses volunteers. Library service offers a range of services to support the wellbeing agenda. & working with practices to promote services. Citizens Advice Bureau working with practices to help address social / financial issues. Providers Advice Forum in Bexley to ensure joined up services and appropriate access for vulnerable people. Care hub in place. Web GP pilot in place across 1/3 of Bexley patients to encourage self help and facilitate e-consultations. | Outcome of pilot needs to be assessed. Likelihood that a mixture of Social Prescribing and health champions will be rolled out across Bexley. | Same | See above | See above | See above | Social prescribing / health champions scheme in place. | None
|  | H&WB champions (see P2) |  |  | 0% | 0% | 50% | 75% | 75% | 75% | 75% | 75% | 75% | 75% | 75% | 75% | 75% | 75% | 75% | 75% | 75% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  | Health champions trained & pilot in place across Bexley. Social prescribing in place in Clocktower and health champions pilot in place across Bexley. CCG has pulled together online resources available for practices. | Outcome of pilot needs to be assessed. Likelihood that a mixture of Social Prescribing and health champions will be rolled out across Bexley. | Same | See above | See above | See above | Social prescribing / health champions scheme in place. | None
|  | Care coordinators (see P2) |  |  | 0% | 0% | 0% | 0% | 0% | 50% | 50% | 75% | 75% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  | Health champions pilot in place across Bexley. Health champions uses volunteers who are fully trained. | Outcome of pilot needs to be assessed. Likelihood that a mixture of Social Prescribing and health champions will be rolled out across Bexley. | Same | See above | See above | See above | Social prescribing / health champions scheme in place. | None
|  | Health Coaching (see P3) |  |  | 0% | 25% | 50% | 75% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  | See P2 & P3. |  | Same |  |  |  | GP practice and other LCN staff trained in motivational skills and health coaching. | None
|  | Active Programmes in the community (see P4) |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  | Working with BVSC and libraries on programmes in the community. | Accessibility to schools, workplaces etc. | Same | See above | See above | See above | Active community programmes in place. | None
|  | Patient/carer education programmes |  |  | 0% | 0% | 0% | 0% | 0% | 25% | 25% | 50% | 50% | 50% | 75% | 75% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  | Expert patient programme for diabetes in place. Self management tools embedded in DXS in every practice. Carers hub now in place in Bexley. |  | Same | 100000 | CCG | Yes | Patient/Carer education programmes in place. | None
Notes:
C5 |  | Multi-disciplinary working | [28 empty] | Patients identified for coordinated care will receive regular multidisciplinary reviews by a team involving health and care professionals with the necessary skills to address their needs. The frequency and range of disciplines involved will vary according to the complexity and stability of the patient and as agreed with the patient/carer. Patients on the coordinated care register will have a review by a multidisciplinary team involving clinicians from within the practice and from linked services. GPs should be regular, active participants in multidisciplinary reviews of their registered patients who have been identified for coordinated care. The frequency of multidisciplinary reviews will vary according to changing needs. Multidisciplinary reviews should ideally include professionals from both health and social care. This might include acute care specialists, social services, housing and finance advisors, community matrons, mental health specialists and district nurses depending on the needs of the patient. General practice should fully participate in multidisciplinary work across the health and care system and use reflective learning to improve patient care and for system enhancement.
|  | SEL |  |  | 25% | 25% | 25% | 25% | 25% | 50% | 50% | 50% | 50% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
|  | CBC Big Hitter |  |  | 25% | 25% | 25% | 25% | 25% | 50% | 50% | 50% | 50% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  | In line with Avoiding Unplanned Admissions, practices carry out monthly review and MDT case care planning. This is being supported by the CCG, supporting the practices to bring in other care services that would be helpful. Patients are invited to partake in care planning and this is shared with the wider MDT. Patients frequently admitted to hospital are discussed at a virtual MDT meeting with A&E consultant, LAS, district nurse and social worker and GP (chaired by community geriatrician). |  | Same | 350000 | CCG/ETTF | Pending | MDT reviews in place. | None
Notes: Older people service in place, under review with the intention of expanding

## Bromley
SEL CBC & Primary Care Delivery Plan |  |  |  |  | Key: |  | Step in progress |  |  | Activity begins to be met for some patients
[7 empty] | Step complete |  |  | SPG specification delivery date
Predicted pan London delivery date
[6 empty] | 2015 |  |  |  | 2016 |  |  |  | 2017 |  |  |  | 2018 |  |  |  | 2019 |  |  |  | 2020
|  | Bromley - validated |  |  | Pre-2015 | Q1 April 2015 | Q2 Jul 2015 | Q3 Oct 2015 | Q4 Jan 2016 | Q1 April 2016 | Q2 Jul 2016 | Q3 Oct 2016 | Q4 Jan 2017 | Q1 April 2017 | Q2 Jul 2017 | Q3 Oct 2017 | Q4 Jan 2018 | Q1 April 2018 | Q2 Jul 2018 | Q3 Oct 2018 | Q4 Jan 2019 | Q1 April 2019 | Q2 Jul 2019 | Q3 Oct 2019 | Q4 Jan 2020 | Q1 April 2020 | Q2 Jul 2020 | Q3 Oct 2020 | Q4 Jan 2021 | Dependent activity? | Change from current baseline | Funding required | Funding source | Funding secured | How will we know if it has been delivered (what are our measures?) | Support required from HLP
Spec |  | Examples of supporting activity | Owner | Start | Pre-2015 | Year 1 |  |  |  | Year 2 |  |  |  | Year 3 |  |  |  | Year 4 |  |  |  | Year 5 |  |  |  | Year 6 |  |  |  | Are there activities which must be completed before this activity can be commenced?
| Federations/Alliances | Integrated single system leadership and management |  |  | 6% | 28.57% | 35.71% | 50% | 64.29% | 71.43% | 71.43% | 78.57% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
|  | Local Care Networks defined |  |  | 25% | 50% | 50% | 50% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | Complete
|  | Leadership & Common Voice (formal/informal leadership development programmes, local learning sets) |  |  | 0% | 0% | 0% | 50% | 50% | 50% | 50% | 50% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | Bromley providers have been supported with their development and understanding to deliver ICNs through a series of call-off days with Impower. This has led to Bromley providers putting forward bids for how they will use ICN funding to deliver the Bromley ICN model. These are being presented and approved in July and August 2016. | Same |  |  |  | Provider bids approved and implemented. ICNs in operation.
|  | Access to Expertise (governance, structure development, legal support, business dev. & new models of care) |  |  | 0% | 25% | 25% | 50% | 50% | 50% | 50% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | This has been provided by the CCG for ICN stakeholders. The governance structures and legal documentation are in place for ICNs. | Faster
|  | Direct Management Support (coaching/mentoring, management/admin staff) |  |  | 0% | 25% | 25% | 50% | 50% | 50% | 50% | 50% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | This has been provided by the CCG as part of the ICN development process and Impower support. | Same |  |  |  | Ongoing throughout delivery of ICNs.
|  | Time & Headroom (facilitated events and engagement across the network) |  |  | 0% | 50% | 50% | 50% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | Complete
|  | Peer Working & Support (enabling strategies, e.g. workforce, IM&T, Estates and across networks) |  |  | 0% | 0% | 50% | 50% | 50% | 50% | 50% | 50% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | This will be subject to ongoing work across partners throughout the life of the ICNs. | Same |  |  |  | Ongoing throughout delivery of ICNs.
|  | LCN leadership team & management structure in place with the 'core' represented/engaged and with clear governance and decision-making arrangements |  |  | 17% | 50% | 50% | 50% | 50% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | Complete
Notes: 6 co-located community teams since 2013 and one on-going LCN integrated care team pilot. Under review supported by on-going external facilitation and extensive membership engagement (complete) with clear principles agreed.
|  | Federations/Alliances |  |  | 11.11% | 52.78% | 69.44% | 86.11% | 94.44% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
|  | All local GP practices have agreed to an Alliance |  |  |  | 75% | 75% | 75% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | Complete | Same
|  | The practices are geographically aligned |  |  | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | Complete | Same
|  | The Alliance has a recognised legal identity |  |  | 0% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | Complete | Same
|  | The Alliance is registered with the CQC |  |  | 0% | 0% | 0% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | Complete | Same
|  | Specification for an enhanced primary care service created and agreed |  |  | 0% | 0% | 50% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | Complete | Same
|  | Commissioner offer made to Alliance and contract in place following due diligence |  |  | 0% | 0% | 0% | 0% | 50% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | Complete | Same
|  | Alliance leadership, governance & decision-making arrangements in place |  |  | 0% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | Complete | Same
|  | Alliance management structure in place |  |  | 0% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | Complete | Same
|  | 3 to 5 year business plan developed |  |  | 0% | 0% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | Partially complete - a shorter term business plan has been produced by the GP Alliance but this is consistent with CCG strategy. | Slower |  |  |  | GP Alliance to produce a 3-5 year business plan, tied in to CCG strategy.
Notes: 86% of population covered by Bromley GP Alliance Ltd. Alliance has assumed responsibility for CEPN. Specifications/proposals for enhanced primary care covering dementia, extended hours for under 18s and shared care prescribing being developed as is a business plan
Accessible Care
A1 | Spec | Patient Choice
|  | SEL |  |  | 28.57% | 32.14% | 35.71% | 42.86% | 71.43% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
|  | Patient able to see particular clinician |  |  | 0% | 0% | 0% | 0% | 50% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | Complete | Same
|  | Patients able to book up to 4 weeks in advance |  |  | 0% | 0% | 0% | 0% | 50% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | Complete | Same
|  | Support available for non English speakers |  |  | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | Complete | Same
|  | Infrastructure available for accessibility (hearing loops etc.) |  |  | 0% | 0% | 0% | 0% | 50% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | Complete | Same
|  | Patients able to book at times convenient to them |  |  | 0% | 0% | 0% | 0% | 50% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | Complete | Same
|  | Improved access to general practice - big hitter scheme |  |  | 0% | 25% | 50% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | Complete | Same
|  | Local Urgent Care Centres/Walk-in centres offering alternatives to GP practice |  |  | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | Complete | Same
Notes: Plan for improved access to be developed but is dependent upon Alliance buy-in and incentives to overcome operational challenges to move towards a networked approach.
A2 |  | Contacting the practice
|  | SEL |  |  | 2.5% | 62.5% | 85% | 90% | 90% | 92.5% | 92.5% | 95% | 97.5% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
Individual practice level
|  | Telephone booking and triage system available |  |  | 0% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | Complete | Same
|  | Online booking system available |  |  | 0% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | Complete | Same
|  | Online prescription service available |  |  | 0% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | Complete | Same
|  | Medical records available online (functionality available) |  |  | 0% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | Complete | Same
|  | Process/ IT in place to support email consultations |  |  | 0% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | Complete | Same
|  | Access routes (in particular online) advertised to patients |  |  | 0% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | Complete | Same
Federation level
|  | Able to share medical records |  |  | 25% | 25% | 50% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  | Faster
|  | Single telephone booking and triage system |  |  | 0% | 0% | 0% | 0% | 0% | 25% | 25% | 50% | 75% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | We do not have a triage system in place, other than use of 111 and enabling our UCCs to refer to the primary care access hubs. | Same
|  | Online booking system |  |  | 0% | 0% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  | Faster
|  | Enhanced access options through working as a federation |  |  | 0% | 0% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  | Faster
Notes: Individual practice positions to be confirmed by CQC, including practice leaflets/websites advertising access routes. Limited sharing of records with community provider liked to diabetes management with discussions underway.
A3 |  | Routine opening hours
|  | SEL |  |  | 0% |  | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
|  | All practices open in routine opening times |  |  | 0% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | Unsure - see comment. As the current contract holders with primary care, we would need NHSE to influence this. | Slower |  |  |  | All practices are open 8am-6.30pm.
|  | Contracts updated to specify appointments to be offered at these times |  |  | 0% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | As above. | Slower |  |  |  | All contracts updated.
|  | Workforce requirements met to offer appointments during these times |  |  | 0% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | As above. Also depends on Bromley's and NHSE's projects and initiatives relating to workforce development. | Slower |  |  |  | All practices are offering appointments at these times.
|  | Appointments available at all routine times |  |  | 0% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | As above. | Slower |  |  |  | All practices are offering appointments at these times.
Notes: contractual requirement with compliance to be confirmed by NHSE and CQC inspections. Full compliance assumed.
A4 |  | Extended opening hours
|  | SEL |  |  | 33.33% | 83.33% | 91.67% | 75% | 75% | 83.33% | 83.33% | 91.67% | 91.67% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
|  | Local Urgent Care Centres/Walk-in centres offering extended hours |  |  | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  | Same
|  | Improved access to general practice - big hitter scheme |  |  | 0% | 25% | 50% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | See comment. | Faster
|  | 8 to 8 7/7 |  |  | 0% | 125% | 125% | 25% | 25% | 50% | 50% | 75% | 75% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | The primary care access hub model will need to be adjusted to provide access on sat and Sun afternoons and evenings. This will then need to be piloted, evaluated and the model adjusted. It will also rely on NHS111 referring into the hubs as much as possible to keep utilisation high at weekends, and for referrer, provider and patient behaviour to be embedded for a time. | Same |  |  |  | Opening hours are 8-8, 7/7 | Possibly, in evaluating the impact on hub utilisation when we pilot 8-8 at the weekends.
Notes: Alliance developing a proposal for extended hours for under 18s, 8 to 8 case for change paper shared with Alliance. Approach to access is based upon population segmentation trgeting specific groups. Re-considering Alliance proposal for longer appointments for LTC patients. Good uptake of extended hours, 10,000 additional appts over winter, PMS Plus uptake of extended reception and nursing in 50% of practices.
A5 |  | Same day access
|  | SEL |  |  | 5% | 25% | 30% | 40% | 40% | 90% | 90% | 95% | 95% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
|  | As A4 above, and: | As A4 above, and: | As A4 above, and:
|  | Reablement big hitter encompassing rapid response and supported discharge |  |  | 25% | 25% | 50% | 75% | 75% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | Complete | Same
|  | Telephone triage - practice |  |  | 0% | 50% | 50% | 75% | 75% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | Complete | Same
|  | Telephone triage - Federation/Alliance |  |  | 0% | 0% | 0% | 0% | 0% | 50% | 50% | 75% | 75% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | See comments on row 54. | Slower |  |  |  | Triage system in place at federation level and being well utilised for efficiency and patient satisfaction.
|  | Access to specialist advice and specialist response clinic (U&EC intervention) |  |  | 0% | 25% | 25% | 25% | 25% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | Complete | Same
|  | Same day diagnostics (planned Care intervention) |  |  | 0% | 25% | 25% | 25% | 25% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | Complete | Same
Notes: Reablement is under review in 2015/16 with a view to respecifying; current offering a mix of short term rapid access and long-term intensive packages, complementing traditional service. To clarify telephone triage coverage by individual practice and at scale plans. MAU offers same day access and diagnostics currently, supporting the principle of a one stop shop for unexplained symptoms as per planned care intervention. Primary Care offer to deliver diagnostics in a community setting - possibly community diagnostic hubs.
A6 |  | Urgent and Emergency Care
|  | SEL |  |  | 8.333% | 12.5% | 43.75% | 50% | 50% | 75% | 75% | 75% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
|  | All practice personnel trained to identify emergencies |  |  | 0% | 0% | 50% | 50% | 50% | 50% | 50% | 50% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | Unsure about these. Surely these are in place already?! | Faster
|  | Processes in place to ensure emergencies are appropriately dealt with |  |  | 0% | 0% | 50% | 50% | 50% | 50% | 50% | 50% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | As above. | Faster
|  | Also see reablement above encompassing rapid response |  |  | 25% | 25% | 50% | 75% | 75% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | Complete
|  | Also see access to specialist advice and specialist response clinic (U&EC intervention) |  |  |  | 25% | 25% | 25% | 25% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | Complete
Notes: CQC inspections should confirm compliance. Local CEPN will be commissioned to ensure that staff are trained and processes in place. Implementing workstreams 1 & 2 of the Emergency Pathway whole system review; monitoring & influencing KCH 4 hour recovery plan; developing and delivering local OOH strategy; implementation of MH liaison. Community Escalation Plan deliverables include discharge bureau, revised complex disharge pathways, revised resilience plans; winter schemes and disharge to assess process specified.
A7 |  | Continuity of Care
|  | SEL |  |  | 37.86% | 46.43% | 53.57% | 57.14% | 71.43% | 92.86% | 92.86% | 96.43% | 96.43% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
|  | All patients given a named GP as main contact (over 75s and risk stratified patients currently asper the DES from 2015/16) |  |  | 15% | 50% | 50% | 75% | 75% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | Complete | Same
|  | Practice able to give flexible appointment lengths - links to offer/contract with Alliances/Federations |  |  | 0% | 0% | 0% | 0% | 50% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | I don't think we have this in place. Some practices offered this as part of winter resilience last year, but it is not adopted generally. | Slower
|  | Assigned life clinician/nurse in final year of life |  |  | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | Complete | Same
|  | Coordinate my care plans for patients identified as in final year of life |  |  | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | Complete | Same
|  | Able to share medical records |  |  | 25% | 25% | 25% | 25% | 25% | 50% | 50% | 75% | 75% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | We will require sign up to an Integrated Care Record by all Bromley providers and then can commence roll out of the ICR in full. | Same
|  | See reablement above |  |  | 25% | 25% | 50% | 50% | 75% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | Complete | Same
|  | Multi-disciplinary Teams |  |  | 0% | 25% | 50% | 50% | 75% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | Complete | Same
Notes: 100% of Bromley practices allocated to one of six integrated community teams. MDT pilot and risk stratification pathway to community matron for case management. GP and community data sharing protocols and EMIS web shared records for diabetes patients for example. 24 hour care coordination end of life with highest CNC record utilisation in London. 25/25 PMS practices incentivised to have EOL registers. Remaining practices not incentivised but working with to encourage engagement in EOL pathway and will have ggreater influence thorough co-commissioning. 11 GSF accredited care homes and integrated personal plan (IPP) implemented in 22 nursing homes
Proactive Care
P1 |  | Co-Design
|  | SEL |  |  | 4.167% | 75% | 75% | 79.17% | 79.17% | 91.67% | 91.67% | 91.67% | 95.83% | 95.83% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
|  | Local strategy and annual plan for user and stakeholder engagement activities including hard to reach groups and communities |  |  | 0% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | Complete | Same
|  | Borough-wide representative PPV group established and recorded engagement activities taking place |  |  | 0% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | Complete | Same
|  | Active Patient Participation at individual practices/LCNs |  |  | 25% | 50% | 50% | 75% | 75% | 75% | 75% | 75% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | Not all practices have PPGs but we are working on this over the remainder of this year. | Slower
|  | Individual practices inviting and recording comments about services and actively responding |  |  | 0% | 50% | 50% | 50% | 50% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | Complete | Same
|  | Local communities and stakeholders actively and routinely involved in priority setting and service redesign and their contributions recorded |  |  | 0% | 50% | 50% | 50% | 50% | 75% | 75% | 75% | 75% | 75% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | This is an ongoing part of business as usual so I am not sure how the completion date has been set?
|  | Variety of channels for communicating with and receiving/recording feedback from service users established |  |  | 0% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | Complete | Same
Notes: Bromley transformation programme extensive stakeholder involvement. Community Links commissioned to work with CYP and BME groups; specific engagement with hard to reach groups, e.g.Somali community; Three Bromley PAG events ytd to infomr and influence plans. All workstreams have patient involvement. PAG, Healthwatch & vol sector involved in developing OOH strategy.
P2 |  | Developing assets and resources for improving health and wellbeing
|  | SEL |  |  | 25% | 31.25% | 37.5% | 43.75% | 43.75% | 59.38% | 59.38% | 87.5% | 87.5% | 90.62% | 90.62% | 90.62% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
|  | Joint Market Position statement/commissioning intentions developed (LA/CCG - with key voluntary sector partners) |  |  | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | Complete | Same
|  | Local asset map developed with key partners and stakeholders and in place |  |  | 0% | 0% | 0% | 50% | 50% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | Complete | Same
|  | Social Prescribing scheme in place |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | This will be in place from Q3 of this year as it is part of our transofrmational ICN roll out and will include recruiting social prescribers. | Faster
|  | Developing role of wider primary care team and using more effectively e.g. community pharmacy |  |  | 0% | 0% | 50% | 50% | 50% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | Complete | Same
|  | Local community health and wellbeing champions identified and developed |  |  |  | 25% | 25% | 25% | 25% | 25% | 25% | 25% | 25% | 25% | 25% | 25% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | Unsure about this one but happy to discuss.
|  | Care coordinators/patient liaison established across LCNs |  |  | 75% | 75% | 75% | 75% | 75% | 75% | 75% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | The PLO scheme did this but was incomplete, whereas ICN roll out will see the recruitment of care coordinators for every scheme. | Slower
|  | Primary prevention and public health programmes (obesity, alcohol and smoking) |  |  | 0% | 50% | 50% | 50% | 50% | 75% | 75% | 75% | 75% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | This might be considerably slower if the local authority remove a lot of funding from Public Health. This is therefore contingent on an adequate Public Health offer. | Slower
|  | Federation to define the services to be offered and to build on existing provision - links to offer/contract with Alliances/Federations |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | This is integral to ICN delivery, and the Alliance have and will be central to provision | Faster
Notes: BCF scheme led by LA (public health) encompassing health & wellbeing assets. Considering Community Links to develop asset map. Many community sector support services, working to align with LCNs and wrap around GP practices. BMI pilot project targeting obese patients with health risks and offering structured lifestyle interventions. CCG patient liaison officers in GP practice scheme trained with coordinator 'competencies. Exploring potential for community pharmacy role in supporting LTCs and public health programmes. PH health champions project under review in the light of budgetary pressures within LA. Tier 2 weight management and smoking cessation service. Review of PH budgets and cut in PH grant make it difficult to plan beyond this FY at this stage.
P3 |  | Personal conversations focussed on an individual's health goals
|  | SEL |  |  | 25% | 25% | 33.33% | 41.67% | 66.67% | 75% | 75% | 83.33% | 91.67% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
|  | Risk stratification tool in place and DES to have goal setting conversations with 2% of population |  |  | 50% | 50% | 50% | 50% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
|  | Training for GP practice staff in motivational skills and health coaching |  |  | 25% | 25% | 50% | 75% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
|  | Training for others within the LCN (including vol sector and health champions) in motivational skills and health coaching |  |  | 0% | 0% | 0% | 0% | 0% | 25% | 25% | 50% | 75% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
Notes: new risk tool developed and implemented with training in 14/15. Regular motivational skills training provided to GP practice staff. Self-management programme for LTC patients encompasses personal goal setting. Obesity project includes goal setting for at risk patients identified.
P4 |  | Health and wellbeing liaison and information
|  | SEL |  |  | 18.75% | 25% | 25% | 37.5% | 37.5% | 50% | 50% | 50% | 56.25% | 56.25% | 56.25% | 56.25% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
|  | Asset mapping advertised and accessible (hard copy and on-line) |  |  | 0% | 0% | 0% | 50% | 50% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | Complete | Same
|  | Active programmes in the community (i.e. schools, workplaces and other community settings) |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | Ongoing - will be part of business as usual. | Same
|  | Care coordinators/navigators/liaison trained in how to access resource |  |  | 75% | 75% | 75% | 75% | 75% | 75% | 75% | 75% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | Part of ICN implementation. | Faster
|  | Health champions, carers and service users able to use resources |  |  | 0% | 25% | 25% | 25% | 25% | 25% | 25% | 25% | 25% | 25% | 25% | 25% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | Ongoing - will be part of business as usual. | Same
Notes: Many community assets registered on My Life (LA community services website) proposed to incorporate health services and enable access within GP practices. PH run programmes linked to school nursing and health visitors but under review in the light of LA budgetary constraints and reduction in the PH grant. Patient/carer education programme includes local resource folder and how to access support etc. See notes above re LA (public health) led BCF scheme
P5 |  | Patients not currently accessing primary care services
|  | SEL |  |  | 6.25% | 17.5% | 17.5% | 36.25% | 36.25% | 56.25% | 56.25% | 62.5% | 68.75% | 93.75% | 93.75% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
|  | Enhanced Call & recall for screening and vaccinations programme targeting hard to reach groups - consider link to Alliance/Federation offer/contract |  |  | 0% | 0% | 0% | 50% | 50% | 50% | 50% | 50% | 50% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | This will be delayed if the PMS contract implementation is delayed further. | Same
|  | Support to vulnerable people in the community (care homes, extra care housing and domiciliary care) |  |  | 0% | 0% | 0% | 25% | 25% | 50% | 50% | 75% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | This is dependant on the wider work of the CCG on care homes, ECH and dom care. This is being looked at and a care homes working group is due to be set up internally, chaired by the CO as this is a Bromley priority. | Same
|  | Working with local third sector, local authority and community groups to identify people not accessing services and co-design and implement ways of reaching such people |  |  | 0% | 20% | 20% | 20% | 20% | 50% | 50% | 50% | 50% | 75% | 75% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | Ongoing. | Same
|  | Training for carers and others to recognise symptoms and engage with primary care services |  |  | 25% | 50% | 50% | 50% | 50% | 75% | 75% | 75% | 75% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | To be delivered as part of the joint Bromley Carers Strategy. Carers Commissioner (band 7) now in post to deliver this. | Same
Notes: LA initial response team provides front line support. CCG focus on screening for and diagnosing dementia in care homes and at home. Also AF screening. Commissioned 'Live Well' services delivering health risk assessments to hard to reach groups; future funding under consideration. Gap analysis of care provision and audit of current support arrangements commenced. Established training for care home staff, domiciliary and unpaid carers in diagnosing UTIs. Additional resources set aside to provide additional support and health training into care homes and extra care housing, subject to finalisation of the OOH strategy.
Coordinated Care
C1 |  | Case finding and review
|  | SEL |  |  | 29.17% | 35.83% | 40% | 48.33% | 48.33% | 75% | 75% | 87.5% | 87.5% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
|  | Risk Stratification tool in place, evaluated and further developed |  |  | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | Complete | Same
|  | Active care registers in place |  |  | 50% | 50% | 50% | 75% | 75% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | Complete | Same
|  | Extending care registers beyond 2% of the adult population - consider as part of offer/contract with Federation/Alliance |  |  | 0% | 0% | 0% | 0% | 0% | 50% | 50% | 75% | 75% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | To be delivered as part of ICNs and integrated case management specification. However, roll out will be gradual, especially without the incentive of the new PMS contract which has been delayed. | Same
|  | Working with local third sector, local authority and community groups to identify people at risk |  |  | 0% | 20% | 20% | 20% | 20% | 50% | 50% | 75% | 75% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | This will be part of Icns and the integrates case management model from October. | Faster
|  | Identify people at risk of developing LTCs (see P5) |  |  | 0% | 20% | 20% | 20% | 20% | 50% | 50% | 75% | 75% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | Part of the proactive care pathway within ICNs. | Faster
|  | Hospital in-reach linked to reablement and end of life services |  |  | 25% | 25% | 50% | 75% | 75% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | Complete | Same
Notes: AF screening, BMI screening for diabetes risk. Dementia screening and review, includes in-reach to care homes and extra care housing. End of Life service case finding people in final year of life. Reablement being reviewed.
C2 |  | Named professional
|  | SEL |  |  | 40% | 44% | 49% | 54% | 64% | 75% | 80% | 90% | 90% | 95% | 95% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
|  | Named professional assigned to individuals on care register |  |  | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | Complete | Same
|  | Care coordinators/patient liaison established across (see P2) |  |  | 75% | 75% | 75% | 75% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | See previous comments on care coordinators - will be part of ICNs. | Same
|  | Named professional assigned to others at risk (see C1) |  |  | 0% | 20% | 20% | 20% | 20% | 50% | 50% | 50% | 50% | 75% | 75% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | Not certain of the background to this relating to the date set of Q3 2017 | Same
|  | Training for GP practice staff in motivational skills and health coaching (see P3) |  |  | 25% | 25% | 50% | 75% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | I don't remember this happening so again, am unsure. | Same
|  | Training for others within the LCN (including vol sector and health champions) in motivational skills and health coaching (see P3) |  |  | 0% | 0% | 0% | 0% | 0% | 25% | 50% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | This has already begun and will be part of ICN roll out. | Faster
Notes:
C3 |  | Care Planning
|  | SEL |  |  | 34.58% | 39.92% | 44.5% | 51.17% | 56.17% | 75% | 77.5% | 88.75% | 88.75% | 97.5% | 97.5% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
|  | See C1 above |  |  | 29.17% | 35.83% | 40% | 48.33% | 48.33% | 75% | 75% | 87.5% | 87.5% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  | Same
|  | See C2 above |  |  | 40% | 44% | 49% | 54% | 64% | 75% | 80% | 90% | 90% | 95% | 95% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  | Same
Notes:
C4 |  | Patients supported to manage their health and wellbeing
|  | SEL |  |  | 17.86% | 21.43% | 25% | 39.29% | 46.43% | 64.29% | 64.29% | 67.86% | 67.86% | 85.71% | 85.71% | 85.71% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
|  | Asset Mapping (see P2) |  |  | 0% | 0% | 0% | 50% | 50% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | See previous. | Same
|  | Social Prescribing (see P2) |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | See previous. | Same
|  | H&WB champions (see P2) |  |  | 0% | 25% | 25% | 25% | 25% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | See previous. | Same
|  | Care coordinators (see P2) |  |  | 75% | 75% | 75% | 75% | 75% | 75% | 75% | 75% | 75% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | See previous. | Same
|  | Health Coaching (see P3) |  |  | 25% | 25% | 50% | 75% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | See previous. | Same
|  | Active Programmes in the community (see P4) |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | See previous. | Same
|  | Patient/carer education programmes |  |  | 25% | 25% | 25% | 50% | 75% | 75% | 75% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | This is part of the joint Bromley carers strategy and self-management element of the ICNs. | Slower
Notes: Two year self-management education programme for patients and carers. UTI training for carers. LA led BCF schemes
C5 |  | Multi-disciplinary working
|  | SEL |  |  | 15% | 15% | 15% | 25% | 25% | 50% | 75% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
|  | CBC Big Hitter |  |  | 15% | 15% | 15% | 25% | 25% | 50% | 75% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | ICN implementation to take place from Q3 2016/17. On track at the current time. | Faster
Notes: Integrated care team operating within 1 or 6 localities, targeting identified at-risk patients. Under review with a view to further development

## Greenwich
SEL CBC & Primary Care Delivery Plan |  |  |  |  | Key: |  | Step in progress |  |  |  | Activity begins to be met for some patients
[7 empty] | Step complete |  |  |  | SPG specification delivery date
Predicted pan London delivery date
[6 empty] | 2015 |  |  |  | 2016 |  |  |  | 2017 |  |  |  | 2018 |  |  |  | 2019 |  |  |  | 2020
|  | Greenwich - validated |  |  | Pre-2015 | Q1 April 2015 | Q2 Jul 2015 | Q3 Oct 2015 | Q4 Jan 2016 | Q1 April 2016 | Q2 Jul 2016 | Q3 Oct 2016 | Q4 Jan 2017 | Q1 April 2017 | Q2 Jul 2017 | Q3 Oct 2017 | Q4 Jan 2018 | Q1 April 2018 | Q2 Jul 2018 | Q3 Oct 2018 | Q4 Jan 2019 | Q1 April 2019 | Q2 Jul 2019 | Q3 Oct 2019 | Q4 Jan 2020 | Q1 April 2020 | Q2 Jul 2020 | Q3 Oct 2020 | Q4 Jan 2021 | Dependent activity? | Change from current baseline | Funding required | Funding source | Funding secured | How will we know if it has been delivered (what are our measures?) | Support required from HLP
Spec |  | Examples of supporting activity | Owner | Start | Pre-2015 | Year 1 |  |  |  | Year 2 |  |  |  | Year 3 |  |  |  | Year 4 |  |  |  | Year 5 |  |  |  | Year 6 |  |  |  | Are there activities which must be completed before this activity can be commenced?
| Federations/Alliances | Integrated single system leadership and management |  |  | 7.143% | 7.143% | 50% | 57.14% | 67.86% | 78.57% | 78.57% | 78.57% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
|  | Local Care Networks defined |  |  | 50% | 50% | 50% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | Completed | Same
|  | Leadership & Common Voice (formal/informal leadership development programmes, local learning sets) |  |  | 0% | 0% | 50% | 50% | 50% | 50% | 50% | 50% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | Access to fundng resources to provide on-going development and leadership training - reliant on HEE funding | Same | £50k | HEE & OHSEL | No | Facilitated events, registration required
|  | Access to Expertise (governance, structure development, legal support, business dev. & new models of care) |  |  | 0% | 0% | 50% | 50% | 50% | 50% | 50% | 50% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | OHSEL to advise on commissioned support from providers | Same
|  | Direct Management Support (coaching/mentoring, management/admin staff) |  |  | 0% | 0% | 50% | 50% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | Limited resources from Pioneer Programme - 20 days | Same
|  | Time & Headroom (facilitated events and engagement across the network) |  |  | 0% | 0% | 50% | 50% | 50% | 75% | 75% | 75% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | Protected Learning Time - dependent on resources via HEE SLA | Same | £200k | HEE & OHSEL | No | Facilitated events, registration required
|  | Peer Working & Support (enabling strategies, e.g. workforce, IM&T, Estates and across networks) |  |  | 0% | 0% | 50% | 50% | 50% | 75% | 75% | 75% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | Protected Learning Time - dependent on resources via HEE SLA | Same
|  | LCN leadership team & management structure in place with the 'core' represented/engaged and with clear governance and decision-making arrangements |  |  | 0% | 0% | 50% | 50% | 75% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | In place and under review | Same
Notes: LCNs have been geographically defined but still evolving
|  | Federations/Alliances |  |  | 0% | 55.56% | 55.56% | 55.56% | 94.44% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
|  | All local GP practices have agreed to an Alliance |  |  | 0% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | Completed | Same
|  | The practices are geographically aligned |  |  | 0% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | Completed | Same
|  | The Alliance has a recognised legal identity |  |  | 0% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | Completed | Same
|  | The Alliance is registered with the CQC |  |  | 0% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | In process for Federation as required dependent on contracts | Same
|  | Specification for an enhanced primary care service created and agreed |  |  | 0% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | Completed | Same
|  | Commissioner offer made to Alliance and contract in place following due diligence |  |  | 0% | 0% | 0% | 0% | 50% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | Completed | Same
|  | Alliance leadership, governance & decision-making arrangements in place |  |  | 0% | 0% | 0% | 0% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | Completed | Same
|  | Alliance management structure in place |  |  | 0% | 0% | 0% | 0% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | Completed | Same
|  | 3 to 5 year business plan developed |  |  | 0% | 0% | 0% | 0% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | Not yet started | Same
Notes: Four LLPs established covering all practices. LTC management contract in place. CQC additional registration not required for LTC contract as commissioned as a GP incentive scheme
Accessible Care
A1 | Spec | Patient Choice
|  | SEL |  |  | 0% | 75% | 75% | 89.29% | 92.86% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
|  | Patient able to see particular clinician |  |  | 0% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | GP Contract | Same
|  | Patients able to book up to 4 weeks in advance |  |  | 0% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | GP Contract | Same
|  | Support available for non English speakers |  |  | 0% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | In place | Same
|  | Infrastructure available for accessibility (hearing loops etc.) |  |  | 0% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | In place | Same
|  | Patients able to book at times convenient to them |  |  | 0% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | GP Contract | Same
|  | Improved access to general practice - big hitter scheme |  |  | 0% | 25% | 25% | 50% | 75% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  | Same
|  | Local Urgent Care Centres/Walk-in centres offering alternatives to GP practice |  |  |  | 0% | 0% | 75% | 75% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | Walk in Centres closing end of September 2016 to be replaced by 2 GP access hubs from 1 October 2016 opening 1 - 5 Saturday, 9 - 5 Sunday but will require top up to cover Saturday morning. Urgent Care Centre in place - see A4 | Same | £.5m | CCG | Yes | Contract in place
Notes: 8 to 8 (3 locations) and walk-in pan Greenwich from Sept 2015
A2 |  | Contacting the practice
|  | SEL |  |  | 0% | 38.5% | 43.5% | 53% | 53% | 77.5% | 80% | 87.5% | 90% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
Individual practice level
|  | Telephone booking and triage system available |  |  | 0% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | GP contract | Same
|  | Online booking system available |  |  | 0% | 50% | 50% | 75% | 75% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | GP contract | Same
|  | Online prescription service available |  |  | 0% | 50% | 75% | 75% | 75% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | GP contract | Same
|  | Medical records available online (functionality available) |  |  | 0% | 20% | 20% | 20% | 20% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | GP contract | Same
|  | Process/ IT in place to support email consultations |  |  | 0% | 10% | 10% | 10% | 10% | 25% | 50% | 50% | 75% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  | Same
|  | Access routes (in particular online) advertised to patients |  |  | 0% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | GP contract | Same
Federation level
|  | Able to share medical records |  |  | 0% | 25% | 50% | 75% | 75% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | Completed | Same
|  | Single telephone booking and triage system |  |  | 0% | 10% | 10% | 25% | 25% | 50% | 50% | 75% | 75% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | Bid submitted under ETTF | Same |  | ETTF
|  | Online booking system |  |  | 0% | 10% | 10% | 25% | 25% | 50% | 50% | 75% | 75% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | Included in Access Hub development | Same
|  | Enhanced access options through working as a federation |  |  | 0% | 10% | 10% | 25% | 25% | 50% | 50% | 75% | 75% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | Included in Access Hub development | Same
Notes:
A3 |  | Routine opening hours
|  | SEL |  |  | 0% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
|  | All practices open in routine opening times |  |  | 0% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | GP Contract | Same
|  | Contracts updated to specify appointments to be offered at these times |  |  | 0% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  | Same
|  | Workforce requirements met to offer appointments during these times |  |  | 0% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  | Same
|  | Appointments available at all routine times |  |  | 0% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  | Same
Notes: CQC inspections to confirm
A4 |  | Extended opening hours
|  | SEL |  |  | 0% | 31.25% | 31.25% | 62.5% | 68.75% | 87.5% | 87.5% | 93.75% | 93.75% | 93.75% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
|  | Local Urgent Care Centres/Walk-in centres offering extended hours |  |  |  | 0% | 0% | 75% | 75% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | Urgent Care Centre in place | Same
|  | Improved access to general practice - big hitter scheme |  |  | 0% | 25% | 25% | 50% | 75% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  | Same
|  | 8 to 8 7/7 |  |  | 0% | 0% | 0% | 25% | 25% | 50% | 50% | 75% | 75% | 75% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | Receipt of resources to fund top up as modelled by PWC | Slower | £1.8m | GP Forward View | No | Contract in place with KPIs
|  | Extended opening hours contract |  |  |  | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  | Same
Note: All practices signed up to extended hours
A5 |  | Same day access
|  | SEL |  |  | 20% | 67% | 67% | 67% | 67% | 90% | 90% | 90% | 90% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
As A4 above, and:
|  | Reablement big hitter encompassing rapid response and supported discharge |  |  | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | Home First model of care under development to improve exisitng model | Same
|  | Telephone triage - practice |  |  | 0% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  | Same
|  | Telephone triage - Federation/Alliance |  |  | 0% | 10% | 10% | 10% | 10% | 50% | 50% | 50% | 50% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  | Same
|  | Access to specialist advice and specialist response clinic (U&EC intervention) |  |  | 0% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | Pilot with Connect Care starting Q3 to access consultant support | Same | £20k | CCG | Yes
|  | Same day diagnostics (planned Care intervention) |  |  | 0% | 25% | 25% | 25% | 25% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | Dependent on Commissionng Intentions | Same
Notes: JET under review with a view to moving to 7 day and 8 to 8. Geriatrician of the Day, Paediatrician of the Day, Cardiologist of the Week. Some day diagnostics access.
A6 |  | Urgent and Emergency Care
|  | SEL |  |  | 33.33% | 50% | 75% | 75% | 75% | 75% | 75% | 75% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
|  | All practice personnel trained to identify emergencies |  |  | 0% | 0% | 50% | 50% | 50% | 50% | 50% | 50% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  | Same
|  | Processes in place to ensure emergencies are appropriately dealt with |  |  | 0% | 0% | 50% | 50% | 50% | 50% | 50% | 50% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  | Same
|  | Also see reablement above encompassing rapid response |  |  | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  | Same
|  | Also see access to specialist advice and specialist response clinic (U&EC intervention) |  |  |  | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  | Same
Notes: local CEPNs to ensure that staff are trained and processes in place
A7 |  | Continuity of Care
|  | SEL |  |  | 16.43% | 67.86% | 71.43% | 75% | 78.57% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
|  | All patients given a named GP as main contact (over 75s and risk stratified patients currently asper the DES from 2015/16) |  |  | 15% | 50% | 50% | 50% | 75% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | GP Contract | Same
|  | Practice able to give flexible appointment lengths - links to offer/contract with Alliances/Federations |  |  | 0% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | GP Contract | Same
|  | Assigned life clinician/nurse in final year of life |  |  | 0% | 50% | 50% | 50% | 50% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | In development with Access Hubs | Same
|  | Coordinate my care plans for patients identified as in final year of life |  |  | 0% | 50% | 50% | 50% | 50% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | In place | Same
|  | Able to share medical records |  |  | 0% | 25% | 50% | 75% | 75% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | In place | Same
|  | See reablement above |  |  | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | Connect Care - phased roll out | Same
|  | Multi-disciplinary Teams |  |  | 0% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  | Same
Notes: EOL service procurement underway. MDT eol and complex/vulnerable adults
Proactive Care
P1 |  | Co-Design
|  | SEL |  |  | 0% | 70.83% | 70.83% | 70.83% | 70.83% | 95.83% | 95.83% | 95.83% | 95.83% | 95.83% | 95.83% | 95.83% | 95.83% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
|  | Local strategy and annual plan for user and stakeholder engagement activities including hard to reach groups and communities |  |  | 0% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  | Same
|  | Borough-wide representative PPV group established and recorded engagement activities taking place |  |  | 0% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  | Same
|  | Active Patient Participation at individual practices/LCNs |  |  | 0% | 50% | 50% | 50% | 50% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  | Same
|  | Individual practices inviting and recording comments about services and actively responding |  |  | 0% | 50% | 50% | 50% | 50% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | FFT in place | Same
|  | Local communities and stakeholders actively and routinely involved in priority setting and service redesign and their contributions recorded |  |  | 0% | 50% | 50% | 50% | 50% | 75% | 75% | 75% | 75% | 75% | 75% | 75% | 75% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  | Same
|  | Variety of channels for communicating with and receiving/recording feedback from service users established |  |  | 0% | 75% | 75% | 75% | 75% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  | Same
Notes: Pt. engagement strategy and range of approaches. CCG survey recording
P2 |  | Developing assets and resources for improving health and wellbeing
|  | SEL |  |  | 0% | 34.38% | 34.38% | 34.38% | 34.38% | 68.75% | 68.75% | 68.75% | 68.75% | 90.62% | 90.62% | 90.62% | 90.62% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
|  | Joint Market Position statement/commissioning intentions developed (LA/CCG - with key voluntary sector partners) |  |  | 0% | 0% | 0% | 0% | 0% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  | Same
|  | Local asset map developed with key partners and stakeholders and in place |  |  | 0% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  | Same
|  | Social Prescribing scheme in place |  |  | 0% | 50% | 50% | 50% | 50% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  | Same
|  | Developing role of wider primary care team and using more effectively e.g. community pharmacy |  |  | 0% | 25% | 25% | 25% | 25% | 50% | 50% | 50% | 50% | 75% | 75% | 75% | 75% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  | Same
|  | Local community health and wellbeing champions identified and developed |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  | Same
|  | Care coordinators/patient liaison established across LCNs |  |  | 0% | 50% | 50% | 50% | 50% | 75% | 75% | 75% | 75% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  | Same
|  | Primary prevention and public health programmes (obesity, alcohol and smoking) |  |  | 0% | 50% | 50% | 50% | 50% | 75% | 75% | 75% | 75% | 75% | 75% | 75% | 75% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  | Same
|  | Federation to define the services to be offered and to build on existing provision - links to offer/contract with Alliances/Federations |  |  | 0% | 0% | 0% | 0% | 0% | 50% | 50% | 50% | 50% | 75% | 75% | 75% | 75% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  | Same
Notes: Established joint commissioning executive with LA. Coordinator test and learn pilot underway. Obesity services; staying healthy programme; effective smoking cessation service
P3 |  | Personal conversations focussed on an individual's health goals
|  | SEL |  |  | 33.33% | 58.33% | 58.33% | 58.33% | 58.33% | 83.33% | 83.33% | 83.33% | 83.33% | 91.67% | 91.67% | 91.67% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
|  | Risk stratification tool in place and DES to have goal setting conversations with 2% of population |  |  | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | GP Contract | Same
|  | Training for GP practice staff in motivational skills and health coaching |  |  | 0% | 75% | 75% | 75% | 75% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  | Same
|  | Training for others within the LCN (including vol sector and health champions) in motivational skills and health coaching |  |  | 0% | 0% | 0% | 0% | 0% | 50% | 50% | 50% | 50% | 75% | 75% | 75% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  | Same
Notes: Every practice trained in year of care and contractually required as part of LTC contract
P4 |  | Health and wellbeing liaison and information
|  | SEL |  |  | 0% | 25% | 25% | 31.25% | 50% | 62.5% | 62.5% | 62.5% | 62.5% | 75% | 75% | 81.25% | 93.75% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
|  | Asset mapping advertised and accessible (hard copy and on-line) |  |  | 0% | 50% | 50% | 50% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | Greenwich Community Directory in place | Same
|  | Active programmes in the community (i.e. schools, workplaces and other community settings) |  |  | 0% | 25% | 25% | 25% | 25% | 50% | 50% | 50% | 50% | 75% | 75% | 75% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  | Same
|  | Care coordinators/navigators/liaison trained in how to access resource |  |  | 0% | 25% | 25% | 50% | 75% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  | Same
|  | Health champions, carers and service users able to use resources |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 25% | 25% | 50% | 75% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  | Slower
Notes: Care navigators project underway. Joint H&WB strategy also encompassing work based activities
P5 |  | Patients not currently accessing primary care services
|  | SEL |  |  | 0% | 43.75% | 43.75% | 43.75% | 56.25% | 81.25% | 81.25% | 81.25% | 81.25% | 87.5% | 87.5% | 87.5% | 87.5% | 93.75% | 93.75% | 93.75% | 93.75% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
|  | Enhanced Call & recall for screening and vaccinations programme targeting hard to reach groups - consider link to Alliance/Federation offer/contract |  |  | 0% | 50% | 50% | 50% | 50% | 75% | 75% | 75% | 75% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  | Same
|  | Support to vulnerable people in the community (care homes, extra care housing and domiciliary care) |  |  | 0% | 50% | 50% | 50% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  | Same
|  | Working with local third sector, local authority and community groups to identify people not accessing services and co-design and implement ways of reaching such people |  |  | 0% | 50% | 50% | 50% | 50% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  | Same
|  | Training for carers and others to recognise symptoms and engage with primary care services |  |  | 0% | 25% | 25% | 25% | 25% | 50% | 50% | 50% | 50% | 50% | 50% | 50% | 50% | 75% | 75% | 75% | 75% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  | Same
Notes: Survey of unregistered residents and action plan in place with LA. LTC contract targeting call and recall and screening, immunisations, DNA. Care home support team and part of BCF. Networks in collaboration with citizens for people with MH problems BCF scheme for carer support and training/education
Coordinated Care
C1 |  | Case finding and review
|  | SEL |  |  | 37.5% | 45.83% | 45.83% | 45.83% | 70.83% | 95% | 95% | 79.17% | 95% | 91.67% | 91.67% | 95.83% | 95.83% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
|  | Risk Stratification tool in place, evaluated and further developed |  |  | 50% | 50% | 50% | 50% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | In place | Same
|  | Active care registers in place |  |  | 50% | 50% | 50% | 50% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  | Same
|  | Extending care registers beyond 2% of the adult population - consider as part of offer/contract with Federation/Alliance |  |  | 0% | 0% | 0% | 0% | 0% |  |  | 0% |  | 50% | 50% | 75% | 75% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  | Same
|  | Working with local third sector, local authority and community groups to identify people at risk |  |  | 50% | 50% | 50% | 50% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  | Same
|  | Identify people at risk of developing LTCs (see P5) |  |  | 0% | 50% | 50% | 50% | 50% | 75% | 75% | 75% | 75% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | LTC Prevalence contract in place | Same | £200k | CCG | Yes
|  | Hospital in-reach linked to reablement and end of life services |  |  | 75% | 75% | 75% | 75% | 75% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  | Same
Notes: Greenwich integrated MDT scheme targeting at risk and vulnerable adults. Reablement team fully established. Considering Plans for extending risk registers. BCF scheme for working with third sector and community groups
C2 |  | Named professional
|  | SEL |  |  | 25% | 55% | 55% | 55% | 65% | 85% | 85% | 85% | 85% | 95% | 95% | 95% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
|  | Named professional assigned to individuals on care register |  |  | 50% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  | Same
|  | Care coordinators/patient liaison established across (see P2) |  |  |  | 50% | 50% | 50% | 50% | 75% | 75% | 75% | 75% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  | Same
|  | Named professional assigned to others at risk (see C1) |  |  | 50% | 50% | 50% | 50% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  | Same
|  | Training for GP practice staff in motivational skills and health coaching (see P3) |  |  | 0% | 75% | 75% | 75% | 75% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | Protected Learning Time | Same
|  | Training for others within the LCN (including vol sector and health champions) in motivational skills and health coaching (see P3) |  |  | 0% | 0% | 0% | 0% | 0% | 50% | 50% | 50% | 50% | 75% | 75% | 75% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | Protected Learning Time | Same
Notes: to clarify training
C3 |  | Care Planning
|  | SEL |  |  | 31.25% | 50.42% | 50.42% | 50.42% | 67.92% | 90% | 90% | 82.08% | 90% | 93.33% | 93.33% | 95.42% | 97.92% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
|  | See C1 above |  |  | 37.5% | 45.83% | 45.83% | 45.83% | 70.83% | 95% | 95% | 79.17% | 95% | 91.67% | 91.67% | 95.83% | 95.83% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  | Same
|  | See C2 above |  |  | 25% | 55% | 55% | 55% | 65% | 85% | 85% | 85% | 85% | 95% | 95% | 95% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  | Same
Notes:
C4 |  | Patients supported to manage their health and wellbeing
|  | SEL |  |  | 0% | 46.43% | 46.43% | 46.43% | 46.43% | 64.29% | 64.29% | 64.29% | 64.29% | 85.71% | 85.71% | 85.71% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
|  | Asset Mapping (see P2) |  |  | 0% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | In place | Same
|  | Social Prescribing (see P2) |  |  | 0% | 50% | 50% | 50% | 50% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | In place | Same
|  | H&WB champions (see P2) |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | Bid submitted to Health Innovation for Health Coaches - outcome September 2016 | Same
|  | Care coordinators (see P2) |  |  | 0% | 50% | 50% | 50% | 50% | 75% | 75% | 75% | 75% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  | Same
|  | Health Coaching (see P3) |  |  | 0% | 75% | 75% | 75% | 75% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  | Same
|  | Active Programmes in the community (see P4) |  |  | 0% | 25% | 25% | 25% | 25% | 50% | 50% | 50% | 50% | 75% | 75% | 75% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  | Same
|  | Patient/carer education programmes |  |  | 0% | 25% | 25% | 25% | 25% | 25% | 25% | 25% | 25% | 25% | 25% | 25% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | In place | Same
Notes: LTC contract requires each network to have local self-management support for LTCs
C5 |  | Multi-disciplinary working
|  | SEL |  |  | 50% | 50% | 50% | 50% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
|  | CBC Big Hitter |  |  | 50% | 50% | 50% | 50% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | Home First model of care under development | Same
Notes: Greenwich integrated MDT scheme targeting at risk and vulnerable adults in 50% of population - pioneer site) In addition, MDT working for eol at 100%. Looking at universal coverage for pioneer depending on outcome of evaluation.

## Lambeth
[5 empty] | Key: |  | Step in progress |  |  |  | Activity begins to be met for some patients
SEL CBC & Primary Care Delivery Plan | [6 empty] | Step complete |  |  |  | SPG specification delivery date
Predicted pan London delivery date
[6 empty] | 2015 |  |  |  | 2016 |  |  |  | 2017 |  |  |  | 2018 |  |  |  | 2019 |  |  |  | 2020
|  | Lambeth - validated |  |  | Pre-2015 | Q1 April 2015 | Q2 Jul 2015 | Q3 Oct 2015 | Q4 Jan 2016 | Q1 April 2016 | Q2 Jul 2016 | Q3 Oct 2016 | Q4 Jan 2017 | Q1 April 2017 | Q2 Jul 2017 | Q3 Oct 2017 | Q4 Jan 2018 | Q1 April 2018 | Q2 Jul 2018 | Q3 Oct 2018 | Q4 Jan 2019 | Q1 April 2019 | Q2 Jul 2019 | Q3 Oct 2019 | Q4 Jan 2020 | Q1 April 2020 | Q2 Jul 2020 | Q3 Oct 2020 | Q4 Jan 2021 | Dependent activity? | Change from current baseline | Funding required | Funding source | Funding secured | How will we know if it has been delivered (what are our measures?) | Support required from HLP
Spec |  | Examples of supporting activity | Owner | Start | Pre-2015 | Year 1 |  |  |  | Year 2 |  |  |  | Year 3 |  |  |  | Year 4 |  |  |  | Year 5 |  |  |  | Year 6 |  |  |  | Are there activities which must be completed before this activity can be commenced?
| Federations/Alliances | Integrated single system leadership and management |  |  | 7.143% | 57.14% | 57.14% | 60.71% | 92.86% | 92.86% | 92.86% | 92.86% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
|  | Local Care Networks defined |  |  | 0% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  | Same |  |  |  | In place
|  | Leadership & Common Voice (formal/informal leadership development programmes, local learning sets) |  |  | 50% | 50% | 50% | 75% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  | Same |  |  |  | In place
|  | Access to Expertise (governance, structure development, legal support, business dev. & new models of care) |  |  | 0% | 50% | 50% | 50% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  | Same |  |  |  | In place
|  | Direct Management Support (coaching/mentoring, management/admin staff) |  |  | 0% | 50% | 50% | 50% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  | Same |  |  |  | In place
|  | Time & Headroom (facilitated events and engagement across the network) |  |  | 0% | 50% | 50% | 50% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  | Same |  |  |  | In place
|  | Peer Working & Support (enabling strategies, e.g. workforce, IM&T, Estates and across networks) |  |  | 0% | 50% | 50% | 50% | 50% | 50% | 50% | 50% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  | Same |  | ETTF | No | General Practices are sharing resources and work effectively together to achieve economies of scale and efficiencies that supports long term viability of primary care
|  | LCN leadership team & management structure in place with the 'core' represented/engaged and with clear governance and decision-making arrangements |  |  | 0% | 50% | 50% | 50% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  | Same |  |  |  | In place
Notes: Three LCNs aligned to Federations. Emerging GP leadership development programme; OD and LCN development sessions, leading to a 'strawman' and pilots testing and demonstrating new ways of working. Facilitated events and engagement is planned to continue.
|  | Federations/Alliances |  |  | 38.89% | 41.67% | 55.56% | 72.22% | 83.33% | 86.11% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
|  | All local GP practices have agreed to an Alliance |  |  | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  | Same
|  | The practices are geographically aligned |  |  | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  | Same
|  | The Alliance has a recognised legal identity |  |  | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  | Same
|  | The Alliance is registered with the CQC |  |  | 0% | 0% | 0% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  | Same
|  | Specification for an enhanced primary care service created and agreed |  |  | 50% | 75% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  | Same
|  | Commissioner offer made to Alliance and contract in place following due diligence |  |  | 0% | 0% | 0% | 0% | 50% | 75% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | Contract to be signed | Slower | Waiting notification of Access funding from NHSE |  | Pending
|  | Alliance leadership, governance & decision-making arrangements in place |  |  | 0% | 0% | 50% | 75% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | Note: 2 of the federations are expected to merge later in 2016/17 | Same
|  | Alliance management structure in place |  |  | 0% | 0% | 50% | 75% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  | Same
|  | 3 to 5 year business plan developed |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | Links to due diligence work and extended contract negotiations | Slower
Notes: Three federations (LLPs) Primary Care Programme Board, strategy and associated workplan. GP Delivery Framework for enhanced primary care in 15/16. Developing contract for 16/17. PM challenge fund supporting enhanced access and services. Re commissioning offer - further discussion through CBC delivery, pursuant to co-commissioning
Accessible Care
A1 | Spec | Patient Choice
|  | SEL |  |  | 14.29% | 89.29% | 89.29% | 92.86% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
|  | Patient able to see particular clinician |  |  | 0% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  | Same
|  | Patients able to book up to 4 weeks in advance |  |  | 0% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  | Same
|  | Support available for non English speakers |  |  | 0% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  | Same
|  | Infrastructure available for accessibility (hearing loops etc.) |  |  | 0% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  | Same
|  | Patients able to book at times convenient to them |  |  | 0% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  | Same
|  | Improved access to general practice - big hitter scheme |  |  | 0% | 25% | 25% | 50% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  | Same
|  | Local Urgent Care Centres/Walk-in centres offering alternatives to GP practice |  |  | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  | Same
Notes: PMCF enhanced access hubs initiative the Lambeth 'big hitter' scheme
A2 |  | Contacting the practice
|  | SEL |  |  | 10% | 65% | 70% | 80% | 90% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
Individual practice level
|  | Telephone booking and triage system available |  |  | 0% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  | Same
|  | Online booking system available |  |  | 0% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  | Same
|  | Online prescription service available |  |  | 0% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  | Same
|  | Medical records available online (functionality available) |  |  | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  | Same
|  | Process/ IT in place to support email consultations |  |  | 0% | 0% | 0% | 0% | 0% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  | Same |  |  |  | Verify with individual GP practices
|  | Access routes (in particular online) advertised to patients |  |  | 0% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  | Same
Federation level
|  | Able to share medical records |  |  | 0% | 25% | 75% | 75% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  | Same
|  | Single telephone booking and triage system |  |  | 0% | 50% | 50% | 75% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  | Same
|  | Online booking system |  |  | 0% | 50% | 50% | 75% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  | Same
|  | Enhanced access options through working as a federation |  |  | 0% | 25% | 25% | 75% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  | Same
Notes: Individual practice positions - contractual compliance . All practices have EMIS web and shared record via hubs from July. Federation delivery links to PMCF.
A3 |  | Routine opening hours
|  | SEL |  |  | 0% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
|  | All practices open in routine opening times |  |  | 0% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  | Same
|  | Contracts updated to specify appointments to be offered at these times |  |  | 0% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  | Same
|  | Workforce requirements met to offer appointments during these times |  |  | 0% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  | Same
|  | Appointments available at all routine times |  |  | 0% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  | Same
Notes: linked workforce demand and capacity baseline audit underway to test and demonstrate on-going improvement
A4 |  | Extended opening hours
|  | SEL |  |  | 33.33% | 50% | 50% | 83.33% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
|  | Local Urgent Care Centres/Walk-in centres offering extended hours |  |  | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  | Same
|  | Improved access to general practice - big hitter scheme |  |  | 0% | 25% | 25% | 75% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  | Same
|  | 8 to 8 7/7 |  |  | 0% | 25% | 25% | 75% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | Opening times Monday to Friday 8-8, and weekend at 10-6 | Same | Linked to NHSE funding as weekend is not 8-8 |  | Pending
Notes: PMCF access hubs
A5 |  | Same day access
|  | SEL |  |  | 0% | 65% | 70% | 75% | 80% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
As A4 above, and:
|  | Reablement big hitter encompassing rapid response and supported discharge |  |  | 0% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  | Same
|  | Telephone triage - practice |  |  | 0% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  | Same
|  | Telephone triage - Federation/Alliance |  |  | 0% | 25% | 50% | 75% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  | Same
|  | Access to specialist advice and specialist response clinic (U&EC intervention) |  |  | 0% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  | Same
|  | Same day diagnostics (planned Care intervention) |  |  | 0% | 0% | 0% | 0% | 0% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | To confirm with Jen | Same
Notes: PMCF creating core capacity in GP practices. Review of direct access diagnostics underway, linked to planned care and PMCF. 'Same day Hot' clinics and geriatrician of the day commissioned
A6 |  | Urgent and Emergency Care
|  | SEL |  |  | 0% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
|  | All practice personnel trained to identify emergencies |  |  | 0% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  | Same
|  | Processes in place to ensure emergencies are appropriately dealt with |  |  | 0% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  | Same
|  | Also see reablement above encompassing rapid response |  |  |  | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  | Same
|  | Also see access to specialist advice and specialist response clinic (U&EC intervention) |  |  |  | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  | Same
Notes: CQC inspections should confirm compliance
A7 |  | Continuity of Care
|  | SEL |  |  | 16.43% | 46.43% | 50% | 53.57% | 67.86% | 71.43% | 71.43% | 71.43% | 71.43% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
|  | All patients given a named GP as main contact (over 75s and risk stratified patients currently asper the DES from 2015/16) |  |  | 15% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  | Same
|  | Practice able to give flexible appointment lengths - links to offer/contract with Alliances/Federations |  |  | 0% | 0% | 0% | 0% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  | Same
|  | Assigned end life clinician/nurse in final year of life |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | Focus has been on end of life care. | Slower |  |  |  | Discusing as part of planning for 2017/18.
|  | Coordinate my care plans for patients identified as in final year of life |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | Focus has been on end of life care. | Slower |  |  |  | Discusing as part of planning for 2017/18.
|  | Able to share medical records |  |  | 0% | 25% | 50% | 75% | 75% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  | Same
|  | See reablement above |  |  | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  | Same
|  | Multi-disciplinary Teams |  |  | 0% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  | Same
Notes: through PMCF commissioning appts lengths appropriate to patient need. MDTs per locality established.
Proactive Care
P1 |  | Co-Design
|  | SEL |  |  | 0% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
|  | Local strategy and annual plan for user and stakeholder engagement activities including hard to reach groups and communities |  |  | 0% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  | Same
|  | Borough-wide representative PPV group established and recorded engagement activities taking place |  |  | 0% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  | Same
|  | Active Patient Participation at individual practices/LCNs |  |  | 0% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  | Same
|  | Individual practices inviting and recording comments about services and actively responding |  |  | 0% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  | Same
|  | Local communities and stakeholders actively and routinely involved in priority setting and service redesign and their contributions recorded |  |  | 0% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  | Same
|  | Variety of channels for communicating with and receiving/recording feedback from service users established |  |  | 0% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  | Same
Notes: going forward, developing community hub to be patient voice through co-production
P2 |  | Developing assets and resources for improving health and wellbeing
|  | SEL |  |  | 25% | 75% | 75% | 78.12% | 78.12% | 90.62% | 90.62% | 93.75% | 96.88% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
|  | Joint Market Position statement/commissioning intentions developed (LA/CCG - with key voluntary sector partners) |  |  | 0% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | An ongoing piece of work | Same |  |  |  | An annual process which we are in the midst of doing for 2017/18
|  | Local asset map developed with key partners and stakeholders and in place |  |  | 0% | 50% | 50% | 75% | 75% | 75% | 75% | 75% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | Some asset mapping. Linked to the maturity of Local Care Networks | Slower
|  | Social Prescribing scheme in place |  |  | 0% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  | Same
|  | Developing role of wider primary care team and using more effectively e.g. community pharmacy |  |  | 0% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  | Same
|  | Local community health and wellbeing champions identified and developed |  |  | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  | Same
|  | Care coordinators/patient liaison established across LCNs |  |  | 0% | 50% | 50% | 50% | 50% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  | Same
|  | Primary prevention and public health programmes (obesity, alcohol and smoking) |  |  | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | A challenge, as dependency on a now reduced public health funding and deconstruction of teams | Slower |  | Public Health | No
|  | Federation to define the services to be offered and to build on existing provision - links to offer/contract with Alliances/Federations |  |  | 0% | 0% | 0% | 0% | 0% | 50% | 50% | 75% | 75% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | Yes, on investment | Same |  | GP delivery framework funding
Notes: Joint integrated commissioning intentions. Developing navigator role. Safe and Independent Living via Age UK. Asset Mapping in one LCN commenced. Health Living Pharmacy initiative focused on smoking, alcohol and obesity and health checks. Champions in place through CCG - 94 trained and working within pharmacies. Phase 3 of GP delivery framework re federations providing primary prevention
P3 |  | Personal conversations focussed on an individual's health goals
|  | SEL |  |  | 33.33% | 66.67% | 66.67% | 66.67% | 83.33% | 83.33% | 83.33% | 83.33% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
|  | Risk stratification tool in place and DES to have goal setting conversations with 2% of population |  |  | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | Through Local Care Networks | Same
|  | Training for GP practice staff in motivational skills and health coaching |  |  | 0% | 50% | 50% | 50% | 75% | 75% | 75% | 75% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | Federations directly funded through HESL | Slower
|  | Training for others within the LCN (including vol sector and health champions) in motivational skills and health coaching |  |  | 0% | 50% | 50% | 50% | 75% | 75% | 75% | 75% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | Federations directly funded through HESL | Slower
Notes: Patient education commissioned via CEPN. Primary Care navigators health coaching operating out of 12 practices with intention to roll-out subject to evaluation
P4 |  | Health and wellbeing liaison and information
|  | SEL |  |  | 12.5% | 43.75% | 50% | 56.25% | 75% | 87.5% | 93.75% | 93.75% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
|  | Asset mapping advertised and accessible (hard copy and on-line) |  |  | 0% | 50% | 50% | 50% | 50% | 50% | 75% | 75% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | Some already in place | Slower
|  | Active programmes in the community (i.e. schools, workplaces and other community settings) |  |  | 0% | 50% | 50% | 50% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  | Same
|  | Care coordinators/navigators/liaison trained in how to access resource |  |  | 0% | 25% | 50% | 50% | 50% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  | Same
|  | Health champions, carers and service users able to use resources |  |  | 50% | 50% | 50% | 75% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  | Same |  | Federations
Notes: health living champions. Lambeth early action partnership - CCG, LA, schools. CYP health partnership (asthma and epilepsy). Service users and carers factored into PC Ed strategy
P5 |  | Patients not currently accessing primary care services
|  | SEL |  |  | 0% | 12.5% | 12.5% | 50% | 93.75% | 93.75% | 93.75% | 93.75% | 93.75% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
|  | Enhanced Call & recall for screening and vaccinations programme targeting hard to reach groups - consider link to Alliance/Federation offer/contract |  |  | 0% | 0% | 0% | 50% | 75% | 75% | 75% | 75% | 75% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | Helped with reducing variation and inequalities, and will further build in enhanced call and recall screening. | Slower
|  | Support to vulnerable people in the community (care homes, extra care housing and domiciliary care) |  |  | 0% | 50% | 50% | 50% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  | Same
|  | Working with local third sector, local authority and community groups to identify people not accessing services and co-design and implement ways of reaching such people |  |  | 0% | 0% | 0% | 50% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  | Same
|  | Training for carers and others to recognise symptoms and engage with primary care services |  |  | 0% | 0% | 0% | 50% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  | Same
Notes: Poss. Fed offer enhanced call & recall for vulnerable and hard to reach. SLIC packages of care and community MDTs. 'Right for Everyone' initiative with Healthwatch with LD clients helping to shape services to meet their needs. Carer training and support 15/16 quality objective
Coordinated Care
C1 |  | Case finding and review
|  | SEL |  |  | 25% | 58.33% | 58.33% | 66.67% | 75% | 91.67% | 91.67% | 95.83% | 95.83% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
|  | Risk Stratification tool in place, evaluated and further developed |  |  | 0% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  | Same
|  | Active care registers in place |  |  | 0% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | Implemented but not all shared/coordinated | Same
|  | Extending care registers beyond 2% of the adult population - consider as part of offer/contract with Federation/Alliance |  |  | 0% | 0% | 0% | 0% | 0% | 50% | 50% | 75% | 75% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | Development of Local Care Network priorities | Same
|  | Working with local third sector, local authority and community groups to identify people at risk |  |  | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | Dependent on joint working in context of public health budget reductions, council cuts | Same
|  | Identify people at risk of developing LTCs (see P5) |  |  | 0% | 0% | 0% | 50% | 75% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  | Same
|  | Hospital in-reach linked to reablement and end of life services |  |  | 50% | 50% | 50% | 50% | 75% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  | Same
Notes: Audit confirmed 100% cover, now examining quality of registers (vol sector supported) SLIC packages of care and community MDTs. Reablement established.
C2 |  | Named professional
|  | SEL |  |  | 0% | 60% | 60% | 60% | 80% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
|  | Named professional assigned to individuals on care register |  |  | 0% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  | Same
|  | Care coordinators/patient liaison established across (see P2) |  |  | 0% | 50% | 50% | 50% | 50% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  | Same
|  | Named professional assigned to others at risk (see C1) |  |  | 0% | 50% | 50% | 50% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
|  | Training for GP practice staff in motivational skills and health coaching (see P3) |  |  | 0% | 50% | 50% | 50% | 75% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | Confirming progress with locality managers | Slower
|  | Training for others within the LCN (including vol sector and health champions) in motivational skills and health coaching (see P3) |  |  | 0% | 50% | 50% | 50% | 75% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | Confirming progress with locality managers | Slower
Notes:
C3 |  | Care Planning
|  | SEL |  |  | 12.5% | 59.17% | 59.17% | 63.33% | 77.5% | 95.83% | 95.83% | 97.92% | 97.92% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
|  | See C1 above |  |  | 25% | 58.33% | 58.33% | 66.67% | 75% | 91.67% | 91.67% | 95.83% | 95.83% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  | Same
|  | See C2 above |  |  | 0% | 60% | 60% | 60% | 80% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
Notes:
C4 |  | Patients supported to manage their health and wellbeing
|  | SEL |  |  | 14.29% | 64.29% | 64.29% | 67.86% | 85.71% | 92.86% | 92.86% | 92.86% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
|  | Asset Mapping (see P2) |  |  | 0% | 50% | 50% | 75% | 75% | 75% | 75% | 75% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  | Slower
|  | Social Prescribing (see P2) |  |  | 0% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  | Same
|  | H&WB champions (see P2) |  |  | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  | Same
|  | Care coordinators (see P2) |  |  | 0% | 50% | 50% | 50% | 50% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  | Same
|  | Health Coaching (see P3) |  |  | 0% | 50% | 50% | 50% | 75% | 75% | 75% | 75% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | Check with locality managers | Slower
|  | Active Programmes in the community (see P4) |  |  | 0% | 50% | 50% | 50% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  | Same
|  | Patient/carer education programmes |  |  | 0% | 50% | 50% | 50% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  | Same
Notes: Patient education commissioned via CEPN
C5 |  | Multi-disciplinary working
|  | SEL |  |  | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
|  | CBC Big Hitter |  |  | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  | Same
Notes: SLIC packages of care and community MDT teams. Holistic health assessments, integrated care managements, CMDT and locality geriatrician

## Lewisham
SEL CBC & Primary Care Delivery Plan |  |  |  |  | Key: |  | Step in progress |  |  |  | Activity begins to be met for some patients
[7 empty] | Step complete |  |  |  | SPG specification delivery date
Predicted pan London delivery date
[6 empty] | 2015 |  |  |  | 2016 |  |  |  | 2017 |  |  |  | 2018 |  |  |  | 2019 |  |  |  | 2020
|  | Lewisham - validated |  |  | Pre-2015 | Q1 April 2015 | Q2 Jul 2015 | Q3 Oct 2015 | Q4 Jan 2016 | Q1 April 2016 | Q2 Jul 2016 | Q3 Oct 2016 | Q4 Jan 2017 | Q1 April 2017 | Q2 Jul 2017 | Q3 Oct 2017 | Q4 Jan 2018 | Q1 April 2018 | Q2 Jul 2018 | Q3 Oct 2018 | Q4 Jan 2019 | Q1 April 2019 | Q2 Jul 2019 | Q3 Oct 2019 | Q4 Jan 2020 | Q1 April 2020 | Q2 Jul 2020 | Q3 Oct 2020 | Q4 Jan 2021 | Dependent activity? | Change from current baseline | Funding required | Funding source | Funding secured | How will we know if it has been delivered (what are our measures?) | Support required from HLP
Spec |  | Examples of supporting activity | Owner | Start | Pre-2015 | Year 1 |  |  |  | Year 2 |  |  |  | Year 3 |  |  |  | Year 4 |  |  |  | Year 5 |  |  |  | Year 6 |  |  |  | Are there activities which must be completed before this activity can be commenced?
| Federations/Alliances | Integrated single system leadership and management |  |  | 0% | 17.86% | 17.86% | 35.71% | 35.71% | 39.29% | 46.43% | 53.57% | 92.86% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
|  | Local Care Networks defined |  |  | 0% | 25% | 25% | 50% | 50% | 75% | 75% | 75% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | Adult Integration Programme - Confirm | Same
|  | Leadership & Common Voice (formal/informal leadership development programmes, local learning sets) |  |  | 0% | 50% | 50% | 50% | 50% | 50% | 50% | 50% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | Adult Integration Programme - Confirm | Same
|  | Access to Expertise (governance, structure development, legal support, business dev. & new models of care) |  |  | 0% | 0% | 0% | 50% | 50% | 50% | 50% | 50% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | Adult Integration Programme - Confirm | Same |  |  |  |  | N/A
|  | Direct Management Support (coaching/mentoring, management/admin staff) |  |  | 0% | 0% | 0% | 50% | 50% | 50% | 50% | 50% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | Adult Integration Programme - Confirm | Same |  |  |  |  | N/A
|  | Time & Headroom (facilitated events and engagement across the network) |  |  | 0% | 50% | 50% | 50% | 50% | 50% | 50% | 50% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | Adult Integration Programme - Confirm | Same
|  | Peer Working & Support (enabling strategies, e.g. workforce, IM&T, Estates and across networks) |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 25% | 50% | 75% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | Adult Integration Programme - Confirm | Slower
|  | LCN leadership team & management structure in place with the 'core' represented/engaged and with clear governance and decision-making arrangements |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 25% | 50% | 75% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | Adult Integration Programme - Confirm | Slower
Notes: four neghbourhood teams established and planning to form the basis of LCN and Federations. Good relationships with local partners, need to develop a shared plan and improve engagement with acutes. Partnership group established and developing the narrative
|  | Federations/Alliances |  |  | 0% | 0% | 38.89% | 50% | 72.22% | 86.11% | 94.44% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
|  | All local GP practices have agreed to an Alliance |  |  | 0% | 0% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
|  | The practices are geographically aligned |  |  | 0% | 0% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
|  | The Alliance has a recognised legal identity |  |  | 0% | 0% | 50% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
|  | The Alliance is registered with the CQC |  |  | 0% | 0% | 0% | 0% | 0% | 25% | 75% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | # CQC Registration - mixed messages with regard to requirement to register # Applications pending with CQC | Slower | N/A | N/A |  | CQC Registered | Provide guidance/best practice on whether registration is needed - confirm this position with CQC
|  | Specification for an enhanced primary care service created and agreed |  |  | 0% | 0% | 0% | 0% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  | Same
|  | Commissioner offer made to Alliance and contract in place following due diligence |  |  | 0% | 0% | 0% | 0% | 50% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  | Same
|  | Alliance leadership, governance & decision-making arrangements in place |  |  | 0% | 0% | 50% | 75% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  | Same
|  | Alliance management structure in place |  |  | 0% | 0% | 50% | 75% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  | Same
|  | 3 to 5 year business plan developed |  |  | 0% | 0% | 0% | 0% | 0% | 50% | 75% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | Four Federations have been set up and currently consoiidating into one Federation, hence delay on business plan | Slower
Notes: see above. Four established neighbourhoods care networks. GP federation leadership capacity an issue. Neighbourhood coordinated primary care service commissioned, supporting collaborative working to agreed outcomes. Legal and business support from July 15
Accessible Care
A1 | Spec | Patient Choice
|  | SEL |  |  | 28.57% | 46.43% | 46.43% | 46.43% | 64.29% | 64.29% | 64.29% | 82.14% | 82.14% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
|  | Patient able to see particular clinician |  |  | 0% | 25% | 25% | 25% | 50% | 50% | 50% | 75% | 75% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  | Same
|  | Patients able to book up to 4 weeks in advance |  |  | 0% | 25% | 25% | 25% | 50% | 50% | 50% | 75% | 75% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  | Same
|  | Support available for non English speakers |  |  | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  | Same
|  | Infrastructure available for accessibility (hearing loops etc.) |  |  | 0% | 25% | 25% | 25% | 50% | 50% | 50% | 75% | 75% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  | Same
|  | Patients able to book at times convenient to them |  |  | 0% | 25% | 25% | 25% | 50% | 50% | 50% | 75% | 75% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  | Same
|  | Improved access to general practice - big hitter scheme |  |  | 0% | 25% | 25% | 25% | 50% | 50% | 50% | 75% | 75% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  | Same
|  | Local Urgent Care Centres/Walk-in centres offering alternatives to GP practice |  |  | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  | Same
Notes: partial achievement but anticipated long lead-in to achieve full coverage
A2 |  | Contacting the practice
|  | SEL |  |  | 0% | 40% | 40% | 40% | 40% | 45% | 45% | 70% | 80% | 95% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
Individual practice level
|  | Telephone booking and triage system available |  |  | 0% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  | Same
|  | Online booking system available |  |  | 0% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  | Same
|  | Online prescription service available |  |  | 0% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  | Same
|  | Medical records available online (functionality available) |  |  | 0% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  | Same
|  | Process/ IT in place to support email consultations |  |  | 0% | 0% | 0% | 0% | 0% | 25% | 25% | 50% | 50% | 75% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | Agreement of PMS Premium (London specification element) Support for IT capital/revenue costs | Same | Yes | TBC | No | Contract Monitoring of PMS premium
|  | Access routes (in particular online) advertised to patients |  |  | 0% | 0% | 0% | 0% | 0% | 25% | 25% | 50% | 50% | 75% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | PMS Core Contract Review | Same | No | N/A | N/A | Contract Monitoring on the Core Contract
Federation level
|  | Able to share medical records |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 50% | 75% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | ETTF Bid - Population Health Management | Slower | Yes | ETTF | Pending | Contractual
|  | Single telephone booking and triage system |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 50% | 75% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | Subejct to extended access offer | Slower | Yes | TBC | TBC | Contractual
|  | Online booking system |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 50% | 75% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | Subejct to extended access offer | Slower | Yes | TBC | TBC | Contractual
|  | Enhanced access options through working as a federation |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 50% | 75% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | Subejct to extended access offer | Slower | Yes | TBC | TBC | Contractual
Notes: Functionality in place with utilisation the greater challenge. Five practice pilots, "connect", developing shared records across primary, community and hospital, with plans to include social care and roll-out
A3 |  | Routine opening hours
|  | SEL |  |  | 0% |  | 75% | 75% | 75% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
|  | All practices open in routine opening times |  |  | 0% | 75% | 75% | 75% | 75% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  | Same
|  | Contracts updated to specify appointments to be offered at these times |  |  | 0% | 75% | 75% | 75% | 75% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  | Same
|  | Workforce requirements met to offer appointments during these times |  |  | 0% | 75% | 75% | 75% | 75% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  | Same
|  | Appointments available at all routine times |  |  | 0% | 75% | 75% | 75% | 75% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  | Same
Notes: 8 - 6 Mon-Fri, 8-12 Sat as part of commissioned neighbourhood primary care service and walk-in centre
A4 |  | Extended opening hours
|  | SEL |  |  | 0% | 16.67% | 25% | 25% | 41.67% | 50% | 50% | 75% | 75% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
|  | Local Urgent Care Centres/Walk-in centres offering extended hours |  |  | 0% | 25% | 25% | 25% | 50% | 50% | 50% | 75% | 75% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | PwC Modelling | Same | Yes | TBC | No | Contractual/GP Patient Survey
|  | Improved access to general practice - big hitter scheme |  |  | 0% | 25% | 25% | 25% | 50% | 50% | 50% | 75% | 75% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | PwC Modelling | Same | Yes | TBC | No | Contractual/GP Patient Survey
|  | 8 to 8 7/7 |  |  | 0% | 0% | 25% | 25% | 25% | 50% | 50% | 75% | 75% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | PwC Modelling | Same | Yes | TBC | No | Contractual/GP Patient Survey
Notes: discussions/planning has commenced (top-up hub proposal)
A5 |  | Same day access
|  | SEL |  |  | 0% | 5% | 5% | 5% | 5% | 50% | 50% | 75% | 75% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
As A4 above, and:
|  | Reablement big hitter encompassing rapid response and supported discharge |  |  | 0% | 0% | 0% | 0% | 0% | 50% | 50% | 75% | 75% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | ACU/Enhanced Care & Supported Discharge Programmes | Slower | Yes | Local | Yes | Contractual/reduced admissions/re-admissions and attendances
|  | Telephone triage - practice |  |  | 0% | 25% | 25% | 25% | 25% | 50% | 50% | 75% | 75% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | Agreement of PMS Premium (Local) | Same | Yes | PMS Contract | Yes | Contractual
|  | Telephone triage - Federation/Alliance |  |  | 0% | 0% | 0% | 0% | 0% | 50% | 50% | 75% | 75% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | Year 2 Commissioner offer to federations (17/18) | Same | Yes | Local | Yes | Contractual
|  | Access to specialist advice and specialist response clinic (U&EC intervention) |  |  | 0% | 0% | 0% | 0% | 0% | 50% | 50% | 75% | 75% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | ACU/Enhanced Care & Supported Discharge Programmes | Slower | Yes | Local | Yes | Contractual
|  | Same day diagnostics (planned Care intervention) |  |  | 0% | 0% | 0% | 0% | 0% | 50% | 50% | 75% | 75% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | ACU/Enhanced Care & Supported Discharge Programmes | Slower | Yes | Local | Yes | Contractual
Notes: telephone triage in place in some practices, to be included in PMS Review. Acute medical and surgical assessment units commissioned
A6 |  | Urgent and Emergency Care
|  | SEL |  |  | 0% | 0% | 12.5% | 12.5% | 12.5% | 50% | 50% | 75% | 87.5% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
|  | All practice personnel trained to identify emergencies |  |  | 0% | 0% | 25% | 25% | 25% | 50% | 50% | 75% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | PMS Core Contract Review (Section 5 - Pg. 4) | Slower
|  | Processes in place to ensure emergencies are appropriately dealt with |  |  | 0% | 0% | 25% | 25% | 25% | 50% | 50% | 75% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | PMS Core Contract Review (Section 5 - Pg. 4) | Slower
|  | Also see reablement above encompassing rapid response |  |  |  | 0% | 0% | 0% | 0% | 50% | 50% | 75% | 75% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | As above A5 | Slower
|  | Also see access to specialist advice and specialist response clinic (U&EC intervention) |  |  |  | 0% | 0% | 0% | 0% | 50% | 50% | 75% | 75% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | As above A5 | Slower
Notes: local CEPN newly established will be responsible for ensuring that staff are trained and processes in place
A7 |  | Continuity of Care
|  | SEL |  |  | 0% | 14.29% | 17.86% | 28.57% | 32.14% | 57.14% | 60.71% | 71.43% | 89.29% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
|  | All patients given a named GP as main contact (over 75s and risk stratified patients currently asper the DES from 2015/16) |  |  | 0% | 50% | 50% | 50% | 50% | 50% | 50% | 50% | 50% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | PMS Core Contract Review/Unplanned Admissions DES | Same | N/A | N/A |  | Contractual
|  | Practice able to give flexible appointment lengths - links to offer/contract with Alliances/Federations |  |  | 0% | 0% | 25% | 50% | 75% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  | Same |  |  |  | Contractual
|  | Assigned life clinician/nurse in final year of life |  |  | 0% | 0% | 0% | 0% | 0% | 25% | 25% | 50% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  | Same |  |  |  | Contractual
|  | Coordinate my care plans for patients identified as in final year of life |  |  | 0% | 25% | 25% | 50% | 50% | 75% | 75% | 75% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | Agreement of PMS Premium (Local) | Slower | Yes | PMS Contract | Yes | Contractual
|  | Able to share medical records |  |  | 0% | 0% | 0% | 0% | 0% | 50% | 50% | 75% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | ETTF Bid | Slower | Yes | ETTF | Pending | Contractual
|  | See reablement above |  |  | 0% | 0% | 0% | 0% | 0% | 50% | 50% | 75% | 75% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  | Same
|  | Multi-disciplinary Teams |  |  | 0% | 25% | 25% | 50% | 50% | 50% | 75% | 75% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  | Slower
Notes: technology to share records in place with one more practice to move to new system. Connect for Care to also connect social care records. Neighbourhood Care Teams part of PC inventive scheme
Proactive Care
P1 |  | Co-Design
|  | SEL |  |  | 0% | 37.5% | 62.5% | 83.33% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
|  | Local strategy and annual plan for user and stakeholder engagement activities including hard to reach groups and communities |  |  | 0% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | Public Engagement Strategy and Charter/Refresh | Same
|  | Borough-wide representative PPV group established and recorded engagement activities taking place |  |  | 0% | 25% | 75% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | Patient Reference Group has been set up with development support | Slower
|  | Active Patient Participation at individual practices/LCNs |  |  | 0% | 25% | 50% | 75% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | PPGs per practice - PMS Core Contract Neighbourhood PPGs as part of Federation Contract | Same
|  | Individual practices inviting and recording comments about services and actively responding |  |  | 0% | 25% | 50% | 75% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | PMS Core Contract - FFT | Same
|  | Local communities and stakeholders actively and routinely involved in priority setting and service redesign and their contributions recorded |  |  | 0% | 25% | 50% | 75% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | Public Engagement Strategy and Charter/Refresh | Same
|  | Variety of channels for communicating with and receiving/recording feedback from service users established |  |  | 0% | 25% | 50% | 75% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | Public Engagement Strategy and Charter/Refresh | Same
Notes: Public engagement plan and strategy. Pt. participation at practice/neighbourhood level part of PC incentive scheme. Patient reference group being established
P2 |  | Developing assets and resources for improving health and wellbeing
|  | SEL |  |  | 50% | 56.25% | 56.25% | 62.5% | 75% | 75% | 81.25% | 81.25% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
|  | Joint Market Position statement/commissioning intentions developed (LA/CCG - with key voluntary sector partners) |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | Adult Joint Strategic Commissioning Group - (Annual) | Same
|  | Local asset map developed with key partners and stakeholders and in place |  |  | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | Adult Integration Programme | Same
|  | Social Prescribing scheme in place |  |  | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | Adult Integration Programme - Community Connections | Same
|  | Developing role of wider primary care team and using more effectively e.g. community pharmacy |  |  | 50% | 50% | 50% | 50% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | LIMOS/Pharmacy First | Same
|  | Local community health and wellbeing champions identified and developed |  |  | 50% | 50% | 50% | 50% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | LTC Champions (Confirm) | Same
|  | Care coordinators/patient liaison established across LCNs |  |  | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | Adult Integration Programme | Same
|  | Primary prevention and public health programmes (obesity, alcohol and smoking) |  |  | 0% | 25% | 25% | 50% | 50% | 50% | 75% | 75% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  | Same
|  | Federation to define the services to be offered and to build on existing provision - links to offer/contract with Alliances/Federations |  |  | 0% | 25% | 25% | 50% | 50% | 50% | 75% | 75% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | Need to confirm what this is?
Notes: Joint commissioning intentions agreed with LA. Neighbourhood Care Team coordinators Diabetes community champions with more being recruited. SPA to advice and information. LIMOS enhanced pharmacy service. Prevention - BCF workstream 15/16
P3 |  | Personal conversations focussed on an individual's health goals
|  | SEL |  |  | 33.33% | 41.67% | 50% | 58.33% | 66.67% | 75% | 83.33% | 91.67% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
|  | Risk stratification tool in place and DES to have goal setting conversations with 2% of population |  |  | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  | Same | Yes | DES | Yes
|  | Training for GP practice staff in motivational skills and health coaching |  |  | 0% | 25% | 50% | 75% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | Collaborative Care Planning Training for all clinicians delivered in 15/16 | Same
|  | Training for others within the LCN (including vol sector and health champions) in motivational skills and health coaching |  |  | 0% | 0% | 0% | 0% | 0% | 25% | 50% | 75% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | Adult Integration Programme - Confirm | Slower
Notes: risk strat PC incentive scheme to achieve 10% over 65s with care plans. Year of Care training model training scheme (locally delivered) 80 of 300 clinicians trained
P4 |  | Health and wellbeing liaison and information
|  | SEL |  |  | 31.25% | 37.5% | 50% | 62.5% | 75% | 75% | 75% | 75% | 75% | 75% | 75% | 75% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
|  | Asset mapping advertised and accessible (hard copy and on-line). See P2 above |  |  | 25% | 25% | 50% | 75% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | Adult Integration Programme - Confirm | Same
|  | Active programmes in the community (i.e. schools, workplaces and other community settings) |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | Adult Integration Programme - Confirm | Same
|  | Care coordinators/navigators/liaison trained in how to access resource. See P2 above |  |  | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | Adult Integration Programme - Confirm | Same
|  | Health champions, carers and service users able to use resources |  |  | 0% | 25% | 50% | 75% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | Adult Integration Programme - Confirm | Same
Notes: Community Programmes, links to BCF scheme and joint commissioning intentions with LA
P5 |  | Patients not currently accessing primary care services
|  | SEL |  |  | 0% | 0% | 6.25% | 18.75% | 25% | 37.5% | 37.5% | 37.5% | 37.5% | 75% | 75% | 75% | 75% | 75% | 75% | 75% | 75% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
|  | Enhanced Call & recall for screening and vaccinations programme targeting hard to reach groups - consider link to Alliance/Federation offer/contract |  |  | 0% | 0% | 0% | 50% | 50% | 50% | 50% | 50% | 50% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | Year 2 Commissioner offer to federations (17/18) | Same
|  | Support to vulnerable people in the community (care homes, extra care housing and domiciliary care) |  |  | 0% |  | 25% | 25% | 50% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | Local contract for enhanced primary medical support for Care Homes | Same | Yes | Local | Yes
|  | Working with local third sector, local authority and community groups to identify people not accessing services and co-design and implement ways of reaching such people |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | Adult Integration Programme - Confirm | Slower
|  | Training for carers and others to recognise symptoms and engage with primary care services |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | Carers Support Service - Reprocuring Service for 17/18 | Faster
Notes: Enhanced Service to care homes to be commissioned from Federations. Improved healthchecks and screening part of neighbourhood PC incentive scheme
Coordinated Care
C1 |  | Case finding and review
|  | SEL |  |  | 16.67% | 33.33% | 33.33% | 37.5% | 54.17% | 70.83% | 75% | 79.17% | 83.33% | 95.83% | 95.83% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
|  | Risk Stratification tool in place, evaluated and further developed |  |  | 50% | 50% | 50% | 50% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  | Same
|  | Active care registers in place |  |  | 50% | 50% | 50% | 50% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  | Same
|  | Extending care registers beyond 2% of the adult population - consider as part of offer/contract with Federation/Alliance |  |  | 0% | 25% | 25% | 25% | 25% | 50% | 50% | 50% | 50% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | Year 1 Commissioner offer to federations (17/18) | Same
|  | Working with local third sector, local authority and community groups to identify people at risk |  |  | 0% | 0% | 0% | 0% | 0% | 25% | 25% | 50% | 50% | 75% | 75% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | Adult Integration Programme - Working Group/Business Case/OHSEL Approach | Slower
|  | Identify people at risk of developing LTCs (see P5) |  |  | 0% | 25% | 25% | 50% | 50% | 50% | 75% | 75% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | Diabetes Prevention Programme | Faster
|  | Hospital in-reach linked to reablement and end of life services |  |  | 0% | 50% | 50% | 50% | 50% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | See reablement | Same
Notes: supported discharge and admissions avoidance team. PC incentive scheme 15/16 to have 10% of over 65s on care registers
C2 |  | Named professional
|  | SEL |  |  | 30% | 40% | 45% | 50% | 65% | 75% | 80% | 85% | 90% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
|  | Named professional assigned to individuals on care register |  |  | 50% | 50% | 50% | 50% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | PMS Core Contract | Same
|  | Care coordinators/patient liaison established across (see P2) |  |  | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  | Same
|  | Named professional assigned to others at risk (see C1) |  |  | 0% | 25% | 25% | 25% | 25% | 50% | 50% | 50% | 50% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
|  | Training for GP practice staff in motivational skills and health coaching (see P3) |  |  | 0% | 25% | 50% | 75% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  | Same
|  | Training for others within the LCN (including vol sector and health champions) in motivational skills and health coaching (see P3) |  |  | 0% | 0% | 0% | 0% | 0% | 25% | 50% | 75% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | Adult Integrted Progamme - to confirm | Slower
Notes:
C3 |  | Care Planning
|  | SEL |  |  | 23.33% | 36.67% | 39.17% | 43.75% | 59.58% | 72.92% | 77.5% | 82.08% | 86.67% | 97.92% | 97.92% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
|  | See C1 above |  |  | 16.67% | 33.33% | 33.33% | 37.5% | 54.17% | 70.83% | 75% | 79.17% | 83.33% | 95.83% | 95.83% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  | Same
|  | See C2 above |  |  | 30% | 40% | 45% | 50% | 65% | 75% | 80% | 85% | 90% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  | Same
Notes:
C4 |  | Patients supported to manage their health and wellbeing
|  | SEL |  |  | 50% | 53.57% | 57.14% | 60.71% | 71.43% | 71.43% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
|  | Asset Mapping (see P2) |  |  | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  | Same
|  | Social Prescribing (see P2) |  |  | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  | Same
|  | H&WB champions (see P2) |  |  | 50% | 50% | 50% | 50% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  | Same
|  | Care coordinators (see P2) |  |  | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  | Same
|  | Health Coaching (see P3) |  |  | 0% | 25% | 50% | 75% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  | Same
|  | Active Programmes in the community (see P4) |  |  | 0% | 0% | 0% | 0% | 0% | 0% | L177 | M177 | N177 | N177 | L178 | M178 | 100% | 100% | L179 | M179 | N179 | N179 | L179 | M179 | N179 | N179 | L179 | M179 | N179 |  | Same
|  | Patient/carer education programmes |  |  | 0% | 0% | 0% | 0% | 0% | 0% | L178 | M178 | N178 | N178 | L179 | M179 | 100% | 100% | L180 | M180 | N180 | N180 | L180 | M180 | N180 | N180 | L180 | M180 | N180 |  | Same
Notes: Self-management programme - diabetes . BC for online diabetes self-management
C5 |  | Multi-disciplinary working
|  | SEL |  |  | 0% | 25% | 25% | 50% | 75% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
|  | CBC Big Hitter |  |  | 0% | 25% | 25% | 50% | 75% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | Adult Integrated Programme - to confirm | Slower
Notes: Neighbourhood Care Teams co-commissioned with LA

## Southwark
[14 empty] | Key: |  | Step in progress |  |  |  | Activity begins to be met for some patients
SEL CBC & Primary Care Delivery Plan | [15 empty] | Step complete |  |  |  | SPG specification delivery date
Predicted pan London delivery date
[6 empty] | 2015 |  |  |  | 2016 |  |  |  | 2017 |  |  |  | 2018 |  |  |  | 2019 |  |  |  | 2020 | [9 empty] | Funding
|  | Southwark |  |  | Pre-2015 | Q1 April 2015 | Q2 Jul 2015 | Q3 Oct 2015 | Q4 Jan 2016 | Q1 April 2016 | Q2 Jul 2016 | Q3 Oct 2016 | Q4 Jan 2017 | Q1 April 2017 | Q2 Jul 2017 | Q3 Oct 2017 | Q4 Jan 2018 | Q1 April 2018 | Q2 Jul 2018 | Q3 Oct 2018 | Q4 Jan 2019 | Q1 April 2019 | Q2 Jul 2019 | Q3 Oct 2019 | Q4 Jan 2020 | Q1 April 2020 | Q2 Jul 2020 | Q3 Oct 2020 | Q4 Jan 2021 | Status | Highlight Report | Exception Report required | Date of report | Key issues and actions | Further support required | Required | Source | Secured | How will we know if it has been delivered (what are our measures?)
Spec |  | Supporting activities | Owner | Start | Pre-2015 | Year 1 |  |  |  | Year 2 |  |  |  | Year 3 |  |  |  | Year 4 |  |  |  | Year 5 |  |  |  | Year 6
| Federations/Alliances | Integrated single system leadership and management |  |  | 35.71% | 64.29% | 67.86% | 78.57% | 82.14% | 85.71% | 85.71% | 92.86% | 96.43% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | Slippage | Geographies, role and purpose defined and aligned to GP Federations. LCNs anticipated to be formal organisational entities by end of 17/18. | No
|  | Local Care Networks defined |  |  | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | Complete
|  | Leadership & Common Voice (formal/informal leadership development programmes, local learning sets) |  |  | 50% | 50% | 50% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | Complete
|  | Access to Expertise (governance, structure development, legal support, business dev. & new models of care) |  |  | 0% | 50% | 50% | 50% | 50% | 50% | 50% | 75% | 75% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | Slippage | LCNs have had access to support including governance advice etc, and are responding to the shared incentive for 3+LTCs/coordinated care. Further resource is required to support transition towards more formal LCN contracting arrangements (e.g. MCP contract). |  |  |  | Advice & learning from Vanguards etc. | 1000000 | GSTC | No | Successful in transitioning to MCP contractual arrangements
|  | Direct Management Support (coaching/mentoring, management/admin staff) |  |  | 0% | 50% | 50% | 50% | 75% | 75% | 75% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | Slippage | Formal recruitment to take place for LCN Chair's (currently interim arrangements in place) and shared Operational Manager |  |  |  |  | 85000 | CCG | No | Successful recruitment within LCNs
|  | Time & Headroom (facilitated events and engagement across the network) |  |  | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | Complete
|  | Peer Working & Support (enabling strategies, e.g. workforce, IM&T, Estates and across networks) |  |  | 0% | 50% | 50% | 50% | 50% | 75% | 75% | 75% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | On track
|  | LCN leadership team & management structure in place with the 'core' represented/engaged and with clear governance and decision-making arrangements |  |  | 0% | 50% | 75% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | Other | Annual governance review taking place with additional resource to be secured as per above (strengthening existing governance & resource for LCNs)
|  | Federations/Alliances |  |  | 72.22% | 88.89% | 94.44% | 94.44% | 94.44% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | Complete | Two federations established (one CiC, one LLP) both covering 2 neighbourhoods each and all practices. Enhanced primary care services and extended opening commissioned - Prime Minister's Challenge Fund (PMCF) | No
|  | All local GP practices have agreed to an Alliance |  |  | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | Complete
|  | The practices are geographically aligned |  |  | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | Complete
|  | The Alliance has a recognised legal identity |  |  | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | Complete
|  | The Alliance is registered with the CQC |  |  | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | Complete
|  | Specification for an enhanced primary care service created and agreed |  |  | 50% | 50% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | Complete
|  | Commissioner offer made to Alliance and contract in place following due diligence |  |  | 0% | 50% | 50% | 50% | 50% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | Complete
|  | Alliance leadership, governance & decision-making arrangements in place |  |  | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | Complete
|  | Alliance management structure in place |  |  | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | Complete
|  | 3 to 5 year business plan developed |  |  | 0% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | Complete
Accessible Care
A1 | Spec | Patient Choice | [29 empty] | No
[5 empty] | 35.71% | 42.86% | 42.86% | 42.86% | 50% | 64.29% | 71.43% | 82.14% | 92.86% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | Slippage
|  | Patient able to see particular clinician |  |  | 0% | 0% | 0% | 0% | 50% | 50% | 75% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | On track
|  | Patients able to book up to 4 weeks in advance |  |  | 0% | 0% | 0% | 0% | 0% | 25% | 25% | 50% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | Slippage | Additional access is offered at our extended primary care service (EPCS) to free up individual practice time to allow pre-bookable appointments for patients but systematic offering of 4 weeks in advance requires full implementation across all practices to ensure consistent offer made in line with their access policy and further use of routine appointments at EPCS. Practices willingness to facilitate and change appointment booking systems is an issue - inclusion in PMS and GMS contracts would enable full delivery.
|  | Support available for non English speakers |  |  | 100% | 100% | 100% | 100% | 50% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | Complete
|  | Infrastructure available for accessibility (hearing loops etc.) |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 25% | 50% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | Slippage | Investment required to cover full infrastructure costs for all practices and federation sites. |  |  |  | Funding and advice on best practice | 200000 | BAU Capital | No | All practices and EPCS sites have infrastructure services for patients to enable full access
|  | Patients able to book at times convenient to them |  |  | 0% | 0% | 0% | 0% | 50% | 75% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | Complete
|  | Improved access to general practice - big hitter scheme |  |  | 50% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | Complete
|  | Local Urgent Care Centres/Walk-in centres offering alternatives to GP practice |  |  | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | Complete | Walk-in centre decommissioned in Nov 2014 and replaced with 8am to 8pm 7 day a week extended primary care service
A2 |  | Contacting the practice | [29 empty] | No
[5 empty] | 55% | 80% | 80% | 80% | 85% | 92.5% | 92.5% | 95% | 97.5% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | Slippage | Patients can access additional GP appointments through their own GP practice rather than a separate telephone system - this is one single point of access for individual patients who are clinically triaged for appropriate appointment booking/advice/signposting. Telephone booking not yet to consistent standard -
|  | Individual practice level | [27 empty] | Complete
|  | Telephone booking and triage system available |  |  | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | Complete
|  | Online booking system available |  |  | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | Complete
|  | Online prescription service available |  |  | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | Complete
|  | Medical records available online (functionality available) |  |  | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | Complete
|  | Process/ IT in place to support email consultations |  |  | 0% | 0% | 0% | 0% | 0% | 25% | 25% | 50% | 75% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | Slippage | Investment required |  |  |  | Funding | 100000 | CCG | No | Process is in place for all practices and their patients to ultilise email to deliver health consultations
|  | Access routes (in particular online) advertised to patients |  |  | 50% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | Complete
|  | Federation level | [27 empty] | Complete - underachieving
|  | Able to share medical records |  |  | 50% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | Complete
|  | Single telephone booking and triage system |  |  | 0% | 0% | 0% | 0% | 50% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | Complete - underachieving | Telephone booking not yet to consistent standard - developing neighbourhood access policy.
|  | Online booking system |  |  | 0% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | Complete - underachieving | Online booking available but not yet to consistent standard - developing neighbourhood access policy.
|  | Enhanced access options through working as a federation |  |  | 50% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | Complete
A3 |  | Routine opening hours | [29 empty] | No
[5 empty] | 0% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | Complete
|  | All practices open in routine opening times |  |  | 0% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | Complete
|  | Contracts updated to specify appointments to be offered at these times |  |  | 0% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | Complete
|  | Workforce requirements met to offer appointments during these times |  |  | 0% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | Other | The workforce requirement is for provider determination. They highlight a shortage of GPs and nurses and practices are finding it difficulte to recruit permanent staff. The CCG has been supporting supervision and training of nurses through the GP federations. The CCG is implementing the practice based pharmacist scheme and urgent care fellows. CCG also asked for 2 GP practices to be included in recent NHSE initiative for those finding it difficult to recruit.
|  | Appointments available at all routine times |  |  | 0% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | Complete
A4 |  | Extended opening hours | [29 empty] | Yes
[5 empty] | 66.67% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | Complete - underachieving
|  | Local Urgent Care Centres/Walk-in centres offering extended hours |  |  | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | Complete | Walk-in centre decommissioned in Nov 2014 and replaced with 8am to 8pm 7 day a week extended primary care service
|  | Improved access to general practice - big hitter scheme |  |  | 50% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | Complete
|  | 8 to 8 7/7 |  |  | 50% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | Complete - underachieving
A5 |  | Same day access | [29 empty] | No
[5 empty] | 40% | 60% | 60% | 60% | 70% | 90% | 90% | 90% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | On track
As A4 above, and:
|  | Reablement big hitter encompassing rapid response and supported discharge |  |  | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | Complete
|  | Telephone triage - practice |  |  | 50% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | Complete
|  | Telephone triage - Federation/Alliance |  |  | 0% | 0% | 0% | 0% | 50% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | On track | Federations have been testing alternative telephone triage systems. This is delivered on a network level.
|  | Access to specialist advice and specialist response clinic (U&EC intervention) |  |  | 50% | 75% | 75% | 75% | 75% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | Other | Review with CLG project manager 'Same day Hot' clinics and geriatrician of the day commissioned and offering access to advice and diagnostics - being evaluated.
|  | Same day diagnostics (planned Care intervention) |  |  | 0% | 25% | 25% | 25% | 25% | 50% | 50% | 50% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | Other | As above
A6 |  | Urgent and Emergency Care | [29 empty] | No
[5 empty] | 33.33% | 87.5% | 93.75% | 93.75% | 93.75% | 93.75% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | Complete | Local CEPNs ensuring that staff are trained and processes in place
|  | All practice personnel trained to identify emergencies |  |  | 0% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | Complete
|  | Processes in place to ensure emergencies are appropriately dealt with |  |  | 0% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | Complete
|  | Also see reablement above encompassing rapid response |  |  | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | Other | See A5 above
|  | Also see access to specialist advice and specialist response clinic (U&EC intervention) |  |  |  | 50% | 75% | 75% | 75% | 75% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | Other | See A5 above
A7 |  | Continuity of Care | [29 empty] | No
[5 empty] | 21.43% | 57.14% | 57.14% | 60.71% | 71.43% | 78.57% | 85.71% | 85.71% | 96.43% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | On track
|  | All patients given a named GP as main contact (over 75s and risk stratified patients currently asper the DES from 2015/16) |  |  | 0% | 50% | 50% | 75% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | Complete
|  | Practice able to give flexible appointment lengths - links to offer/contract with Alliances/Federations |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 50% | 50% | 75% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | On track | Transformation to deliver flexible appointment lengths requires both facilitation and incentives for GPs to change their booking systems. |  |  |  | Funding | 200000 | CCG | No
|  | Assigned clinician/nurse in final year of life |  |  | 0% | 0% | 0% | 0% | 50% | 50% | 50% | 50% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | On track | Structure to be developed to identify and manage patients outside palliative and community matron careload |  |  |  | Funding and best practice. | 200000 | CCG | No
|  | Coordinate my care plans for patients identified as in final year of life |  |  | 0% | 50% | 50% | 50% | 50% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | Complete
|  | Able to share medical records |  |  | 50% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | Complete
|  | See reablement above |  |  | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | Complete
|  | Multi-disciplinary Teams |  |  | 0% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | Complete | MDTs per locality established.
Proactive Care
P1 |  | Co-Design | [29 empty] | No
[5 empty] | 70.83% | 91.67% | 91.67% | 91.67% | 95.83% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | Complete | All practices have PPGs. Community & Stakeholder involvement through localities (federations)
|  | Local strategy and annual plan for user and stakeholder engagement activities including hard to reach groups and communities |  |  | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | Complete
|  | Borough-wide representative PPV group established and recorded engagement activities taking place |  |  | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | Complete
|  | Active Patient Participation at individual practices/LCNs |  |  | 75% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | Complete
|  | Individual practices inviting and recording comments about services and actively responding |  |  | 50% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | Complete | Locality PPGs facilitating PPI
|  | Local communities and stakeholders actively and routinely involved in priority setting and service redesign and their contributions recorded |  |  | 0% | 50% | 50% | 50% | 75% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | Complete
|  | Variety of channels for communicating with and receiving/recording feedback from service users established |  |  | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | Complete
P2 |  | Developing assets and resources for improving health and wellbeing | [29 empty] | No
[5 empty] | 18.75% | 34.38% | 46.88% | 65.62% | 75% | 81.25% | 81.25% | 81.25% | 90.62% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | Slippage
|  | Joint Market Position statement/commissioning intentions developed (LA/CCG - with key voluntary sector partners) |  |  | 0% | 0% | 75% | 75% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | Complete
|  | Local asset map developed with key partners and stakeholders and in place |  |  | 0% | 50% | 50% | 50% | 50% | 50% | 50% | 50% | 75% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | Slippage | Voluntary Care Sector to complete as part of LCN approach to coordinated care
|  | Social Prescribing scheme in place |  |  | 0% | 0% | 0% | 50% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | Complete | Safe and Independent Living via Age UK
|  | Developing role of wider primary care team and using more effectively e.g. community pharmacy |  |  | 25% | 25% | 50% | 50% | 50% | 75% | 75% | 75% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | Slippage | Community Pharmacy leadership programme linked to GP & Pharmacy Federation working & Federations to roll-out general practice based pharmacists service model. Development of wider primary care to deliver contracts requires CP federations to be set up. |  |  |  |  | 200000 | CCG | No | Community pharmacies set up federations in line with GP federation/LCN
|  | Local community health and wellbeing champions identified and developed |  |  | 0% | 0% | 0% | 50% | 50% | 50% | 50% | 50% | 75% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | Slippage | Some champions already in place & Primary Care Navigation training underway incl. voluntary sector. More standardised approach to be developed as part of LCN approach to coordinated care
|  | Care coordinators/patient liaison established across LCNs |  |  | 25% | 50% | 50% | 50% | 50% | 75% | 75% | 75% | 75% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | Slippage | A number of roles exist within LCNs. Review will form part of LCN approach to coordinated care for people with 3+ LTCs
|  | Primary prevention and public health programmes (obesity, alcohol and smoking) |  |  | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | Complete
|  | Federation to define the services to be offered and to build on existing provision - links to offer/contract with Alliances/Federations |  |  | 0% | 50% | 50% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | Complete | Federation contracts to build upon existing provision
P3 |  | Personal conversations focussed on an individual's health goals | [29 empty] | No
[5 empty] | 25% | 58.33% | 66.67% | 66.67% | 91.67% | 91.67% | 91.67% | 91.67% | 91.67% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | Slippage | New risk strat tool commissioned. Training linked to care planning and incorporated within Every Contact Counts element of development plan.
|  | Risk stratification tool in place and DES to have goal setting conversations with 2% of population |  |  | 75% | 75% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | Complete
|  | Training for GP practice staff in motivational skills and health coaching |  |  | 0% | 50% | 50% | 50% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | Complete
|  | Training for others within the LCN (including vol sector and health champions) in motivational skills and health coaching |  |  | 0% | 50% | 50% | 50% | 75% | 75% | 75% | 75% | 75% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | Slippage | Training exists within individual organisations. System approach needs to be in place to form part of LCN response to system-wide incentive for coordinated care & be supported by CEPN.
P4 |  | Health and wellbeing liaison and information | [29 empty] | No
[5 empty] | 12.5% | 43.75% | 50% | 56.25% | 62.5% | 62.5% | 62.5% | 68.75% | 68.75% | 93.75% | 93.75% | 93.75% | 93.75% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | Slippage
|  | Asset mapping advertised and accessible (hard copy and on-line) |  |  | 0% | 50% | 50% | 50% | 50% | 50% | 50% | 75% | 75% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | Slippage | Engaging VCS through LCNs to support system wide incentive for coordinated care.
|  | Active programmes in the community (i.e. schools, workplaces and other community settings) |  |  | 0% | 50% | 50% | 50% | 50% | 50% | 50% | 50% | 50% | 75% | 75% | 75% | 75% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | Slippage | Some liaison has taken place through NDP programme and CYPHP. Further review to be undertaken through LCNs Intending to roll-out healthy living pharmacies in association with LA.
|  | Care coordinators/navigators/liaison trained in how to access resource |  |  | 0% | 25% | 50% | 75% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | On track | Care navigator/coordinator training on-going
|  | Health champions, carers and service users able to use resources |  |  | 50% | 50% | 50% | 50% | 50% | 50% | 50% | 50% | 50% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | Slippage | Asset mapping through LCNs.
P5 |  | Patients not currently accessing primary care services | [29 empty] | No
[5 empty] | 12.5% | 31.25% | 31.25% | 50% | 50% | 68.75% | 87.5% | 93.75% | 93.75% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | Slippage | Part of development plan
|  | Enhanced Call & recall for screening and vaccinations programme targeting hard to reach groups - consider link to Alliance/Federation offer/contract |  |  | 0% | 25% | 25% | 50% | 50% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | Complete
|  | Support to vulnerable people in the community (care homes, extra care housing and domiciliary care) |  |  | 0% | 25% | 25% | 50% | 50% | 50% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | On track | Homes with nursing beds receive an enhanced primary care service with MDT approach.
|  | Working with local third sector, local authority and community groups to identify people not accessing services and co-design and implement ways of reaching such people |  |  | 0% | 25% | 25% | 50% | 50% | 75% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | On track
|  | Training for carers and others to recognise symptoms and engage with primary care services |  |  | 50% | 50% | 50% | 50% | 50% | 50% | 50% | 75% | 75% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | Slippage | Will be reviewed as part of LCN approach to coordinated care. Need to link to carers assessment.
Coordinated Care | [31 empty] | No
C1 |  | Case finding and review
[5 empty] | 33.33% | 58.33% | 58.33% | 58.33% | 79.17% | 83.33% | 83.33% | 83.33% | 91.67% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | Slippage | SLIC packages of care and community MDTs. Health living pharmacies initiative.
|  | Risk Stratification tool in place, evaluated and further developed |  |  | 0% | 50% | 50% | 50% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | Complete | New risk tool commissioned.
|  | Active care registers in place |  |  | 0% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | Complete
|  | Extending care registers beyond 2% of the adult population - consider as part of offer/contract with Federation/Alliance |  |  | 50% | 50% | 50% | 50% | 50% | 50% | 50% | 50% | 50% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | Slippage | Planning expansion of cohort through system wide incentive coordinated through LCNs
|  | Working with local third sector, local authority and community groups to identify people at risk |  |  | 50% | 50% | 50% | 50% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | Complete
|  | Identify people at risk of developing LTCs (see P5) |  |  | 50% | 50% | 50% | 50% | 50% | 50% | 50% | 50% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | On track
|  | Hospital in-reach linked to reablement and end of life services |  |  | 50% | 50% | 50% | 50% | 75% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | Complete
C2 |  | Named professional | [29 empty] | Yes
[5 empty] | 10% | 30% | 45% | 55% | 60% | 65% | 65% | 80% | 80% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | Slippage
|  | Named professional assigned to individuals on care register |  |  | 0% | 0% | 50% | 75% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | Complete
|  | Care coordinators/patient liaison established across (see P2) |  |  | 50% | 50% | 50% | 50% | 50% | 75% | 75% | 75% | 75% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | Slippage | A number of roles exist within LCNs. Review will form part of LCN approach to coordinated care via system wide incentive
|  | Named professional assigned to others at risk (see C1) |  |  | 0% | 0% | 25% | 50% | 50% | 50% | 50% | 75% | 75% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | Slippage | Named GP in place. Standardised approach to named professional is part of system wide incentive for coordinated care via LCNs which is in the progress of being agreed.
|  | Training for GP practice staff in motivational skills and health coaching (see P3) |  |  | 0% | 50% | 50% | 50% | 50% | 50% | 50% | 75% | 75% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | Slippage
|  | Training for others within the LCN (including vol sector and health champions) in motivational skills and health coaching (see P3) |  |  | 0% | 50% | 50% | 50% | 50% | 50% | 50% | 75% | 75% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | Slippage
C3 |  | Care Planning | [29 empty] | No
[5 empty] | 21.67% | 44.17% | 51.67% | 56.67% | 69.58% | 74.17% | 74.17% | 74.17% | 78.33% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | On track
|  | See C1 above |  |  | 33.33% | 58.33% | 58.33% | 58.33% | 79.17% | 83.33% | 83.33% | 83.33% | 91.67% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | On track
|  | See C2 above |  |  | 10% | 30% | 45% | 55% | 60% | 65% | 65% | 65% | 65% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | On track
C4 |  | Patients supported to manage their health and wellbeing | [29 empty] | Yes
[5 empty] | 3.571% | 35.71% | 35.71% | 50% | 64.29% | 71.43% | 71.43% | 71.43% | 78.57% | 96.43% | 96.43% | 96.43% | 96.43% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | Slippage | Diabetes, CYP and self-management education programmes in place
|  | Asset Mapping (see P2) |  |  | 0% | 50% | 50% | 50% | 50% | 50% | 50% | 50% | 75% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | Slippage | VCS to complete as part of LCN approach to coordinated care
|  | Social Prescribing (see P2) |  |  | 0% | 0% | 0% | 50% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | Complete
|  | H&WB champions (see P2) |  |  | 0% | 0% | 0% | 50% | 50% | 50% | 50% | 50% | 75% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | Slippage | Some champions already in place & Primary Care Navigation training underway incl. voluntary sector. More standardised approach to be developed as part of LCN approach to coordinated care
|  | Care coordinators (see P2) |  |  | 25% | 50% | 50% | 50% | 50% | 75% | 75% | 75% | 75% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | Slippage | A number of roles exist within LCNs. Review will form part of LCN approach to coordinated care for people with 3+ LTCs once incentive is agreed and implemented.
|  | Health Coaching (see P3) |  |  | 0% | 50% | 50% | 50% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | Complete
|  | Active Programmes in the community (see P4) |  |  | 0% | 50% | 50% | 50% | 50% | 50% | 50% | 50% | 50% | 75% | 75% | 75% | 75% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | Slippage | Some liaison has taken place through NDP programme and CYPHP. Further review to be undertaken through LCNs
|  | Patient/carer education programmes |  |  | 0% | 50% | 50% | 50% | 50% | 75% | 75% | 75% | 75% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | Slippage | Some programmes in place but need to consolidate through LCN approach to coordnated care & look to roll-out to other cohorts as appropriate.
C5 |  | Multi-disciplinary working | [29 empty] | No
[5 empty] | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | Complete
|  | CBC Big Hitter |  |  | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | Complete | CMDTs already in place across each LCN. MDT working is being reviewed as part of LCN approach to coordinated care via system-wide incentive

## Sheet1 (hidden)
Spec Number | Spec Name | Detail | Elements |  | What will patients notice?
A1 | Patient Choice | Patients will be given a choice of access options and should be able to decide on the consultation most appropriate for their needs | Continuity over rapid access
|  |  | Seeing a particular clinician |  | Dependant on GPs being able to be assignbed
|  |  | Convenient appointment time |  | Dependant on routine/ extended opening hours
|  |  | Booking more than 4 weeks in advance | IT
Support for non english speaker
|  |  | Adhere to equality requirements such as hearing loops | Estates
A2 | Contacting the practice | Patients will be required to only make one call, click or contact in order to make an appointment. Primary care teams will maximise the use of technology and actively promote online services to patients including appointment booking, online prescriptions, viewing medical records and email consultations | Telephone booking system available (individual practice) | IT
|  |  | Callback/ triage system | IT
|  |  | Online booking system available enabled (individual practice) | IT
Online booking system advertised
|  |  | Online prescription system available | IT
|  |  | Medical records available (individual practice) | IT
|  |  | Email consultations | IT
Online systems advertised
|  |  | Medical records shared between federated practices? | IT
A3 | Routine opening hours | Patients will be able to access pre-bookable appointments at all practices 8am - 6.30pm Monday to Friday and 8am - 12pm Saturday | All practices are open at these times | Contracts
|  |  | Sufficient workforce to be able to see patients at these times | Workforce
|  |  | All practices offer appointments at these times | Contracts
A4 | Extended opening hours | Patients will be able to access a GP or other Primary Care Professionals 7 days a week, 12 hrs per day (8am - 8pm) for pre-bookable and unscheduled appointments | Federations in place | Federations
|  |  | Able to contract with federations | Federations
|  |  | Extended opening hours contracts in place | Contracts
|  |  | Federations sharing medical records | IT
A5 | Same day access | Patients who want to be seen the same day will be able to have a consultation with a GP or appropriately skilled nurse on the same day within routine surgery hours | Triage available (may be the over the phone or face to face) | Likely IT/ Provider development
A6 | Urgent and Emergency Care | Patients with urgent or emergency needs will be clinically assessed rapidly. Practices should have systems in place and skilled staff to ensure these patients are effectively identified and responded to appropriately. | All practice personnel trained to identify emergencies | Provider development
|  |  | Procedures in place to follow if required | Provider development
A7 | Continuity of Care | All patients will be registered with a named GP who is responsible for providing an ongoing relationship for care coordination and care continuity. Practices will provide flexible lengths as appropriate | All patients given a named GP | Provider development
|  |  | Workforce sufficient to provide further coordination of care | Workforce
|  |  | Practice able to give multiple length appointments |  | Dependant on triage systems
|  |  | Workforce new roles & re-tooling supports GPs with further workforce coordination | Workforce

## Inputs (hidden)
each step has here been assigned an equal weighting
Integrated single system leadership and management | Progress Weighting | CCG | 2014/15 GP registered population
Local Care Networks defined | 14.29% | Bexley | 231274.427
Leadership & Common Voice (formal/informal leadership development programmes, local learning sets) | 14.29% | Bromley | 339928.7902
Access to Expertise (governance, structure development, legal support, business dev. & new models of care) | 14.29% | Greenwich | 276753.9401
Direct Management Support (coaching/mentoring, management/admin staff) | 14.29% | Lambeth | 371185.3341
Time & Headroom (facilitated events and engagement across the network) | 14.29% | Lewisham | 305700.1542
Peer Working & Support (enabling strategies, e.g. workforce, IM&T, Estates and across networks) | 14.29% | Southwark | 308760.2399
LCN leadership team & management structure in place with the 'core' represented/engaged and with clear governance and decision-making arrangements | 14.29% | SEL | 1833602.8854
each step has here been assigned an equal weighting
Federations/Alliances | Progress Weighting
All local GP practices have agreed to an Alliance | 11.11%
The practices are geographically aligned | 11.11%
The Alliance has a recognised legal identity | 11.11%
The Alliance is registered with the CQC | 11.11%
Specification for an enhanced primary care service created and agreed | 11.11%
Commissioner offer made to Alliance and contract in place following due diligence | 11.11%
Alliance leadership, governance & decision-making arrangements in place | 11.11%
Alliance management structure in place | 11.11%
3 to 5 year business plan developed | 11.11%

## Look Ups (hidden)
Time | Lookup value | Specifications
Pre-2015 | 4 | Patient Choice
Q1 April 2015 | 5 | Contacting the practice
Q2 Jul 2015 | 6 | Routine opening hours
Q3 Oct 2015 | 7 | Extended opening hours
Q4 Jan 2016 | 8 | Same day access
Q1 April 2016 | 9 | Urgent and Emergency Care
Q2 Jul 2016 | 10 | Continuity of Care
Q3 Oct 2016 | 11 | Co-Design
Q4 Jan 2017 | 12 | Developing assets and resources for improving health and wellbeing
Q1 April 2017 | 13 | Personal conversations focussed on an individual's health goals
Q2 Jul 2017 | 14 | Health and wellbeing liaison and information
Q3 Oct 2017 | 15 | Patients not currently accessing primary care services
Q4 Jan 2018 | 16 | Case finding and review
Q1 April 2018 | 17 | Named professional
Q2 Jul 2018 | 18 | Care Planning
Q3 Oct 2018 | 19 | Patients supported to manage their health and wellbeing
Q4 Jan 2019 | 20 | Multi-disciplinary working
Q1 April 2019 | 21
Q2 Jul 2019 | 22
Q3 Oct 2019 | 23
Q4 Jan 2020 | 24
Q1 April 2020 | 25
Q2 Jul 2020 | 26
Q3 Oct 2020 | 27
Q4 Jan 2021 | 28

## Graph build (hidden)
Time | Q1 April 2018
Specification | Health and wellbeing liaison and information
|  | Integrated single system leadership and management | Federations/Alliances | Patient Choice | Contacting the practice | Routine opening hours | Extended opening hours | Same day access | Urgent and Emergency Care | Continuity of Care | Co-Design | Developing assets and resources for improving health and wellbeing | Personal conversations focussed on an individual's health goals | Health and wellbeing liaison and information | Patients not currently accessing primary care services | Case finding and review | Named professional | Care Planning | Patients supported to manage their health and wellbeing | Multi-disciplinary working | Health and wellbeing liaison and information
1 | SEL | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 94.89% | 100% | 100% | 100% | 99.55% | 100% | 100%
2 | Bexley | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 96.43% | 100% | 100%
3 | Bromley | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
4 | Greenwich | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 93.75% | 100% | 100% | 100% | 100% | 100% | 100%
5 | Lambeth | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
6 | Lewisham | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 75% | 100% | 100% | 100% | 100% | 100% | 100%
7 | Southwark | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
|  | Bexley | Bromley | Greenwich | Lambeth | Lewisham | Southwark | SEL
| Local Care Networks defined | 100% | 100% | 100% | 100% | 100% | 100% | 100%
| Leadership & Common Voice (formal/informal leadership development programmes, local learning sets) | 100% | 100% | 100% | 100% | 100% | 100% | 100%
| Access to Expertise (governance, structure development, legal support, business dev. & new models of care) | 100% | 100% | 100% | 100% | 100% | 100% | 100%
| Direct Management Support (coaching/mentoring, management/admin staff) | 100% | 100% | 100% | 100% | 100% | 100% | 100%
| Time & Headroom (facilitated events and engagement across the network) | 100% | 100% | 100% | 100% | 100% | 100% | 100%
| Peer Working & Support (enabling strategies, e.g. workforce, IM&T, Estates and across networks) | 100% | 100% | 100% | 100% | 100% | 100% | 100%
| LCN leadership team & management structure in place with the 'core' represented/engaged and with clear governance and decision-making arrangements | 100% | 100% | 100% | 100% | 100% | 100% | 100%
|  | Bexley | Bromley | Greenwich | Lambeth | Lewisham | Southwark | SEL
| All local GP practices have agreed to an Alliance | 100% | 100% | 100% | 100% | 100% | 100% | 100%
| The practices are geographically aligned | 100% | 100% | 100% | 100% | 100% | 100% | 100%
| The Alliance has a recognised legal identity | 100% | 100% | 100% | 100% | 100% | 100% | 100%
| The Alliance is registered with the CQC | 100% | 100% | 100% | 100% | 100% | 100% | 100%
| Specification for an enhanced primary care service created and agreed | 100% | 100% | 100% | 100% | 100% | 100% | 100%
| Commissioner offer made to Alliance and contract in place following due diligence | 100% | 100% | 100% | 100% | 100% | 100% | 100%
| Alliance leadership, governance & decision-making arrangements in place | 100% | 100% | 100% | 100% | 100% | 100% | 100%
| Alliance management structure in place | 100% | 100% | 100% | 100% | 100% | 100% | 100%
| 3 to 5 year business plan developed | 100% | 100% | 100% | 100% | 100% | 100% | 100%